The Immunization Data Quality Audit (DQA)

Madagascar, Year 2004

Picture: CSB Bemanevika, Sambava

English Summary Report for GAVI

by The Swiss Centre for International Health®

Swiss Tropical Institute

14 November 2005

By

Marcel Braun

Abdoulkarim Nassirou

# Table of Contents

Table of Contents	2

Acknowledgements	3

Abbreviations	4

1.	Background	5

2.	Objectives of the data quality audit	6

3.	Methodological Approach	6

4.	Findings	7

4.1 National Level	7

4.2	Niveau district	9

4.3	Health Unit Level	10

5.	Recommandations	11

Preamble

This report has been compiled for the Global Alliance for Vaccines and Immunization (GAVI). The statements and opinions expressed in this report are those of the auditors and do not necessarily represent the opinion of the agency. For detailed results and further information please consult the French version of this report.

# Acknowledgements

The audit team would like to thank all those who have participated in this review and made their valuable time available throughout the mission. Our special thanks go out to the administrative authorities and especially to Dr. Randriamanalina Bakolalao, Coordinator of the Expanded Program on Immunization (EPI) of the Ministry of Health and Family Planning for her support and full co-operation. We would also like to express our gratitude towards the district teams of Sambava, Toliary I, Mahajanga I and Anjozorobe who accompanied the two auditing groups during their field work.

In particular, the audit team would like to thank Dr Rabialahy Célestine and Rakotondrazaka Célestin – the two national experts appointed by the Ministry of Health and Family Planning - for their availability and valuable input during data collection.

In addition, the auditors herewith thank the WHO and the UNICEF for their support and Bonaventure Savadogo for the revision of the report.

# Abbreviations

AD 	auto-disable syringe

AFR 	Member States belonging to the WHO African Region

AFRO 	WHO Regional Office for Africa

AQD	Audit de la Qualité des Données

BCG 	bacille Calmette-Guérin (vaccine against tuberculosis)

CBAW 	childbearing aged women

CI 	core indicator

CS	Centre de Santé

DHS 	Demographic and Health Survey

Dip 	diphtheria vaccine

DS	District de Santé

DT 	diphtheria and tetanus toxoid vaccine

DTaP 	diphtheria and tetanus toxoid with acellular pertussis vaccine

DTP 	diphtheria-tetanus-pertussis vaccine

DTP3 	third dose of diphtheria-tetanus-pertussis vaccine

DTPHep 	Tetravalent diphtheria and tetanus toxoid with pertussis and hepatitis B vaccine

DQA	Data Quality Audit

EPI 	Expanded Programme on Immunization 30 cluster survey

FV	Facteur de vérification

GAVI 	Global Alliance for Vaccines and Immunization

GNP 	gross national product

GDP 	gross domestic product

HBV 	hepatitis B virus

HepA 	hepatitis A vaccine

HepB 	hepatitis B vaccine

HepB3 	third dose of hepatitis B vaccine

Hib 	Hæmophilus influenzæ type b vaccine

Hib3 	third dose of Hæmophilus influenzæ type b vaccine

ICC 	inter-agency coordinating committee

IPV 	inactivated polio vaccine

ITS	Institut Tropical Suisse

IVB 	WHO's Department of Immunization, Vaccines and Biologicals

MCV 	measles-containing vaccine

MCV1 	first dose of measles-containing vaccine

MCV2 	second dose of measles-containing vaccine

MICS 	Multiple Indicator Cluster Survey

MinSanPF 	Ministère de la Santé et du Planning Familiale

MSPF	Ministère de la Santé et du planning Familiale

NT 	neonatal tetanus

OMS	Organisation Mondiale de la Santé

OPV3 	third dose of oral polio vaccine

PEV	Programme Elargie de Vaccination du MSP

POL3 	third dose of polio vaccine

RMA	Rapport Mensuel d’Activité

SCIH	Swiss Centre for International Health

SSSa 	Service de Statisitque Sanitaire

TT 	tetanus toxoid vaccine

TT2plus 	second and subsequent doses of tetanus toxoid

UNICEF 	United Nations Childrens Fund

VAA	Vaccin Anti-amarile

VAD 	vitamin A deficiency

VAR 	Vaccin Anti-rougeole

VATT2+	Vaccin Anti-tétanique

VF 	Vaccine Fund

VitA 	first-dose of vitamin A supplement

VPD 	vaccine-preventable diseases

WHO 	World Health Organization

YFV 	yellow fever vaccine

# 1.	Background

The Global Alliance for Vaccines and Immunization (GAVI) is a partnership between the public and private sector. It aims at protecting people’s health, especially the health of children, through the widespread use of vaccines with a particular emphasis on developing countries.

Data inconsistencies are frequently reported, thus the importance of evaluating and improving the quality of a countries immunization and reporting system. To do so, GAVI uses a standardized Data Quality Audit. The DQA verifies the consistency of reporting systems based on the proportion of third doses of diphtheria-tetanus-pertussis administered to children younger than 12 months reported and actually recounted in written documentation found at three levels of the health system (national, district and health unit).

Since 2001 Madagascar is one of the beneficiary countries of GAVI. The financial support year to date sum up to over USD 10 million and have been spent on the purchase of vaccines and parts have been used to improve vaccination services and vaccine safety.

The Expanded Program on Immunization (EPI) of the Ministry of Health and Family Planning was set-up in 1985. In this context in order to preserve and improve the health of the children, the PEV introduced the strategy « Approche District » in 2003. The partners of the PEV, particularly the WHO and UNICEF gave technical and financial support. This new approach introduced the micro planning to basic levels (Community, CSB and district) and has been implemented in 2004 and 2005.

The general objectives of the PEV until 2006 are:

- To reach at least a vaccine cover rate of 80 % for all the antigens and in at least 80% of the districts.

- Eradication of Polio

- Control of measles

- Elimination of neonatal and maternal tetanus

The strategies are:

- Reinforcement of the advanced and mobile strategies for the improvement of the vaccination coverage, in particular of the population difficult to reach with the assistance of the community and the implementation of the "ACD" approach to reach each district

- Improvement of the safety of the injections and the waste management

- Introduction of links between the administration of the vaccines with the services of other interventions which have an impact on the reduction of infantile and maternal mortality and morbidity (PCIME, fight against malaria, vitamin A supplementation, etc)

- Reinforcement of the vaccination and the monitoring within the frame of Health sector reforms in order to reinforce the systems of vaccination and to accelerate the fight against the diseases (on level of health workers, equipment and materials, follow-up and evaluation, improvement of the data management, etc.)

The evolution of vaccination coverage rates are displayed in following graph:

# 2.	Objectives of the data quality audit

The specific objectives of GAVI and the DQA in Madagascar were to:

- Assess the quality, accuracy, timeliness, and completeness of administrative immunization reporting system

- Verify the accuracy of reported DTP3<1 vaccinations in the calendar year 2004

- Estimate the National Verification Factor (recounted/reported) for use in the allocation of GAVI fund shares.

- Indicate to national authorities and institutions involved in vaccination activities in Madagascar the potential ways for improving the reporting system

# 3.	Methodological Approach

The Data Quality Audit in Madagascar was conducted from 09 October – 26 October 2005 and relied on tools and procedures developed by the WHO. Consequently the work focused on three levels: (1) the national, (2) the district, and (3) the health unit level

Following standard procedures of GAVI, four districts and 24 health units were randomly selected in order to assess the quality and accuracy of the immunization and reporting system by verifying the reported and recounted DTP 3<1 administered in the year 2004.

Using these standard procedures the following 4 districts and 24 Health Units (6 Health Units per District) were randomly selected.

| Sambava | Farahalana, Anjangoveratra, Bemanevika, Morafeno, Nosiarina, Ambohimalaza |
| --- | --- |
| Mahajanga I | Mahabibo, Tanambao, Mahavoky, Amborovy, Antanimasaja, Espace Medical |
| Anjozorobe | Anjozorobé, Antanaetibe, Mangamila, Bongatsara, Andanona, Soavinarivo |
| Toliary I | Tsimenatse, Tanambao, Betania, Mahavatse II, Clinique St Luc, Jirama |

The standardized tools used consisted of a log book where all information gathered during daily auditing activities were recorded, such as answers to quality questions, the number of DTP3<1 vaccinations recounted vs. reported, debriefing notes etc.; a set of child health cards and a master workbook (Excel) which contained all collected data.

Two teams were formed consisting of external auditors and a national expert in charge or involved in the EPI programme. The national experts received a one day introductory seminar on DQA and the tools to be used. Concerning logistical issues, selected districts and health units were informed prior to the audit visit.

A final presentation of the findings was given on 26 October 2005 during a meeting at national level. Representatives from the Ministry of Health and Family Planning including EPI, UNICEF, WHO Santé Net and USAID attended this meeting. Subsequent to the debriefing, national authorities were invited to comment on the recommendations.

# 4.	Findings

## 4.1 National Level

The DQA in Madagascar estimated the verification factor (vaccinations recounted/reported for DTC3<1 in 2004) at 100.2 %.

The following figures present the results for reported DTP3<1 (2004) and the Quality of the System Index Score (70.0%) for the national level.

Figure 1 Reported DTP3<1 for the year 2004 by source

Figure 2 Quality of the System Index by Component

One major issue to mention is that the immunization data of the CHD (Centre Hospitalier de District) and the CHR (Centre Hospitalier Régional) is not taken into account by the PEV.

At national level, the audit observed:

National Level:

Strengths::

Data collection and data registration - Existing registries for vaccines - Registering of received vaccines in 2004 - Usage of the PEV tools in the districts - Handling of the 2004 reports - Registering of the vaccine batch numbers and the expiry dates

Archive / Reporting - Existence of a back up system for PEV data - Existence of an electronic folder with all PEV data by district (2005) - Archiving of the reports by year and district (2005)

Monitoring and Evaluation - Diagrams, tables et curves with performance of the PEV are clearly visible - Monitoring table of drop out’s existing, actual and complete - Reports are marked with the date of reception - Monitoring of stock outs and supervision activities in the districts

Denominator - Utilization of the denominators is conform WHO recommendation (Children surviving 0-11 months (but only for the joint report WHO /UNICEF and the GAVI reports) - Adjustment of the denominators with the populations growth

System conception - Usage of an integrated reporting system at all levels - Uniform reporting forms - Syringe stock ledger kept - Possibility to supervise the expiry dates and the LOT numbers of vaccines in the stock ledger (from 2005 onwards) - Monitoring of the received district reports

Points to be improved

Data collection and data registration - The vaccine stock ledger is not actualized every day - The vaccine stock ledger does not mention exceptional deregistration (outdated, broken, unreadable labels etc) - The warehousing of the vaccines and the syringes do not allow a fast identification or a fast and clear inventory (expiry date, LOT/ Batch number)

Archive / Reporting - Missing IT network or defined procedure for data transfer

Monitoring and Evaluation - Missing reporting forms for retro information for the different levels - Missing predefined forms to create and reproduce punctual information out of the IT system

Denominator - The denominators on national level are different to those on district level - The proportion of children per vaccination strategy is not known - The denominator use is not in line with the WHO recommendation

System conception - The immunization data of the CHD (Centre Hospitalier de District) and the CHR (Centre Hospitalier Régional) is not taken into account by the PEV as they do not report with the RMSD - The used CSB reports do not allow the follow up of vaccine wastage - Missing procedure about the treatment of late reporting - Absence of a follow up system and reporting of individual adverse effects of the vaccines on CSB level towards the DS and the national level - Stock outs on PEV tools in 2004 (children register cards, stock ledgers, tally sheets, etc)

## District Level

At district level, the audit observed:

Quality of System Index Score for the four districts:

| District de Sambava | 81.8% |
| --- | --- |
| District de Mahajanga I | 86.8% |
| District de Toliary I | 97.3% |
| District de Anjazorobe | 84.2% |

Distric Level:

Strengths::

Demography / Planning - The child and CBAW denominators by district are based on actualized population growth data - The target number of children and CBAW to vaccinate are defined - Existence of an annual action plan at District Level - Map in the District are existing and clearly visible - All programs are using the same target numbers

Monitoring and Evaluation - Diagram of vaccine coverage existing clearly visible - Table of monitoring of drop outs existing clearly visible - Organization of regular meetings for the heads of the Health Units (CSB) - Monitoring of late reporting - Monitoring of activities and supervision

Data collection and data registration - Stock management of vaccines and syringes - Usage of the same uniform templates for the monthly reports

Archive - The archiving of data is performed

Points to be improved

Demography / Planning - The denominator use is not in line with the WHO recommendation (Children surviving 0-11 months) - The proportion of children per vaccination strategy is not known and no corresponding map

Monitoring and Evaluation - For 2004: absence of supervision of vaccine wastage at health unit level (CSB) - For 2004: vaccine coverage tabulation by CSB not available in some districts (electronic version) - Weak follow up on health unit activities - Insufficient technical support of the EMAD at CSB level - Procedures of data transfer insufficiently defined - Printing date or date of document creation not mentioned - No standardized tally sheet in 2004 - The incoming CSB reports are not regularly dated and marked in some districts (reception date)

## 4.3	Health Unit Level

At health unit level, the audit observed:

Health Unit Level:

Strengths:

Archive / Reporting - The reports for the audit year of the CSB have been available - The filing system permits to retrieve easily and fast all relevant documents

Monitoring and Evaluation - Map of the CSB available (to particularize) - Existence of CSB micro plans - Target of children and pregnant women to vaccinate were always defined - All programs used the target figures - Diagram of the vaccine coverage available - Monitoring table of drop out rates made and used - Inventory control of vaccines and syringes

Points to be improved

Monitoring and Evaluation - Sometimes absence of vaccine waste monitoring - Absence of mechanism to seek for "lost of sight" in some CSB - Data not always used to improve the vaccine coverage

Data collection and recording - Unsatisfying usage of the registers or the tally sheets, stock ledgers in some CSB - No systematic vaccine stock monitoring by batch number and expiry dates

Archive / Reporting: - Absence of a follow up system and reporting of individual adverse effects of the vaccines on CSB level towards the DS and the national level

# 5.	Recommendations

National Level:

- To keep up to date the vaccine stock register and to record the exceptional exits systematically

- To adapt a clear procedure of vaccine and consumables storage to allow their easy identification

- To introduce a standardized tally sheet

- To work out a retro information form for the lower levels

- To set up a functional network or a procedure for the electronic data transfer

- To standardize the denominators of the national level with those of the district

- To register the proportion of children vaccinated by strategy

- To introduce the use of the denominator recommended by WHO into the programs

- To enter PEV data of the CHD and CHR in the reporting system of the districts

- To collect information via the forms used by the CSB and the districts allowing a follow-up of vaccine wastage

- To set up a written procedure describing the way late reports will be treated

- To set up a system of follow-up and reporting of the individual cases of adverse effects of the vaccines

- To ensure the permanent provision of PEV material at lower levels (children health cards, stock ledgers, charts, tally sheets, etc)

District Level:

- To introduce the WHO recommendation on child denominator (surviving children 0-11 month)

- To define the children to be reached by vaccination strategy and adapt the map accordingly

- To follow-up of the vaccine wastage on CSB level and to take actions if required

- To follow-up the vaccine stock outs of the CSB

- To compare and control if the number of reported children vaccinated is compatible with the doses delivered to the CSB

- To define the procedures of electronic data transfer

- To include in the printed documents the print date or date of creation of documents

- To reinforce the follow-up and the supervision of PEV activities at CSB level

- To make tabulations of the vaccine coverage of all CSB per month / year (electronic version)

- To put on disposition 2 health card trays per CSB

- To put the date of reception and to mark the monthly reports of the CSB received on the SSD level

- To reinforce the use of PEV data for the implementation of the activities

Health Unit Level :

- To improve the monitoring of the vaccine wastage

- To improve the maps by adding borders, targets to be vaccinated by strategy, reference marks etc.

- To set up a system of follow-up and reporting of the individual cases of adverse effects of the vaccines (action: central level)

- To use the infantile registers, charts and trays to seek "lost of sights”

- To use the collected data to initiate actions

- To fill the registers, stock ledgers and tally sheets correctly

- To develop a reporting system to get census on the information on the new births in the sector

- To make the systematic follow-up on the vaccine stock (batch number and expiry dates, entries, exits and actual stock)