Revision  5

February 2005

The Government of

REPUBLIC OF SIERRA LEONE

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and The Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and The Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Expanded Program on Immunization (EPI) is a priority program for the Government of Sierra Leone (GOSL), a result GOSL places great importance on the program. The current multi-year plan for EPI which was developed in the year 2000 to cover the period 2001-2005 comes to an end this year and GOSL would want to avail itself the opportunity of developing a comprehensive multi-year (cMYP) as recommended by WHO. The first draft included among the background documents accompanying this application is considered as “draft zero”. Technical assistance will be needed during the first of 2006 to finalize the plan as there is currently to expertise locally available to assist with its completion.

Sierra Leone has benefited from GAVI/VF support for Immunization Strengthening (ISS) since 2001 and Yellow fever vaccine and the Injection Safety support (INS) support since 2002. Having achieved the immunization coverage eligibility criteria, the country is now applying for support for new vaccine introduction (HepB and Hib vaccines) in the combination presentation (pentavalent). The GOSL and partners have decided to spread the GAVI/VF support over a period of eight years by beginning a-phase contribution from 2008. The total number of doses of the pentavalent vaccine required over the 9-year period is estimated at 6,385,528 (the ninth year is when the GOSL takes over full responsibility of the procurement of the new vaccine and supplies). Table 7.1 and 7.1 b show details of number of doses and contribution by year from 2007-2015.

The GOSL and partners hope to introduce the pentavalent vaccine by mid-January 2007, using the same schedule as the DTP vaccine (at age 6, 10 & 14 weeks). At this point in time, the GOSL has no plans to administer birth dose of monovalent HepB vaccine.

To ensure sustainable increases in coverage and completion rates, the Ministry of Health and Sanitation (MoHS) has initiated efforts to improve access and to reduce vaccination dropouts.

With the GAVI/VF supports for Injection Safety coming to an end, GOSL has created a budget line in the MoHS budget for the procurement of AD syringes and other injection safety materials.

The GOSL takes financial sustainability of the EPI very seriously. A Financial sustainability plan (FSP) was developed in 2004 and since then, the MoHS has had several discussions with other relevant government ministries/agencies and partners to effect its implementation.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of the Republic of Sierra Le commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health and Sanitation (MoHS) | Dr. Arthur Williams, Ag. Director General of Medical Services |  |
| United Nations Children’s Fund (UNICEF) | Mr. Geert Cappelaere |  |
| World Health Organization (WHO) | Dr. Joaquim Saweka WHO Representative |  |
| Rotary International | Mr. S.H.O.T Macauley Rotary Polio-plus Coordinator |  |
| Christian Children’s Fund | Mr. Daniel Kaindaneh Country Director |  |
| Sierra Leone Red Cross | Dr. M. S, Jolloh |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Dr. Magnus K, Gborie		Title/Address: EPI Manager

Tel.No.: 232-33-601-690   	              MCH/EPI Division, MoHS

Central Medical Stores

New England-Freetown, Sierra Leone

Fax No.:…………………………..

E-mail: gboriemk@yahoo.com

Alternative address:

Name: Dr. Zakari Wambai		Title/Address: WHO Epidemiologist

21 A/B Riverside Drive,

Brookfields, Freetown, Sierra Leone

Tel.No.: 232-22-233-565.

Fax No. 232-22-235-215

E-mail:wambaiz@sl.afro.who.int

- Immunization-related fact sheet

| Table 1: Basic facts for the year 2005 (most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 5,727,191 | GNP per capita | 180$US |
| Surviving Infants* | 190,143 | Infant mortality rate | 170/ 1000 |
| Percentage of GDP allocated to Health | 10% | Percentage of Government expenditure for Health Care | 2% |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported* |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2003 | 2004 | 2003 | Age group | 2004 | Age group |  | 2003 | 2004 |
| BCG |  |  | 87% | 83% | N/A |  | N/A |  | Tuberculosis | ND | ND |
| DTP | DTP1 |  | 87% | 76..9% | N/A |  | N/A |  | Diphtheria | 0 | ND |
|  | DTP3 |  | 70% | 60.7% | N/A |  | N/A |  | Pertussis | 0 |  |
| OPV3 |  |  | 70.4% | 60.8% | N/A |  | N/A |  | Polio | 0 | ND |
| Measles |  |  | 86.4% | 64% | N/A |  | N/A |  | Measles | 586 | 12* |
| TT2+ (Pregnant women) |  |  | 62% | 75.5% | N/A |  | N/A |  | NN Tetanus | 93 | 11 |
| Hib3 |  |  | N/A | N/A | N/A |  | N/A |  | Hib | 72 | ND |
| Yellow Fever |  |  | 76% | 64% | N/A |  | N/A |  | Yellow fever | 4* | 0 |
| HepB3 |  |  | N/A | N/A | N/A |  | N/A |  | hepB seroprevalence (if available) | ND | ND |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) |  | ND |  | 10.8% |  |  |  |  |  |
|  |  | Infants ( > 6 months) |  |  |  |  |  |  |  |  |  |

- Laboratory confirmed cases

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: The above coverage data are the best official estimates among infants. Unlike the coverage data in the JRF (above) where birth cohort was used as the denominator to calculate coverage for all antigens, surviving infants was used as denominator for calculating coverage for DTP, Measles. Polio and yellow fever in table 4 of this form.…………………………………

- Summary of health system development status relevant to immunization:

The Ministry of Health and Sanitation (MoHS) has responsibility for immunization services in Sierra Leone. The Expanded Programme on Immunization was established in 1978 by the Ministry of Health and Sanitation as an intervention programme to reduce the very high infant and under fives mortality rates.  The coverage for key antigens remained very low for many years after the programme was introduced (coverage for fully immunized children were 6% in 1986 and 24% in 1988).  The programme was then restructured and re-launched in 1989 to achieve better coverage. This resulted in the attainment of coverage of 75% by 1990, Universal Child Immunization (UCI) year.

The services are delivered through a network of primary health care facilities generally referred to as Peripheral Health Units (PHUs). These include the following types of health facilities:

- Community Health centers (CHCs): These are headed by Community Health Officers (CHO) who are the equivalent of Physician’s Assistants in some countries, they are supported in some cases by midwives and other categories of health workers

- Community Health Post (CHPs): Usually headed by State Enrolled Community Health Nurses (SECHN) also supported by other categories of health workers

- Maternal and Child Health Posts (MCHPs): usually headed by Maternal and child health Aides nurses who are like midwifery assistants

Before the war, there were a total of 772 functioning PHUs. Immediately after the war in 2001, there were only 406 functioning PHUs, the rest had either been destroyed or vandalized. Reconstruction and renovation of PHUs began immediately after the cessation of hostilities. An assessment of health facility status in the country in May 2003 showed that there were a total of 669 functioning PHUs, today the number has increased to 711.

Management of these facilities is the responsibility of district Health Management Teams (DHMT) headed by a District Medical Officer (DMO). The DHMTs supervise PHC activities in their respective districts of assignment and are in turn under the supervision of the director of primary health care with the programme managers acting as intermediaries, mobilizing resources and other necessary inputs at the national level

Almost all these facilities provide immunization services. The major health facilities have refrigerators while the smaller ones are provided with cold boxes. In the past most of the cold chain equipment in the PHUs run on gas however the erratic supply of gas has necessitated a shift to solar powered refrigerators. So far 365 solar refrigerators have been installed in district cold stores and major PHUs in 10 out of the 13 districts. Additional 90 solar refrigerators have been received for two districts, while delivery of those for the remaining district is being awaited. An additional cold room has been built at the Lungi international airport.

| - Attached are the relevant section(s) of strategies for health system development | Document number………….. |
| --- | --- |

# The Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

4.1 Profile of the ICC

- Name of the ICC: The Inter-agency Coordinating Committee

- Date of constitution of the current ICC: The ICC was established in June 1998

- Organisational structure (e.g., sub-committee, stand-alone): The ICC has two sub-committees (Technical and Social Mobilization).

The ICC was originally established to coordinate activities related to polio eradication. Over the years, the roles of the committee has been broadened to cover all aspects of  the immunization programme including routine immunization and polio eradication  and measles supplemental Immunization Activities (SIAs).

- Frequency of meetings: Normally, the ICC meets monthly but the committee meets more frequently when it becomes necessary like during preparations for SIAs

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Hon. Minister of Health and Sanitation | Mrs. Abator Thomas |
| Secretary | MCH/EPI Manager | Dr. Magnus K. Gborie |
| Members | - Director General, Medical Services - Dirctor Primary Health Care - Director Hospital and Laboratory - Deputy MCH/EPI Manager - WHO Country Representative - UNICEF Country Representative - Project Officer, Health and Nutrition - WHO Epidemiologist - Polio-Plus Coordinator - Sierra Leone Red Cross - Country Director CCF - Rep. World Vision - Rep.MSF/ Belgium, France Holland - Rep IMC. - Rep. Action Aid/sierra Leone …………. | Dr. Noah Conteh Dr. P. A. T. Robert Dr Arthur Williams Dr. Lynda Foray Dr. J. Saweka Mr. Geert Cappelaere Dr. Kedrick Kiawoin Dr. Zakari Wambai Mr. S. H.O.T. Macauley Dr. M.S. Jolloh Mr. Daniel Kaindaneh |

- Major functions and responsibilities of the ICC:

- Advocacy/Social mobilization: The committee advocates for EPI at higher political level nationally and internationally to ensure that the programme objectives are achieved.

- Coordination: The committee  coordinates support from all partners

- Programme Implementation: The ICC reviews and endorses EPI Plans including budget and supports the EPI programme implementation..

- Resource mobilization: The ICC assists the MoHs in mobilizing resources both at local and international levels. It is also responsible for ensuring that it supports the operationalization of the technical issues through its various sub-committees.

Attached is the supporting document:

| - Terms of reference of the ICC | Document number……. |
| --- | --- |

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Hold regular meetings as planned and that an agenda of each meeting is circulated in advance of the meeting date and time.

- Detail minutes of the ICC meetings  will be taken and circulated to members in time for comments prior to the next meeting

- The technical sub-committee will brief the full ICC periodically about the level of implementation of planned immunization and surveillance activities

4.2 Functioning of the ICC

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- The drop-out rate: as a sign of improvement in the immunization services, the ICC looks at the reduction in drop-out rate in multi-dose antigens (DTP1-DTP3) as well as drop-out between BCG and measles

- Completeness and timeliness of report from districts to central level

- Vaccine wastage rates: management of vaccine  will be closely monitored

Attached are the supporting documents :

| - ICC’s workplan for the next 12 months | Document number……. |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number……. |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| System-wide barriers to immunization | MoHS, GAVI, UNICEF, WHO, NORAD | June 2004 |
| Cold chain assessment | MoHS, NICEF, WHO | Aug. 2005 |
| AFP Surveillance Review | MoHS, UNICEF, WHO | July 2005 |
| DQA | Pricewaterhousecoopers | Sept. 2004 |
| Desktop Review of EPI | MoHS, UNICEF, WHO | Sept. 2005 |

- The three major strengths identified in the assessments:

- Improved routine coverage in 2004

- Improved AFP surveillance performance

- Improved EPI monitoring system

- The three major problems identified in the assessments:

- High drop out rate

- poor-monitoring of vaccine wastage rate

- Low  national DTP3 coverage

- The three major recommendations in the assessments:

- Reduce  drop out rate

- Reduce Vaccine Wastage rate

- Identify and implement innovations to improve DTP 3 coverage

- Attached are  complete copies (with an executive summary) of:

| - The most recent assessment reports on the status of immunization services | Document number….. |
| --- | --- |
| - A list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number….. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Injection safety assessment | June 2006 |
| Immunization coverage survey | Aug. 2006 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the comprehensive Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number……. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Consultant(s) for the finalization of the comprehensive multi-year plan (cMYP) | March 2006 | WHO, UNICEF and other relevant GAVI partners |
| Consultants for MLM training | 4th quarter 2006 | WHO, UNICEF and other relevant GAVI partners |
| Training of health workers for the introduction of new vaccines | 3rd – 4th quarter 2006 | WHO, UNICEF and other relevant GAVI partners |
| Injection safety assessment | June 2006 | WHO, UNICEF and other relevant GAVI partners |
| Immunization coverage survey | Aug. 2006 | WHO, UNICEF and other relevant GAVI partners |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | X |  |  |
| Polio | At birth, 6, 10. and 14 weeks | X |  |  |
| DTP | 6, 10. and 14 weeks | X |  | Pentavalent (DTP-Hep B +Hib to be administered at this age when introduced |
| Measles | At 9 Months | X |  |  |
| Yellow Fever | At 9 Months | X |  |  |
| TT | Pregnant and women of childbearing age (15-45 Years) | X |  |  |
| Vitamin A | 6-59 months | X |  | With routine immunization and SIAs |

- Summary of major action points and timeframe for improving immunization coverage:

| Major Action Points | Responsible Office | Timeframe |
| --- | --- | --- |
| Implementation of the RED strategy in all districts | MoHS, WHO, UNICEF & NGOs | 2006-2007 |
| Providing cold chain equipments (solar) to all functioning major health facilities (PHUs) | MoHS, WHO, UNICEF | 2005-2006 |
| Training of staff and improved supportive supervision aims at reducing missed opportunities for vaccination and improve quality of services and safety | MoHS, WHO, UNICEF | 2006-2007 |
| Expansion of vaccination services: 1) by rehabilitation of health facilities that will function as fixed vaccination post 2) By re-establishing out-reach and mobile immunization services. | MoHS and key partners,(WHO, UNICEF & world bank) | 2005- 2007 |
| Ensure vaccine availability at all times by procurement of vehicles for distribution of EPI materials | MoHS, WHO, UNICEF, JICA | 2005-2007 |
| Strengthening advocacy and communication | MoHS, WHO, UNICEF | 2005-2007 |

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of |  | Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | Base-year | Year of GAVI/VF application | Year of Preparation for introduction | Year 1 of Programme implementation | Year2 of Programme implementation | Year 3 of Programme implementation | Year 4 of Programme implementation | Year 5 of Programme implementation | Year 6 of Programme implementation |
|  |  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Births |  | 217438 | 229088 | 234402 | 239841 | 245404 | 251098 | 256924 | 262884 | 268983 |
| Infants’ deaths |  | 36964 | 38945 | 39848 | 40773 | 41719 | 42687 | 43677 | 44690 | 45727 |
| Surviving infants |  | 180474 | 190143 | 194554 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| Pregnant women |  | 217438 | 229088 | 234402 | 239841 | 245405 | 251098 | 256924 | 262884 | 268983 |
| Infants vaccinated with BCG |  | 217438 | 229088 | 234402 | 239841 | 245404 | 251098 | 256924 | 262884 | 268983 |
| BCG coverage* |  | 180585 | 183271 | 192210 | 201467 | 211048 | 220966 | 231232 | 239225 | 247464 |
| Infants vaccinated with OPV3 |  | 180474 | 190143 | 194554 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| OPV3 coverage** |  | 132316 | 115987 | 128406 | 141338 | 162949 | 166730 | 170598 | 174555 | 178605 |
| Infants vaccinated with DTP3*** |  | 180474 | 190143 | 194554 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| DTP3 coverage** |  | 61% | 61% | 66% | 0% | 0% | 0% | 0% | 0% | 0% |
| Infants vaccinated with DTP1*** |  | 180474 | 190143 | 194554 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| DTPI Coverage |  | 76% | 61% | 66% | 0% | 0% | 0% | 0% | 0% | 0% |
| Wastage[1] rate in base-year and planned thereafter |  | 50% | 50% | 50% | 0 | 0 | 0 | 0 | 0 | 0 |
| Infants vaccinated with 3rd dose of DPT-HepB+Hib** |  | 0 | 0 | 0 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| DPT-HepB+Hib 3 Coverage** |  | 0 | 0 | 0 | 76% | 79% | 81% | 83% | 85% | 87% |
| Infants vaccinated with 1st dose of DPT-HepB+Hib* |  | 0 | 0 | 0 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| DTP-HepB+Hib1 coverage |  | 0 | 0 | 0 | 76% | 79% | 81% | 83% | 85% | 87% |
| Wastage1 rate in base-year and planned thereafter |  | 0 | 0 | 0 | 10% | 10% | 10% | 10% | 10% | 10% |
| Infants vaccinated with Measles |  | 180474 | 190143 | 194554 | 199068 | 203686 | 208412 | 213247 | 218194 | 223256 |
| Measles coverage** |  | 64% | 70% | 73% | 76% | 79% | 81% | 83% | 85% | 87% |
| Pregnant women vaccinated with TT+ |  | 217438 | 229088 | 234402 | 239841 | 245404 | 251098 | 256924 | 262884 | 268983 |
| TT+ coverage |  | 60% | 59% | 63% | 67% | 70% | 73% | 76% | 79% | 81% |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | 11% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% |
|  | Infants (6-59 months) | 37% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% |
| * Number of infants vaccinated out of total births |  |  |  |  |  |  |  |  |  |  |
| ** number of infants vaccinated out of surviving infants |  |  |  |  |  |  |  |  |  |  |
| *** Indicate total number of children vaccinated with either DTP alone or combined |  |  |  |  |  |  |  |  |  |  |

| Table 5: Estimate of annual DTP drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009… | 2010 | 2011 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 20% | 18% | 15% | 12% | 10% | 10% | 10% | 10% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

Not applicable

- Planning and constraints for the Polio Eradication Initiative:

As part of the efforts being made for the eradication of polio, Sierra Leone started conducting national immunization days (NIDs) in the year 1996. Since 2000, Sierra Leone has participated in the synchronized NIDs with countries in the Western block).

The OPV vaccination coverage during the NIDs in 2004 was 103%, and 110% for first and second rounds respectively. In 2005, the coverage has been 109% and 106% for first and second rounds respectively

Surveillance for acute flaccid paralysis (AFP) is a part of the national integrated disease surveillance system. Moreover, non polio AFP detection rate in 2004 was 1.5 per 100,000 children under the age of 15. However, surveillance gaps have been identified in some district, more so, one district which been silence in the last 12 months.

Constraints for polio eradication

- Low routine OPV coverage

- Limited and delayed arrival of available funds

- Limited Government input

# Injection safety

7.1 Summary of the injection safety strategy for immunization (for all proposals):

Steps to ensure safety of Injection in the immunization has been part of the immunization activities since 1998 and also documented in the immunization policy. The use of auto-disabled (AD) syringes and safety boxes began early 2000 and by the end of 2000 approximately 60% of functioning health facilities were using AD syringes. By end of 2001, nearly all health workers had been trained on injection safety practices and health facilities supplied with injection safety equipments .With injection safety support received from GAVI/VF, much improvement have been made in the national programme. All functioning EPI facilities (711) are now using AD syringes and safety boxes for immunization activities.  Major health facilities are provided with incinerators for disposal of immunization wastes. However, pits are still in use for the disposal of immunization waste, particularly by small health facilities and outreach sites.  There are plans to construct more incinerators in the near future as resources become available.

An injection safety plan has been developed to address government and partners’ concern. The plan includes the following strategies

- Advocacy for legislation on safe injection practices and disposal for both public and private health care providers.

- Mobilization of resource for the procurement of injection equipment

- Estimate reliable  injection equipment requirements and effective distribution systems at all levels

- Ensure the collection and disposal of used injection equipment and the construction of incinerators

7.2  For countries submitting a proposal  for Injection Safety Support.  Summarise the most important findings of a recent assessment of Injection Safety and Waste Disposal. The relevant documents are attached

Not Applicable

| - Situation Analysis of Injection Safety and Waste Disposal or Report of the most recent Injection Safety and Waste Disposal Assessment | Document number… |
| --- | --- |
| - Update of the implementation status of recommendations from recent injection safety assessment or injection safety components from a broader review. | Document number… |
| - Policy on Injection Safety and Waste Disposal or a Draft Policy awaiting endorsement | Document number… |
| - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number… |

  - Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

Not Applicable

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supply for safety of vaccination with ………... vaccine ( Use one table for each vaccine BCG(1 dose), DTP(3 doses), TT(2 doses) 1, Measles(1 dose) and Yellow Fever(1 dose), and number them from 6.1 to 6.5) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 20… | 20… | 20… | 20… | 20… |
| A | Number of children to be vaccinated 2 | # |  |  |  |  |  |
| B | Percentage of vaccines requested from The Vaccine Fund 3 | % |  |  |  |  |  |
| C | Number of doses per child | # |  |  |  |  |  |
| D | Number of doses | A x B/100 x C |  |  |  |  |  |
| E | Standard vaccine wastage factor 4 | Either 2.0 or 1.6 |  |  |  |  |  |
| F | Number of doses ( incl. wastage) | A x B/100 x C x E |  |  |  |  |  |
| G | Vaccines buffer stock 5 | F x 0.25 |  |  |  |  |  |
| H | Number of doses per vial | # |  |  |  |  |  |
| I | Total vaccine doses | F + G |  |  |  |  |  |
| J | Number of AD syringes (+ 10% wastage) requested | (D + G) x 1.11 |  |  |  |  |  |
| K | Reconstitution syringes (+ 10% wastage) requested 6 | I / H x 1.11 |  |  |  |  |  |
| L | Total of safety boxes (+ 10% of extra need) requested | (J + K) / 100 x 1.11 |  |  |  |  |  |
| 1 GAVI/The Vaccine Fund supports the procurement of AD syringes to deliver two doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of two doses for Pregnant Women (estimated as total births) 2 To insert the number of infants that will complete vaccinations with all scheduled doses of a specific vaccine. 3 Estimates of 100% of target number of children is adjusted if a phased-out of GAVI/VF support is intended. 4 A standard wastage factor of 2.0 for BCG and of 1.6 for DTP, Measles, TT, and YF vaccines is used for calculation of INS support 5 The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. 6 It applies only for lyophilized vaccines; write zero for other vaccines. |  |  |  |  |  |  |  |

7.4 For countries requesting GAVI/The Vaccine Fund to provide funds in lieu of the supply calculated above.

List of activities of the injection safety plan funded by The Vaccine Fund and by other sources:

| Source of fund | ###### Injection Safety activity | Month of start of fund utilization |
| --- | --- | --- |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the comprehensive multi-year immunization plan that refer to the introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| HepB |  |  | 9.6-14.4 |
| Hib | Sentinel surveillance of Hib |  |  |

- (For Europe and Asia countries requesting support for Hib Vaccines). WHO advise on Hib introduction is attached:

| - WHO advise on introduction of Hib in this country N/A | Document number…… |
| --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

Experience with the introduction of yellow fever vaccine (under-used vaccine) shows that adequate planning is key to ensure sufficient cold chain capacity to accommodate the new vaccine. Although there was no concern for freezing of the yellow fever vaccine, appropriate training of health workers would be key to avoid accidental freezing of cold-sensitive vaccines, and other vaccine management issue as well as immunization waste management.

A lesson learnt with the introduction of yellow fever is that all efforts should be made to ensure that vaccines administered at the same time come in vials of the same number of doses. With the yellow fever in a 20-dose vial and the measles vaccine in a 10-dose vial couple with the concern to avoid wastage of vaccine lead to reduce coverage in some districts and major differences in coverage of the two vaccines.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

In an effort to overhaul the cold system following the civil war, the MoHS with support from partners has rehabilitated or install a cold room at the Lungi Airport. Although the original aim of the cold room at the airport was to serve as a transit storage point for vaccines coming into the country, the capacity of the cold room is large enough to accommodate all vaccines required for the country for at least 12 months. Additionally, solar power refrigerators are being installed in all major functioning health facilities and at district levels. The solar-power refrigerators provide storage capacity to accommodate the new vaccines (2-dose vial pentavalent vaccine) and the tradition vaccines.

First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

| Table 7.1: Estimated number of doses of Pentavalent. vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula |  | 2007 |  | 2008 | 2009 |  | 2010 |  | 2011 |  | 2012 |  | 2013 |  | 2014 |  | 2015 |
| A | Number of children to be vaccinated with the first dose 1 | # |  | 185,133 |  | 189,428 | 197,991 |  | 202,585 |  | 207,284 |  | 212,093 |  | 217,014 |  | 222,048 |  | 227200 |
| B | Percentage of vaccines requested from The Vaccine Fund 2 | % |  | 100% |  | 90% | 80% |  | 70% |  | 60% |  | 40% |  | 30 |  | 30 |  | 0% |
| C | Number of doses per child | # |  | 3 |  | 3 | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |
| D | Number of doses | A x B/100 x C |  | 555,399 |  | 568,284 | 593,973 |  | 607,755 |  | 621,852 |  | 636,279 |  | 651,042 |  | 666,144 |  | 681,600 |
| E | Estimated vaccine wastage factor | see list in table  |  | 1.11 |  | 1.11 | 1.11 |  | 1.11 |  | 1.11 |  | 1.11 |  | 1.11 |  | 1.11 |  | 1.11 |
| F | Number of doses ( incl. wastage) | D x E |  | 616,493 |  | 630,795 | 659,310 |  | 674,608 |  | 690,256 |  | 706,270 |  | 722,657 |  | 739,420 |  | 756,576 |
| G | Vaccines buffer stock 3 | F (-F of previous year) x 0.25 |  | 154,123 |  | 3,576 | 7,129 |  | 3,825 |  | 3,912 |  | 4003 |  | 4097 |  | 4191 |  | 4289 |
| H | Number of doses per vial | # |  | 2 |  | 2 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |
| I | Total vaccine doses requested | F + G |  | 770,616 |  | 634,371 | 666,439 |  | 678,433 |  | 694,168 |  | 710,273 |  | 726,753 |  | 743,611 |  | 760,865 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  | 787,570 |  | 634,764 | 667,223 |  | 678,853 |  | 694,598 |  | 710,714 |  | 727,204 |  | 744,072 |  | 761,337 |
| K | Reconstitution syringes (+ 10% wastage) 4 | I / H x 1.11 |  | 427,692 |  | 352,076 | 369,873 |  | 376,530 |  | 385,263 |  | 394,202 |  | 403,348 |  | 412,704 |  | 422,280 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  | 13,489 |  | 10,954 | 11,512 |  | 11,715 |  | 11,986 |  | 12,265 |  | 12,549 |  | 12,840 |  | 13,138 |
| 1 To insert the number of infants that will be vaccinated with the first dose only (as indicated in table 4). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 Estimates of 100% of target number of children is adjusted if a phased-out of GAVI/VF support is intended. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 The buffer stock for vaccines is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 It applies only for lyophilized vaccines; write zero for other vaccines. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 7.1 b: Projected contribution   in US Dollars by year  from GAVI and from Government of Sierra Leone and partners

|  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contribution from GAVI | 2,891,764 | 2,141,544 | 1,999,845 | 1,781,338 | 1,562,273 | 1,065,679 | 817,804 | 836,774 | 0 |
| Contribution from Gov/Partners | 0 | 237,949 | 499,961 | 763,430 | 1,041,516 | 1,598,519 | 1,908,210 | 1,952,473 | 2,853,966 |

| - Table  : Wastage rates and factors Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial, 25% for a liquid vaccine in a10 or 20-dose vial, 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial, and to reduce it in the following years. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Summary of major action points and timeframe for reduction of vaccine wastage.  If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

- Implementation of multi-dose vial policy

- Training of health workers

- Improve monitoring of vaccine management

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

|  |  | Formula | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated with the first dose 1 | # | 185,133 | 189,428 | 197,991 | 202,585 | 207,284 |
| B | Percentage of vaccines requested from The Vaccine Fund 2 | % | 100% | 100% | 100% | 100% | 100% |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 555,399 | 568,284 | 593,973 | 607,755 | 621,852 |
| E | Estimated vaccine wastage factor | see list in table  | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| F | Number of doses ( incl. wastage) | D x E | 616,493 | 630,795 | 659,310 | 674,608 | 690,256 |
| G | Vaccines buffer stock 3 | F (-F of previous year) x 0.25 | 154,123 | 3,576 | 7,129 | 3,825 | 3,912 |
| H | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| I | Total vaccine doses requested | F + G | 770,616 | 634,371 | 666,439 | 678,433 | 694,168 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 837,236 | 634,764 | 667,223 | 678,853 | 694,598 |
| K | Reconstitution syringes (+ 10% wastage) 4 | I / H x 1.11 | 85,538 | 70,415 | 73,975 | 75,306 | 77,053 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 10,243 | 7,827 | 8,227 | 8,371 | 8,565 |

| - Attached is the plan of action for introduction of vaccinations with new or under-used vaccines (if already contained within the national multi-year plan, indicate pages) | Document number… |
| --- | --- |

# Financial analysis and planning

Assured long term financing is crucial for maintaining program improvements and sustaining the introduction of new vaccines.  Meeting the financial requirements of improved and expanded immunization programs has proven to be the biggest challenge that countries and their partners face.  The financial analysis of the estimated cost of immunization (including the introduction of a new vaccine) is summarised in three major areas for the next years (see the document attached hereby):

- Rigorous analyses of the current and projected future costs for the program for the next years;

- Projected financing from all sources for the same time period;

- Description of the highest priority actions that the government/ will take to fill any resource gaps.

  - For countries that have already completed a Financial Sustainability Plan (FSP):

| - The attached document is an update of the program costs, financing projections and the plan of action for addressing the financial gap (if already contained within the national, comprehensive multi-year plan, indicate pages) | Document number…… |
| --- | --- |

  - For countries that have not completed a FSP:

| - The attached document summarises the results of most recent efforts to conduct the needed financial analyses and prepare a FSP. (if already contained within the national, comprehensive multi-year plan, indicate pages) | Document number…… |
| --- | --- |

Please follow the latest version of the financial analysis tool which is available @ http://www.who.int/immunization_financing/tools/annexes/en/

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the Republic of Sierra Leone, considering that its DTP3 coverage for 2004 was 73%  corresponding to 132,039 number of children receiving 3 doses of DTP(using surviving infants as denominator), requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

Support for Immunization Services                       		  YES

NO

YES

- Support for New and Under-used vaccines                                                     NO

NO

- Support for Injection Safety                                                          YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 20…according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 2) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund (fill in the annual amount of row “I” of table 7.1. Specify one additional row for each presentation of any vaccine as per tables 7.2, 7.3, …) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Pentavalent vaccine (DTP-HepB + Hib) | 2 | January 2007 | 770,616 | 634,371 |
| Tetravalent vaccine (DTP-HepB) | 10 | January 2007 | 770,616 | 634,371 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”( Annex 2) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “J, K and L” of tables 6.1, 6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 20.. | 20.. | 20.. | 20.. |
| J | Total AD syringes | for BCG |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |
| K | Total of reconstitution syringes |  |  |  |  |  |
| L | Total of safety boxes |  |  |  |  |  |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 2) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

We have been fully briefed on the content of this application and endorse it. We will do all we can to support the introduction and sustainability of the vaccines.

ANNEX  1

Index of documents attached

| Section of proposal | Document Subject | Document number |
| --- | --- | --- |
| 3 | A copy of the relevant section(s) of strategies for health system development | 1 |
| 4 | a) The terms of reference of the ICC | 2 |
|  | b) The ICC’s workplan for the next 12 months | 3 |
|  | c) The minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | 4 |
| 5 | - Most recent, national assessment report(s) on the status of immunization services - EPI Desk Review - DQA - System Wide Barriers to Immunization - Surveillance review | 5a,b,c,d |
|  | b) Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | 6 |
| 6 | A complete copy (with executive summary) of the comprehensive Multi-Year Immunization Plan or of the relevant pages of the health sector plan | 7 |
| 7 | a) The Situation Analysis of Injection Safety and Waste Disposal or Report of the most recent Injection Safety and Waste Disposal Assessment | 8 |
|  | b) An update of the implementation status of recommendations from recent injection safety assessment or injection safety components from a broader review. | NA |
|  | c) The Policy on Injection Safety and Waste Disposal or a Draft Policy awaiting endorsement | 9 |
|  | d) The plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or relevant pages of the health plan. | 10 |
| 8 | a) WHO’s advise on introduction of Hib in this country (for European and Asian countries) | NA |
|  | b) Plan of Action for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | 11 |
| 9 | Updated Financial Sustainability Plan (or a summary of the relevant financial analysis for preparation of the FSP) | 12 |

ANNEX  2

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of Republic of Sierra Leone , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  | Ministry of Health and Sanitation |  |  |  |  |  |  |  |  |
| #### Address: |  | Youyi Building, 4th Floor |  |  |  |  |  |  |  |  |
|  |  | Brookfields |  |  |  |  |  |  |  |  |
| #### City – Country: |  | Freetown, Sierra Leone |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  | Leone |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  | 8000654 |  |  |  |  |  |  |  |  |
| At: Bank’s name |  | Sierra Leone Commercial Bank |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES (√ ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: | Mr. M. S. Kebe |  |  |  |  |  |  |  | Seal: |  |
| #### Title: | Director General Management Services |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  | Sierra Leone Commercial Bank |  |  |  |
| Branch Name: |  | Siaka Stevens Street |  |  |  |
| Address: |  | Siaka Stevens Street |  |  |  |
| City – Country: |  | Freetown, Sierra Leone |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No.8000654 . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by Ministry of Health and Sanitation at this banking institution. (Sierra Leone Commercial Bank) |  |  |  |  |  |
| The account is to be signed jointly by at least TWO (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: | Dr Noah Conteh |  | Signature: |  |  |
|  | Director General Medical Services |  | Date: |  |  |
| 2 Name: Title: | Mr. M. S. Kebe |  | Seal: |  |  |
|  | Director General Management Services |  |  |  |  |
| 3 Name: Title: | Mr. M. A. Sandi |  |  |  |  |
|  | Director Financial Resources |  |  |  |  |
| 4 Name: Title: | Dr. Clifford Kamara |  |  |  |  |
|  | Director Planning and Information |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the 04 October 4, 2005 I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  | Mr. M. S. Kebe |  |  | Director general Management Services |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name | Mr. Geert Cappelaere |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |