May 2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: CAMBODIA

Date of submission: May 18th 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report 2001 First annual progress report 2002 Second annual progress report 2003 Third annual progress report 2004 Fourth annual progress report 2005 √ Fifth annual progress report ....... Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

ISS funds are directly managed by the senior management team of the NIP, in consultation with the Ministry of Health. A Technical Working Group, comprising members of the NIP management and GAVI partners, meets every 2 weeks and provides technical advice to the NIP on management of the ISS funds. During quarterly meetings with the ICC (immunization services sub committee), the NIP presents a report on use of the ISS funds. Where possible, research and evaluation information on the use of ISS funds is also provided. An administration and finance unit at the NIP directly manages the funds, and allocates funds to Provinces and Districts according to the direction from the NIP manager. The head of the administration and finance unit provides a quarterly and annual report on the status of the funds to the NIP management. The ISS funds and activity plans are included in the Multi Year Plan of the NIP and the Financial Sustainability Plan (both attached). There were no major issues associated with receipt or disbursement of ISS funds. Only half the funds for ISS were disbursed in 2005, because the NIP was not receiving a performance payment and needed to keep half the funds for maintaining immunization coverage in 2006. The Ministry of Health would like to express its concern regarding the future availability of these funds. In 2004, based on a demographic study, The Ministry of Planning Cambodia adjusted population statistics, resulting in a sharp reduction of the birth cohort for 2005 to 367,455. The adjusted population figures, based on census data and fertility surveys, are relevant for all sectors of the Government of Cambodia. In the original GAVI proposal, the projected population for Cambodia for infants under the age of 1 in the year 2004 was 478,225.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004                 US$ 668,600.00

Remaining funds (carry over) from 2004   US$ 395,366.77

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training | $58,161.89 | $9,941.75 | $10,644.28 | $37,575.86 |  |
| IEC / social mobilization | $97,283.42 | $58,740.00 | $38,543.42 |  |  |
| Outreach | $80,761.35 | $11,943.00 | $4,504.00 | $64,314.35 |  |
| Supervision | $28,693.20 |  | $11,880.00 | $16,813.20 |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) | $1,254.00 | $1,254.00 |  |  |  |
| Total: | $266,153.86 | $81,878.75 | $65,571.70 | $118,703.41 |  |
| Remaining funds for next year: | $129,212.91 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

IMMUNIZATION ISSUES Immunization Coverage New vaccine introduction was completed in 2005. There was a slight decline in immunization coverage for DPT-HepB 3 in 2005. In 2004 305,933 were vaccinated, but this declined to 299,606 in 2005. Coverage rates are now 82% for DPT3-Hep B. Measles coverage increased slightly. Since 2004, due to a high level executive government decree, there are now no incentives (travel per diem) for health workers to travel to villages less than 10km from a health facility. There is suspicion that this may be a main reason for coverage decline. There still remain high areas of drop out in remote areas. There are also pockets of very low coverage in high population density areas. This was confirmed by the recent outbreak of VDPV (2 laboratory confirmed, one clinically confirmed) in areas close to Phnom Penh in villages that had coverage of as little as 30%. In response, the NIP has commenced polio campaigns (March, April, May 2006) with expectation to cover 50-60% of the population in this period. There is recognition that routine services management and financing will need to be strengthened in order to avoid a repeat of this situation. A measles elimination plan is currently being drafted with the assistance of WHO. Measles coverage was 79% in 2005, with 0 districts with coverage below 50% Increasing Demand for immunization ISS funds were used to conduct workshops with local authorities in order to increase their support for and understanding of immunization. There was also airing of TV spots for routine immunization and in support of hepatitis B vaccine introduction. A fixed facility strategy (promotion of health centre based immunization services initiated by WHO) was also promoted using GAVI funds in co ordination with WHO and PATH. This pilot will be evaluated in 2006. Use of ISS Funds to Improve Coverage and Quality In 2005, the NIP dispersed half of the ISS funds (because of no performance payments in 2006 as described above). The remaining funds have been kept to maintain coverage in the first quarter of 2006 through support for outreach services in areas not supported by NGOs. The NIP conducts regular meeting with NGOs to map national support for health centre level immunization activities. ICC Function There were less meetings of the ICC in 2005. In order for the ICC to be a strategic group in making major recommendations about resource allocation, there needs to be a much higher level of representation from bilateral donors, Regional Working Group and in particular from the Ministry of Finance. Efforts are now being made by the NIP and partners to develop a higher level ICC in 2006, and then leave operational issues to the technical working group of the NIP. HEALTH SYSTEM ISSUES EFFECTING IMMUNIZATION PERFORMANCE Financing of Basic Health Services The NIP advocated to the Ministry of Finance in 2004 and finance for outreach services was re instated at the beginning of 2005 in the form of an annual “health centre support program” funded centrally by the Ministry of Health. However, in reality, the finance did not eventuate due to the MOH interpretation of the high level government decree which limits funding to health workers for travel less than 10 kms from health centres. A high level ICC (with invitation to high level Ministry of Finance officials) is proposed for May 2006 and a discussion paper has been prepared for Ministry of Finance to negotiate improved financing of basic health services (This paper is appended to this report. This paper outlines the main problems in financing in 2005) Health Centre Utilization and Private Sector GAVI ISS funds were dispersed to support strengthening of health centre utilization at 100 health centres. Coverage was maintained at these facilities with reduced vaccine wastage. However, concern is expressed at sustaining budget support for the strategy in the absence of government budget and ISS funds. Guidelines for improvement to private sector immunization have been researched, developed and approved by the Ministry of Health. Health Planning Following the MOH planning cycle and system, a 3 year rolling plan for NIP was developed for 2006 – 2008 (attached). A multi year plan (5 years) in line with the MOH planning cycle will be developed in 2006. Options under consideration for health systems strengthening include: - Strengthened planning and delivery of minimum package of activity (MPA) of primary health care services to underserved or high risk areas - Promotion of health centre utilization for MPA - Strengthening of decentralized health planning (including building capacity for use of health information in the local area) - Support for health education / communication strategy for MPA in areas of low service access - Support for increased delivery by midwife (including increased post natal care coverage and birth dose hepatitis B/BCG) EXPRESSION OF INTEREST Based on the above, the MOH / NIP would like to express interest in the following: - Health System Strengthening Application to GAVI October 2006 - Application to GAVI for Measles 2nd Dose October 2006 - Bridge Financing (commence planning early late 2007 / early 2008) The MOH / NIP would also like to seek clarification from GAVI on the issue of Cambodia's eligibility to apply for ISS funds. As the graph below demonstrates, reassessment of population denominators by UNFPA indicates that GAVI baseline estimates of performance are no longer relevant. Based on the new population denominators, Cambodia's coverage has remained consistently above 80% for the period 2000 to 2005, while still remaining to vaccinate additional numbers of children in the same time period. The original GAVI estimate over estimates population by 25% in 2004. The NIP / MOH would also like to seek clarification from GAVI on Cambodia's eligibility for ISS funds in 2007.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

X

YES                              NO

## If yes, please report on the degree of its implementation.

Numerator checking was undertaken as part of the EPI review in 2005. Through the survey, total 874 children in 125 villages registered in EPI record at 48 health centers of 11 operational districts in 6 provinces were examined. Among 874 registered children in EPI record, 73% (641) of them were really found in their village, 18% (153) of them had been dead or migrated already, and 9% (80) of them did not exist in the recorded village name from the beginning. The overall accuracy rate of the EPI record was 91 %. However the accuracy of Phnom Penh was especially low as 29% in OD Kandal and 67.5% in OD Choeung because of major mobility of the population into Phnom Penh. If Phnom Penh is excluded, the overall accuracy becomes high as 96.5%. The immunization coverage was part of the last Cambodia Demography Health Survey (CDHS) that was conducted late 2005 and in mid 2006 will provide information on the immunization coverage status. The last data quality audit (DQA) was conducted in 2003, showing 98% accuracy rates.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

An EPI Review was conducted. Recommendations were: - Strengthening of strategies to reach High Risk and High Drop Out Area - Strengthening management capacity Management capacity in the areas of Vaccine management, Supervision & Planning - Strengthening Fixed Facility Services, in order to reach a better balance with outreach activity - Research and development of policy and strategy to improve coverage and quality of immunization services delivered through private sector by building strategic public and private sector partnerships. - Improving the quality of health information through the NIP partnering with PHDs, ODs and Local Authorities at all levels to develop an effective strategy to follow up all births, deaths and reportable disease - Improving co ordination between MCH and Immunization Programs (EPI/NIP) A numerator survey was conducted (results outlined above in DQA section). A Private sector survey was conducted. Recommendations were: - Develop guidelines for private sector immunization - Reach agreement on quality standards in the private sector - Develop a capacity building program for vaccinators in the private sector - Establish system for vaccine and equipment supply and health information exchange - Establish a monitoring and contract system between private and public sectors A vaccine temperature monitoring study was conducted. Results and recommendations are being finalized.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           YEAR 2001

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

In 2005, 1,661,500 doses of DPT Hepatitis B were received into the country in 10 dose vials. There were no problems associated with the receipt of the vaccines. 906,430 doses remained at the beginning of 2005.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Combined vaccine has been introduced to 100% of districts in 2005. Birth dose vaccine has been expanded using 2 strategies – fixed facility and outreach. Health information on the timeliness of birth dose will be collected in 2006. Birth dose numbers reached 102, 032 which is 28% of the target. The target was 30% in 2005, and will be 35% in 2006. Given that 80% of infants are born in village homes and the new recommendation from WHO to vaccinate within 24 hours, Cambodia is now considering additional delivery approaches for the birth dose, including provision of the single dose vaccine for midwives. The NIP is therefore shifting from multi dose to single dose vial procurement. From June 2006, it is expected that the NIP will have at least two years supply of single dose vaccine. A temperature monitoring study has been conducted (results are available soon). The NIP is waiting on WHO policy before proceeding with outside the cold chain policy for hepatitis B birth dose. The wastage rate of combined vaccine in 2005 was 33%. The target in 2006 is 40%. In 2005, the NIP undertook the following activities in support of wastage reduction: - Expansion of fixed facility strategy to 100 health centre in Cambodia - Reinforcement of multi dose vial policy at Annual Program Review and Mid Term Review - Attachment of VVMs to all combined vaccine vials The target for wastage is higher in 2006, because in this year the combined vaccine is introduced for the whole country for 12 months of the year. In 2005, the combined vaccine was partially introduced, and in some areas DPT and mono-valent Hepatitis B vaccine was used to speed introduction of hepatitis B vaccine. Mono-valent Hepatitis B vaccine has significantly lower vaccine wastage rates.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

N/A

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Injection safety support was received bundled with combined vaccine supply.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Injection safety supply financing is secure in coming years. It is financed through a combination of JICA, Government of Cambodia and Japan Grant Aid supply. There will be still some supply through GAVI (bundled with combined vaccine).

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.*

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - % of Health Centres with 100% AD use for all EPI vaccines and safe disposal practices | 100% | 100% | Transport of full safety boxes difficult in some areas. Waste management remains a challenge due to transport and distribution system. | Achieved |
| - % of Operational Districts with adequate access to appropriate disposal system, including exchange mechanism for new and used injection equipment | 80% by 2003 and 100% by 2005 | --All provinces and 100% of ODs have access to a functioning incinerator. 51/75 ODs have an incinerator in-place. | Full safety boxes remain at the health facility because transportation to the incinerator sites remains a problem (long distance, large quantity). Still weak supervision and management of waste disposal by PHD. | Unchanged |
| - % of Operational Districts with adequate stocks of injection equipment for the whole year | 80% by 2003 and 100% by 2005 | 100%. No stock-outs reported. Supervision checklist includes information on stock usage. | Storage of reconstitution syringes (5ml) at all levels is combined for both curative care and immunization, which makes stock management problematic. | Unchanged |
| - (%) of AD syringe wastage | 10% nationwide | 10% |  | Unchanged |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

N/A

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for HEP B DPT (new vaccine)) for each new vaccine.

| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| A: Proportion funded by GAVI/VF (%)*** | 5 | 25 | 50 | 100 | 100 | 100 | 100 | 20 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) |  |  |  | 0 | 0 | 0 | 0 | 80 | 100 | 100 |
| C: Total funding for DPT HepB (new vaccine) |  | 582,705 | 875,000 | 2,887,992 | 2,774,679 | 2,386,460 | 2,550,027 | 2,462,551 | 2,544,004 | 2,622,686 |

The above table represents the proportion of vaccines supported without taking into account bridge financing. The MOH / NIP have already expressed interest in submitting a bridge financing proposal in a letter submitted to the GAVI secretariat in 2006. The MOH / NIP would like to seek clarification from GAVI on the possibility of co financing from 2009. The final GAVI payment from phase 1 is 20% in 2009. It is not expected that the government will have the capacity to co finance the remaining 80%, and bi lateral co financing of combined vaccine is not expected at this time. So the MOH / NIP would like to express interest in bridge financing from GAVI commencing in 2009.

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Increase national Govt. financial contribution to immunization. | (1) Advocate to Dept. Finance, MOH and Finance controller for timely provision of govt. funds for vaccine procurement (2) Advocacy to UNICEF and other donors to raise the ceiling of VII (3) Advocacy to national government to support health outreach funding and social mobilization | (1) There has been an increase in government financing of vaccine procurement (2) The ceiling of VII has been raised to $294,000 per cycle from a previous ceiling of $150,000. | (1) Although the VII ceiling has been raised and government commitments to vaccine procurement have increased , there is still ongoing concern about capacity of government and partners to finance the increasing vaccine budget (2) | (1) In 2002, Govt expended $152,668 on vaccine procurement. (2) Total Govt. NIP Budget in 2001 = $1,699,439 (3) Cost per Child 2001 = $14.11 | (1) In 2005, Govt expended $220,000 on vaccine procurement (2) Total Govt. NIP planned exp. in 2005 = $2,835,816 (3) Cost per Child 2005 = $25.60 | (1) Bridge Financing - The Government of Cambodia proposes to apply for bridge financing for co financing of combined vaccine. GAVI support ends in 2009 with a final 20% financing for combined vaccine by GAVI. The Government of Cambodia expresses interest in commencing bridge financing from 2009. (2) VII – Advocate at high level of Ministry of Finance and UNICEF to increase timeliness of procurement and financing of vaccines through this mechanism. (3) Outreach Financing – a discussion paper has been prepared and a high level ICC will be organised to resolve the issue of financing of basic services. |
| 2.Increase Provincial level expenditures for immunization (and reliability) | (1) Conducted Annual and Mid Term review and the NIP and partners are promoting sub national accountability for immunization performance | (1) There are no clear measures on how to evaluate sub national financing of primary health care (actual expenditures) | NA | NA | NA | (1) The NIP will continue to promote accountability for immunization services at provincial level through MLM training, job descriptions for Provincial staff and involvement of Provincial Heal Directors and Local Authority leaders in annual and mid term reviews of the program. National level supervisors will monitor the financing of outreach services to ensure that finance is reaching the primary level of care. (2) The NIP will involve the Provincial level in planning activities (review of MYP) so that they understand the strategic direction of the NIP (decentralization of accountability to PHD) |
| 3. Increase donor funding for immunization | (1) Update FSP information and present financial gap to donors at ICC meetings | (1) Updated financial information has been included in the JRF. (2) A discussion paper on financing of immunization has been prepared for presentation at ICC with donor and MOF involvement | Accurate information on FSP projections is limited by lack of information on policy developments and timeframes for new vaccines (JE, RV, HIB) and limited information on trends in prices of combined vaccine. | Total Donor Budget in 2001 = $2,437,088 | Total donor Budget in 2005 = $5,784,823 | Identify additional funding sources and/or bridge financing mechanism for combined vaccine. |
| 4. Increase efficiency through reduced wastage, increased fixed session and better outreach micro-planning | (1) Promote Multi Dose Vial Policy through annual program reviews (2)VVMs now attached to all vials (3) Fixed facility immunization strategy now expanded to 100 facilities (4) MLM training conducted with focus on vaccine management |  | The MOH would like to focus on urban sites initially for promotion of a fixed site strategy, with access remaining a major issue for fixed utilization in rural and remote areas. | Cost per Child 2001 = $14 DPT3% 2001 = 71% DPT Wastage 2001= % Vaccinated during outreach 2001 = 80% | Cost per Child 2005 = $25.60 DPT3 % 2005 = 80% DPT Wastage 2004 = 35% Vaccinated During outreach 2005 = 75% | (1) Wastage (a) further disseminate information on MDVP (b) MLM training with focus on vaccine management (2) Micro-planning. Select poor performing districts in last quarter with high numbers of un immunized and provide micro-planning and financial support. (3) Evaluate and expand fixed session strategy |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 384334 | 392945 | 401580 | 409934 | 419453 | 427492 | 436223 | 443006 | 450068 |
| Infants’ deaths | 25,840 | 25,500 | 25,113 | 24,514 | 24,636 | 23,465 | 23,320 | 21,860 | 21,452 |
| Surviving infants | 358,494 | 367445 | 376467 | 385421 | 394817 | 404028 | 412904 | 421146 | 428616 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 188,358 | 129157 |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 171,897 | 118280 |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)*Hep B. (new vaccine) | 142,229 | 184,393 | 357,644 | 366150 | 375076 | 383827 | 392259 | 400089 | 407185 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of Hep B ( new vaccine) | 134,036 | 181,326 | 335056 | 346879 | 359283 | 371706 | 384000 | 395877 | 407185 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 49% | 45% | 40% | 35% | 30% | 25% | 25% | 25% | 25% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 196,605 | 115,289 | 293,153 | 307,451 | 327,173 | 341,994 | 348,978 | 354,405 | 360,054 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 320,067 | 349073 | 357,644 | 366150 | 375076 | 383827 | 392259 | 400089 | 407185 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 290,556 | 301305 | 316232 | 331462 | 347439 | 363625 | 379872 | 395877 | 407185 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

N/A

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

N/A

Table 4: Estimated number of doses of combined DPT-Hepatitis B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.?

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

N/A

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

N/A

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| DPT3-Hep B | 319,766 | 299,606 (combined total of DPT and tetra valent vaccine) | Under financing of basic health services at primary level of care Under utilization of health facility Reduced ISS expenditure | 335,056 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | May 15 |  |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | Yes |  |
| Reported on use of 100,000 US$ | N/A |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | N/A |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

A draft report was submitted to the RWG. RWG sought clarification on bridge financing and provided comments on ISS proposal development. Clarifications were also sought regarding vaccine wastage and vaccine targets. Responses to these clarifications have been included in this report. The report was circulated to ICC members.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO |  |  | JICA |  |  |
| UNICEF |  |  | USAID |  |  |
| PATH |  |  |  |  |  |

~ End ~