Revision  4

August  2002

The Government of

ALBANIA

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# EXECUTIVE SUMMARY

Albanian Ministry of Health has been committed to improve the immunisation policies and services in the country. WHO recommendations on implementing regional strategies for disease elimination and control have been followed in the last years.

Before important economic and social changes of early 90s Albania was self-sufficient and reported high immunisation coverage of locally produced vaccines (BCG, DTP, DT, dT, TT and Measles) as well as of those imported ones such as OPV. The effective control of some important infectious diseases including measles was the result of such activity.

Since 1993 when EPI was created the country efforts of implementation of new or underused vaccines have been related and faced with needs to meet WHO recommendations on Safety of Injections.

The country ‘s national immunisation plan of action has set some targets not only for elimination, eradication or disease control activities and their sustainability and maintenance but also for injection safety considering them an important part of immunisation activities.

The introduction of AD syringes in Albania was done through the contribution of UNICEF and immediately after 1994 they accompanied the Hepatitis B Vaccine, which was introduced at that time.

During the following years AD syringes and disposable syringes were normally used for the implementation of Routine childhood immunisation schedule at national level replacing in 1996 the autoclaved reusable syringes. Also disposable syringes were introduced in all injection practices all over the country. Since 1999 disposable injection equipment is almost universally used in Albania and no direct or indirect evidence was found for the re-use of injection equipment in the absence of sterilisation.

After Measles/Rubella mass immunisation campaign for children 1-14 years old was implemented in November 2000, AD syringes were available for all antigens of National Immunisation Schedule. The respective numbers of safety boxes made available during the campaign are still present together with AD syringes within immunisation practices and services.

The introduction of new antigens in the national vaccination schedule and generally not very common appropriate collection and disposal of sharp waste in hospitals made a priority the development of a Plan of Action for Injection Safety in Albania. This Plan was based on two important documents prepared by the EPI (Institute of Public Health) and approved from Minister of Health:

- "Guidelines of Immunisation Injection Safety through disposal and destruction of used injection equipment in the framework of immunisation programs". These guidelines approved by Minister of Health shows the deep commitment of Ministry of Health to properly solve such issue. The Guidelines has been distributed all over the country and continuous supervision of injection safety is planned to monitor the their implementation in each district.

- "National Policy for Injection Safety and Safe Disposal of Injection Equipment". Following the Guidelines on "Immunisation Injection Safety through disposal and destruction of used injection equipment in the framework of immunisation programs", this National Policy document approved by Minister of Health, in collaboration with other actors is trying to standardise the future strategies concerning the issue of injection safety practices including all injections (in addition to the immunisation ones), both in public and private health sector in the country.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of ALBANIA commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government request

The Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application

Signiture:  Dr.Petrit Vasili

Title:	Vice-Minister of Health

National Chief Sanitary Inspector

Date:	April 30 2003

The GAVI secretariat is unable to return the submitted documents and attachments to individual countries. Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: ……………………………	Title/Address: ……………………………….

Tel.No.: ………………………….   		            ………………………………..

Fax No.:………………………….. 		            ………………………………..

E-mail:……………………………                         ……………………………….

Alternative address:

Name: Marjana Bukli………………	Title/Address:  UNICEF Tirana Office.

Tel.No.:00 355 692027089            ………………………………..

Fax No.:00 355 4 371741            ………………………………..

E-mail:…mbukli@unicef.org                  ……………………………….

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2002 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 3.087.159 | GNP per capita | 831 $USD |
| Surviving Infants* | 41733 | Infant mortality rate | 11.44/ 1000 |
| Percentage of GDP allocated to Health | 3,4% | Percentage of Government expenditure for Health Care | 7.2% (2001) |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2001 | 2002 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 91 | 94 |  |  |  |  | Tuberculosis | 700 | 733 |
| DTP | DTP1 |  | 97 | 98 |  |  |  |  | Diphtheria | 4 | 0 |
|  | DTP3 |  | 97 | 98 |  |  |  |  | Pertussis | 89 | 36 |
| OPV3 |  |  | 98 | 98 |  |  |  |  | Polio | 0 | 0 |
| Measles |  |  | 95 | 96 |  |  |  |  | Measles | 662 | 18 |
| TT2+ (Pregnant women) |  |  | 93 | 94 |  |  |  |  | NN Tetanus | 0 | 0 |
| Hib3 |  |  | NA | NA |  |  |  |  | Hib | ND | ND |
| Yellow Fever |  |  | NA | NA |  |  |  |  | Yellow fever | 0 | 0 |
| HepB3 |  |  | 98 | 96 |  |  |  |  | hepB seroprevalence (if available) |  |  |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | NA | NA | NA | NA | NA | NA |  |  |  |
|  |  | Infants ( > 6 months) | NA | NA | NA | NA | NA | NA |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

- Summary of health system development status relevant to immunization:

Immunisation services are under primary health care units. Directory of Primary Health Care within the Ministry of health is responsible for their organisation through the district primary health care directories.

Institute of Public Health (IPH) is the main technical agency of the Ministry of Health responsible for monitoring and evaluation of their activities as well as for implementing and recommending new policies.

EPI programme within the IPH works very closely with National Infectious Diseases Surveillance Unit in IPH.

Meanwhile through the decentralisation process funding of main activities of immunisation services at district level will be from local government.

A health system strategy is underdevelopment but a Public Health and Health promotion strategy has been recently developed and is addressing the same problem and underlying the importance of multisectorial responsibility and mobilising partners for better public health

Control of infectious diseases and vaccination programmes are strongly considered.

The strategy outlines the key policy areas to be addressed to protect and improve the health of the Albanian population.

This strategy identifies the immediate short and medium term targets and actions required to preserve the positive aspects of population health in Albania and to decrease the harmful influences.

| - Attached are the relevant section(s) of strategies for health system development | Document number………….. |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC  National Immunisation Committee

- Date of constitution of the current ICC: August 2000

- Organisational structure (e.g., sub-committee, stand-alone):Stand-alone…….

- Frequency of meetings:4 meetings/year…

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Ministry of Health, Chief Sanitary Inspector | Dr.Petrit Vasili |
| Secretary | Institute of Public Health Director EPI Manager | Dr.Silvia Bino Dr.Fabian Cenko |
| Members | - USAID - WHO HUMANITARIAN OFFICE - WHO LIASSON OFFICER - WORLD BANK - UNICEF - AMERICAN RED CROSS - PRIMARY CARE DIRECTORY/MoH - TB UNIT - Greek Embassy - Swiss cooperation Fund …………. | Dr.Zhaneta Shatri Dr.Santino Severoni, Dr.Stefania [ace-Shanklin Dr.Vasil Miho Mrs.Lorena Kostallari, Mr.Saimir Kadiu Dr.Lenin Guzman, Dr.Mariana Bukli Mrs.Ermira Brasha Dr.Jorgo Kosta Dr.Hasan Hafizi, National TB Coordinator |

- Major functions and responsibilities of the ICC:

Support to the Government in improving and expanding the National Immunisation Programme

Advocacy to increase national commitment on strengthening of immunisation programmes

Identification of required resources and assistance to sustain and strengthen immunisation services

Coordinate the support of existing partners to ensure the most effective use of resources

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

Strengthen collaboration between different partners by sharing information and coordinating actions

Increase partner support and participation into the process of decentralisation and funding of immunisation services

Mobilize partners to increase public private partnerships initiatives to strengthen immunisation programmes

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

100 %  use of safety boxes

Above 97 % of vaccination sites with safe immunisation practices

100% use of AD syringes into primary care practic

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number……. |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number……. |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Evaluation of vaccination coverage in risk populations in Tirana District | IPH,UNICEF,MoH, Local Gov, Tirana Regional Health Authority | April 2002 |
| Cold Chain Survey | IPH, UNICEF, WHO, MoH, District Public Health Directories | January –December 2002 |

- The three major strengths identified in the assessments:

Periodic stock reporting

### Cold chain availability in all districts

High awareness of vaccination programmes in a high urban residential setting

- The three major problems identified in the assessments:

National Inventory of of current status of cold chain based on each district and health facility level still to be defined

No clear recommendations about packing of vaccines in vaccine carriers during transportation process

Not all children included into the assessment were registered into the vaccination registry of vaccination point and other documents reflecting the place that children currently live

- The three major recommendations in the assessments

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number….. |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number….. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number……. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| Vitamin A |  |  |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 20033 |  | 20043 | 20053 | 20063 | 20073 | 20083 |
| Births |  | 52.880 | 42.2162 | 50.000 |  | 50.000 | 50.000 | 50.000 | 50.000 | 50.000 |
| Infants’ deaths |  | 604 | 483 | 572 |  | 572 | 572 | 572 | 572 | 572 |
| Surviving infants |  | 52.276 | 41.733 | 49.428 |  | 49.428 | 49.428 | 49.428 | 49.428 | 49.428 |
| Pregnant women |  | 44.880 | 37.259 | 50.000 |  | 50.000 | 50.000 | 50.000 | 50.000 | 50.000 |
| Infants vaccinated with BCG* |  | 48.120 | 39.683 | 47.000 |  | 47.000 | 47.000 | 47.000 | 47.000 | 47.000 |
| Infants vaccinated with OPV3** |  | 47.663 | 53.039 | 48.500 |  | 48.500 | 48.500 | 48.500 | 48.500 | 48.500 |
| Infants vaccinated with DTP3** |  | 49.918 | 53.026 | 49.000 |  | 49.000 | 49.000 | 49.000 | 49.000 | 49.000 |
| Infants vaccinated with HBV3**: |  | 48.628 | 52.128 | 48.000 |  | 48.000 | 48.000 | 48.000 | 48.000 | 48.000 |
| Infants vaccinated with Measles**1 |  | 47.573 | 50.704 | 48.000 |  | 48.000 | 48.000 | 48.000 | 48.000 | 48.000 |
| Pregnant women vaccinated with TT+ |  | 35.873 | 26453 | 40.000 |  | 40.000 | 40.000 | 40.000 | 40.000 | 40.000 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) |  |  |  |  |  |  |  |  |  |
|  | Infants (> 6 months) |  |  |  |  |  |  |  |  |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

1 Number of infants vaccinated with Measles containing vaccine is considered the first dose of MR

2 The birth cohort during 2002 used redused because of national vaccination program for Women in Childbearing Age against Measles Rubella that was implemented during the period October 2001 till December 2002. One of the major recommendations for vaccinated women was not to get a pregnancy for at least 3 months after vaccination

3 For the years 2003 until 2008 the vaccinated populations are projections calculated implying to reach the same vaccination coverage of the year 2002 which is almost the same with the vaccination coverage of the last years

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate |  |  |  |  |  |  |  |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 |  |  |  |  |  |  |  |  |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

This summery of the strategies is part of the attached document of "Plan of Action to improve Immunization Injection Safety and Safe Disposal of Injection Equipment in Albania"

Strategies:

- Ensure central and district governments commitment

- Sustain exclusive use of ADs in immunization services

- Improve planning and distributing so that to ensure reliability of estimates of equipment requirements, minimum stock levels and effective supply/ distribution of injection and disposal equipment

- Ensure the safe collection (establish a collection procedure) and disposal of used injection equipment through uninterrupted supply of safety boxes to all immunization sites and appropriate incineration

- Institute monitoring and supervising procedures to ensure adequate supplies at all levels and correct practices by HCWs

- Improve training of HCWs and managers on safe injection and disposal procedures

- Secure the required budget for injection safety including safe disposal of used equipment

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number……. |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for BCG vaccination | Match with targets in table 4 | 50.000 | 50.000 | 50.000 | 50.000 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 50.000 | 50.000 | 50.000 | 50.000 |
| D | AD syringes (+10% wastage) | C x 1.11 | 55.500 | 55.500 | 55.500 | 55.500 |
| E | AD syringes buffer stock | D x 0.25 | 13.875 | 13.875 | 13.875 | 13.875 |
| F | Total AD syringes | D + E | 69.375 | 69.375 | 69.375 | 69.375 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 2 | 2 | 2 | 2 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 5.550 | 5.550 | 5.550 | 5.550 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 832 | 832 | 832 | 832 |

| Table 6.2: Estimated supplies for safety of vaccination with DTP |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for DTP | Match with targets in table 4 | 50.000 | 50.000 | 50.000 | 50.000 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 |
| C | Number of DTP doses | A x B | 150.000 | 150.000 | 150.000 | 150.000 |
| D | AD syringes (+10% wastage) | C x 1.11 | 166.500 | 166.500 | 166.500 | 166.500 |
| E | AD syringes buffer stock | D x 0.25 | 41.625 | 41.625 | 41.625 | 41.625 |
| F | Total AD syringes | D + E | 208.125 | 208.125 | 208.125 | 208.125 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | N.R. | N.R. | N.R. | N.R. |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | N.R. | N.R. | N.R. | N.R. |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 2081 | 2081 | 2081 | 2081 |

| Table 6.3: Estimated supplies for safety of vaccination with MR |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for MR vaccination | Match with targets in table 4 | 50.000 | 50.000 | 50.000 | 50.000 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 |
| C | Number of MR doses | A x B | 50.000 | 50.000 | 50.000 | 50.000 |
| D | AD syringes (+10% wastage) | C x 1.11 | 55.500 | 55.500 | 55.500 | 55.500 |
| E | AD syringes buffer stock | D x 0.25 | 13.875 | 13.875 | 13.875 | 13.875 |
| F | Total AD syringes | D + E | 69.375 | 69.375 | 69.375 | 69.375 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 8.880 | 8.880 | 8.880 | 8.880 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 869 | 869 | 869 | 869 |

| Table 6.4: Estimated supplies for safety of vaccination with TT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of pregnant women for TT vaccination | Match with targets in table 4 | 50.000 | 50.000 | 50.000 | 50.000 |
| B | Number of doses per pregnant woman | # | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 100.000 | 100.000 | 100.000 | 100.000 |
| D | AD syringes (+10% wastage) | C x 1.11 | 111.000 | 111.000 | 111.000 | 111.000 |
| E | AD syringes buffer stock | D x 0.25 | 27.750 | 27.750 | 27.750 | 27.750 |
| F | Total AD syringes | D + E | 138.750 | 138.750 | 138.750 | 138.750 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | N.R. | N.R. | N.R. | N.R. |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | N.R. | N.R. | N.R. | N.R. |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1387 | 1387 | 1387 | 1387 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
|  | AD syringes and waste disposal boxes |  |
| GAVI/Vaccine Fund |  |  |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses  of   ………...   vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  |  |  |  |  |
| B | Percentage of vaccines requested from The Vaccine Fund | % |  |  |  |  |  |  |
| C | Number of doses per child | # |  |  |  |  |  |  |
| D | Number of doses | A x B/100 x C |  |  |  |  |  |  |
| E | Estimated wastage factor | see list in table  |  |  |  |  |  |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 |  |  |  |  |  |  |
| G | Vaccines buffer stock | F x 0.25 |  |  |  |  |  |  |
| H | Total vaccine doses requested | F + G |  |  |  |  |  |  |
| I | Number of doses per vial | # |  |  |  |  |  |  |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  |  |  |  |  |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  |  |  |  |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  |  |  |  |  |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number…… |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number .…. |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of ALBANIA,

Considering that its DTP3 coverage for 2002 was 98% corresponding to 53.026 number of children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):	     X	The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | N.R. | 69.375 | 69.375 | 69.375 |
|  |  | for other vaccines | N.R. | 416.250 | 416.250 | 416.250 |
| I | Total of reconstitution syringes |  | N.R. | 14.430 | 14.430 | 14.430 |
| J | Total of safety boxes |  | N.R. | 5.169 | 5.169 | 5.169 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

In according with the Action Plan for Safety of Injection, ICC fully endorsed the alternatives given in that material for the optimal solution of safe disposal and safe elimination of injection supplies. The ICC meeting suggested finalizing all the materials that dealt with this issue during the past national immunization activities. The Director of IPH supported directly the process of the preparation of these final materials until they were approved from the Vice-Minister of Health and National Chief Sanitary Inspector. In the next ICC meeting there will be presented the comments about the problems encountered into filed the implementation of those important materials (“Guideline of immunization injection safety through safe disposal and destruction of used injection equipment” and “National Policy for Injection Safety and Safe Disposal of Injection Equipment”). The process of analysing of all alternatives concerning the safe disposal of injection equipments, will implicate many partners (state institutions and others as Ministry of Finance, Ministry of Environments, Local Agency Environmental Agencies etc), because of consistent financial costs, compliance with current strategies of those institutions etc. Thus this process will be started in ICC meetings where its political, technical and financial support will be a constant prerequisite.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2002 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… | 42 000USD |  |  | 141000USD |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) | 20000USD |  |  | 54000USD |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific | 10000USD |  |  |  | 10000USD |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2003 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… | 94000USD |  |  | 80000USD |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | Lin ns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number……. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Terms of reference of the ICC | Document number…… |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number…… |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number…… |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number…… |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…… |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…… Document number…… |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number…… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible