24Revision  4

August  2002

The Government of

BHUTAN

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Royal Government of Bhutan is committed to improve the health status of its citizens and therefore have launched a number of programs to achieve Health for all. Expanded Program of Immunization (EPI) is one of the major preventive programs in health through which children and women are vaccinated. An effective EPI system is developed and the country and this system has attained a coverage over 90% since for over a decade.

In Bhutan Hep B vaccine for children was introduced into EPI through funding from DANIDA in 1996. However, the funding was available for the duration of 1996-2002 only. Bhutan therefore requested and obtained funding from the Vaccine Fund for HepB+DTP, with the intent of switching to combo after the funding from DANIDA ends. Because of the lack of a disease burden study to support introduction of Hib vaccine, Bhutan did not include Hib vaccine in its initial GAVI application. In June of 2002 a consultant from CDC conducted a Hib disease burden review and noted that the result of the assessment justifies introduction of Hib vaccine. The objective of the current application therefore is to request GAVI to include Hib vaccine in combination vaccine (DTP-HepB-Hib) into its EPI. Bhutan will also introduce AD syringes for all vaccines all over the country.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of Bhutan commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	Secretary, Ministry of Health and Education, Royal Government of Bhutan .

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date | Signature |
| --- | --- | --- | --- |
| Ministry of Health and Education, Royal Government of Bhutan | Dr. Sangay Thinley, Secretary |  |  |
| Health Department, Ministry of Health and Education, Royal Government of Bhutan | Dr. Gado Tshering, Director |  |  |
| Department of Aid and debt Management, Ministry of Finance, Royal Government of Bhutan | Aum/Ms Yanki T. Wangchuk |  |  |
| Public Health Division, Health Department, Ministry of Health and Education, Royal Government of Bhutan | Dr. Tenzin Penjor, Jt. Director, Public Health Division |  |  |
| Planning and policy Division Ministry of Health and education | Mr. Pemba Wangchuk, Head Planning and policy Division |  |  |
| Bhutan Chamber of Commerce and Industry | Mr.TsheringDorji ,Secretary General |  |  |
| Planning Comission, Royal Government of Bhutan | Mr. Dorji Norbu Dy.Director |  |  |
| Multisectoral Task Force, Thimphu District | Dr. T.B. Rana District Medical Officer, Thimphu |  |  |
| Youth Guidance and Counselling Division, Education Department, Ministry of Health and Education, Royal Government of Bhutan | Mr. Rinzin Wangmo,Programme Officer |  |  |
| Bhutan Broadcasting Service | Mr. K.B.Lama, HRD Co-ordinator |  |  |
| Dratshang Lhentshog | Mr.Ugyen Penjor, Project Manager, Religion and Health Project |  |  |
| DANIDA | Dr. Bjarne Jensen, Chief Technical Advisor |  |  |
| JICA | Mr.Yasuyuki Mori, Resident Representative |  |  |
| WHO | Dr. Orapin Singhadej Representative |  |  |
| UNICEF | Dr. Hemlal Sharma Project Officer, Health and Nutrition |  |  |

In case the GAVI Secretariat have queries on this submission, please contact:

Name: 			Dr. Gado Tshering,

Title/Address: 	Director, Health Department, Ministry of Health and Education

Tel.No.:                       +975-2-326747		                                 +975-2-323305

Fax No:                        +975-2-321446

E-mail:                       dr.gado@druknet.net.bt

Alternative address:

Name: 			Dr. Tenzin Penjor,

Title/Address: 	Joint Director, Public Health Division, Health Department, Ministry of Health and Education

Tel.No.:                       +975-2-325984 		                                 +975-2-322458

Fax No:                        +975-2-326038

E-mail:                       tenjor2000@yahoo.com

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 698,950 | GNP per capita | 599.2 $US |
| Surviving Infants* | 22,386 | Infant mortality rate | 60.5/ 1000 live birth |
| Percentage of GDP allocated to Health | 4% | Percentage of Government expenditure for Health Care | 8.5 % |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 93 | 81 |  |  |  |  | Tuberculosis | 625 | 326 |
| DTP | DTP1 |  | 95 | 90 |  |  |  |  | Diphtheria | 1 | 1 |
|  | DTP3 |  | 88 | 86 |  |  |  |  | Pertussis | 96 | 26 |
| OPV3 |  |  | 89 | 95 |  |  |  |  | Polio | 0 | 0 |
| Measles |  |  | 79 | 76 |  |  |  |  | Measles | 84 | 460 |
| TT2+ (Pregnant women) |  |  | 73 | 78 |  |  |  |  | NN Tetanus | - | - |
| Hib3 |  |  | - | - |  |  |  |  | Hib | - | - |
| Yellow Fever |  |  | - | - |  |  |  |  | Yellow fever | - | - |
| HepB3 |  |  | 86 | 87 |  |  |  |  | HepB sero-prevalence (if available) | - | - |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | - | - |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) | - | - |  |  |  |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: The estimates are the only estimate available. They are expected to be reliable as they are based on quarterly reports submitted by the district, who base their estimate on the monthly report sent by the immunization service delivery facility. These facilities keep tallies of vaccination provided and compile and send the reports to the districts monthly.

- Summary of health system development status relevant to immunization:

The Royal Government of Bhutan is committed to improve the health status of its citizens and therefore has launched a number of programs to achieve health for all. Expanded Program on Immunization (EPI) is one of the major preventive programs in health through which children and women are vaccinated. The EPI in Bhutan was initiated on 15th November 1979, targeting vaccine preventable diseases. The programme currently targets seven diseases preventable by immunization – poliomyelitis, tetanus, including neonatal tetanus, hepatitis B, diphtheria, pertussis, measles and childhood forms of tuberculosis. EPI aims at elimination of polio and tetanus by 2005, reduce measles cases by 90% and deaths due to measles by 95% by end of 9th Five Year Plan.

The Royal Government of Bhutan (RGOB) commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

| - Attached are the relevant section(s) of strategies for health system development | Document number 1, 9th five year plan draft, attached |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC:			Partner Co-ordination mechanism (PCM)

- Date of constitution of the current ICC: 	12.8.2002

- Organisational structure (e.g., sub-committee, stand-alone):

Partner Coordination Mechanism (PCM) has been established to coordinate and provide broad policy advice relating to GFATM in Bhutan. The Health Secretary, Ministry of Health and Education is the chair and the Director of Health Department is designated as the member secretary This Committee will also represent as the interagency coordination committee (ICC) for GAVI. The PCM is stand alone committee but may constitute a sub-committee for a specific purpose.

- Frequency of meetings

PCM meets Bi-annually but on request of any member and agreement of the chairperson meeting can be convened more than twice a year

- Composition:

| Function | Title/organisation | Name |
| --- | --- | --- |
| Chair | Secretary, Ministry of Health and Education, Royal Government of Bhutan | Dr. Sangay Thinley |
| Vice-chair | Health Department, Ministry of Health and Education, Royal Government of Bhutan | Dr. Gado Tshering, Director |
| Member | Director General, Department of Aid and Debt Management, Ministry of Finance, Royal Government of Bhutan | Aum/MsYankiT. Wangchuk |
| Member secretary | Jt. Director, Public Health Division, Health Department, Ministry of Health and Education, Royal Government of Bhutan | Dr. Tenzin Penjor |
| Member | Head, Planning and policy Division Ministry of Health and education | Mr. Pemba Wangchuk |
| Member | Secretary General, Bhutan Chamber of Commerce and Industry | Mr.Tshering Dorji |
| Member | Dy.Director, Planning Comission, Royal Government of Bhutan | Mr. Dorji Norbu |
| Member | District Medical Officer, Thimphu, Multisectoral Task Force, Thimphu District | Dr. T.B. Rana |

| Member | Programme Officer, Youth Guidance and Counselling Division, Education Department, Ministry of Health and Education, Royal Government of Bhutan | Mr. RinzinWangmo |
| --- | --- | --- |
| Member | HRD Co-ordinator, Bhutan Broadcasting Service | Mr. K.B.Lama |
| Member | Project Officer, Religion and Health Project, Dratshang Lhentshog | Mr.Ugyen Penjor |
| Member | Chief Technical Advisor, DANIDA | Dr. Bjarne Jensen |
| Member | Resident Representative, JICA/JOCV | Mr.Yasuyuki Mori |
| Member | WHO Representative | Dr.Orapin Singhadej |
| Member | Project Officer, Health and Nutrition, UNICEF | Dr. Hemlal Sharma |

- Major functions and responsibilities of the ICC:

- To support in preparation, review and endorse submission of country coordinated proposals for GAVI and GFTAM as relevant.

- to periodically monitor, review progress, report and advise on the policies and strategies related to EPI, STD/AIDS, TB and malaria situation and control activities in the country in light of new approaches and changing global and regional priorities.

- To advice on capacity building and on implementation of innovative strategies and approach in relation to EPI, TB, STD/AIDS and Malaria.

- To advise and assist in mobilizing internal and external resources from various sources including GAVI and GFTAM and ensure proper use of these resources

- To promote and facilitate partnership building including the involvement of NGOs and the civil society in above disease control programmes.

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Development of formal work plan for ICC

- Action or anted quarterly meetings to discuss needs of EPI for generating commitments of ICC partners for supporting priority needs.

- Focus on capacity development for EPI.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- National EPI policy guideline revised to include new vaccines.

- Percentage of health workers trained on vaccine management  injection safety use of new vaccine, & revised EPI policy.

- Percentage of DMOs & DHSO trained on Mid level Management training.

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number: 2, Attached |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number: 3, Attached |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number: 4, 5 and 6 Attached |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| EPI coverage survey | WHO & UNICEF | April 2002 |
| EPI review | WHO & UNICEF |  |
| Cold chain review | WHO |  |

- The three major strengths identified in the assessments:

- Strong will and commitment of at levels

- Good EPI and primary health care network reaching into the communities

- High coverage of all vaccines

- The three major problems identified in the assessments:

- Limited capacity of the EPI system- Lack of a formal policy statement, lack of adequately trained manpower at all levels and relative lack of supportive supervision

- Lack of clearly defined target population for each facility, district and thereby at the national level making it difficult to forecast needs, plan immunisation and monitor coverage

- There is a relative lack of focus on Information, Education and Communication  (IEC) and community mobilisation.

- The three major recommendations in the assessments:

- Quality assurance- Through putting in place guidelines for procedures and practices for immunization, injection safety assurance, improving information management system for target setting, planning of supplies and monitoring coverage and through meticulous micro planning for each activity,

- Capacity development- Training Need Assessment, training and Re-orientation of staff followed by strong supportive supervision,

- Development of comprehensive IEC plan for national, district and community level

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number : 7, EPI coverage survey report, Document Number 8, EPI review report Attached |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number: 9, Multiyear plan of action Attached |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Injection safety practices | May/2003 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 9, Multi-year plan of action. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Training need assessment | 2002 | WHO |
| Training of trainers | 2002 | WHO |
| National EPI policy revision | 2002 | Request made to UNICEF |
| Injection safety assessment | 2003 | WHO |
| IEC need assessment and development of IEC package for EPI | 2003 | UNICEF |
| Technical assistance for comprehensive immunization services assessment, including injection safety, coverage survey and cold chain | 2005 | WHO |
| Technical assistance for monitoring of bacterial meningitis and invasive pneumonia in children | 2003 | WHO/GAVI RWG |
| Technical assistance for developing financial sustainability plan | 2005 | WHO/GAVI RWG |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | X |  |  |
| OPV | 6weeks 10 weeks 14 weeks | X |  |  |
| DPT | 6 weeks 10 weeks 14 weeks | X |  | DTP+Hib+HepB will be given in place of DPT when they are introduced |
| Hep.B | 6 weeks 10 weeks 14 weeks | X |  |  |
| Measles | 9 months | X |  |  |
| Vitamin A | 6 months and every six month thereafter for under-5 children and single dose with in 2 weeks of delivery to mothers | X |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

| Activity | 2003 |  |  |  | 2004 |  |  |  | 2004 |  |  |  | 2006 |  |  |  | 2007 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV |
| Midlevel management and vaccine management training of all DMO and DHSOs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cascade training of all health workers on vaccine management, community mobilisation and developing micro-plan for immunization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| District level and facility level micro-plan development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IEC need assessment and package development for EPI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mass media and interpersonal communication for EPI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outreach services expansion, focussing on hard to reach and low coverage area |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births |  | 23,827 | 24,423 | 25,033 |  | 25,659 | 26,301 | 26,958 | 27632 | 28323 |
| Infants’ deaths |  | 1442 | 1478 | 1515 |  | 1552 | 1591 | 1631 | 1671 | 1771 |
| Surviving infants |  | 22,386 | 22945 | 23,519 |  | 24,107 | 24,710 | 25,327 | 25961 | 26554 |
| Pregnant women |  | 24,463 | 25,075 | 25,702 |  | 26,344 | 27,003 | 27,678 | 28370 | 29053 |
| Infants vaccinated with BCG* |  | 23,827 | 24,423 | 25,033 |  | 25,659 | 26,301 | 26,958 | 27,632 | 28,323 |
| Infants vaccinated with OPV3** |  | 22,386 | 22,945 | 23,519 |  | 24,107 | 24,710 | 25,327 | 25,961 | 26,554 |
| Infants vaccinated with DTP3** |  | 22,386 | 22,945 | 23,519 |  | 24,107 | 24,710 | 25,327 | 25,961 | 26,554 |
| Infants vaccinated with**: (use one row for any new vaccine) |  | 22,386 | 22,945 | 23,519 |  | 24,107 | 24,710 | 25,327 | 25,961 | 26,554 |
| Infants vaccinated with Measles** |  | 22,386 | 22,945 | 23,519 |  | 24,107 | 24,710 | 25,327 | 25,961 | 26,554 |
| Pregnant women vaccinated with TT+ |  | 24,463 | 25,075 | 25,702 |  | 26,344 | 27,003 | 27,678 | 28,370 | 29,053 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | - | 30000 | 30750 |  | 31519 | 32307 | 33114 | 33942 | 34791 |
|  | Infants (> 6 months) | - | 110000 | 112750 |  | 115569 | 118458 | 121419 | 124455 | 127566 |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate | 40% | 40% | 10% | 10% | 10% | 8% | 5% | 5% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 2.6% | 2.6% | 2.6% | 2.4% | 2.5% | 2.5% | 2.5% | 2.5% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

The last case of polio was detected in Bhutan in 1986. Polio vaccine coverage has been maintained consistently above 80 percent sine mid eighties. Acute flaccid surveillance is in place since 1997. The surveillance indicators, timeliness, completeness and AFP detection have been good but no polio has been detected. Despite that, the biggest challenge in polio eradication in Bhutan is the external factor- the pool of wild poliovirus in the neighbouring countries. To prevent the entry of wild poliovirus, apart form maintaining high routine immunization coverage through routine services, two rounds of Subnational immunization days are being conducted every year in the area bordering India and the isolated camps where roadworkers and armed forces families live. These activities will be continued and Bhutan will achieve polio certification, if the external factor is taken care of through global initiatives.

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

Objective 5 of MYPOA is “To increase the safety of injections used for all EPI vaccines through converting to the use of auto disable syringes for all immunizations by end 2003”. To achieve this objective, the following activities will be carried out:

- Assess the current injection safety practices

- Prepare a national Injection safety policy and plan in the light of the injection safety assessment practices.

- Implement the national Injection safety plan

- Submit a proposal to the GAVI for AD syringes and safety boxes.

- Prepare for the introduction of AD syringes in routine EPI i.e logistic arrangements, training etc

- Give adequate publicity to use of AD syringes in EPI so as to further boost public confidence.

- Initiate use of AD syringes for EPI injections  so that  they are used country wide  by the end of 2003

- Explore the possibility of funding from Health Trust Fund and negotiate with donors/UNICEF for their support in this field after GAVI support ends.

- Provide a copy of injection safety plan at each health facility.

- Update Injection safety guidelines, prepared during immunization campaigns 2000-01

- Integrate training in the use and disposal of AD syringes into all training courses for , primary health care workers , and supervisory staff.

- Initiate / strengthen AEFI system.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 10, injection safety plan |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with …… ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Tetanus toxoid | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 25,702 | 26,344 | 27,003 | 27,678 |
| B | Number of doses per child (or per woman in case of TT) | # | 2 | 2 | 2 | 2 |
| C | Number of …… doses | A x B | 51,404 | 52,688 | 54,006 | 55,356 |
| D | AD syringes (+10% wastage) | C x 1.11 | 57,058 | 58,483 | 59947 | 61445 |
| E | AD syringes buffer stock | D x 0.25 | 14265 | 14621 | 14986 | 15361 |
| F | Total AD syringes | D + E | 71323 | 73104 | 74933 | 76806 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | - | - | - | - |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 792 | 811 | 832 | 853 |

|  | Measles | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for Measles) | Match with targets in table 4 | 23,519 | 24,107 | 24,710 | 25,327 |
| B | Number of doses per child for Measles | # | 1 | 1 | 1 | 1 |
| C | Number of …… doses | A x B | 23,519 | 23,519 | 23,519 | 23,519 |
| D | AD syringes (+10% wastage) | C x 1.11 | 26106 | 26759 | 27428 | 28113 |
| E | AD syringes buffer stock | D x 0.25 | 6526 | 6690 | 6857 | 7029 |
| F | Total AD syringes | D + E | 32632 | 33449 | 34285 | 35142 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 4.00 | 3.33 | 2.50 | 2.50 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 9408 | 8,028 | 6128 | 6332 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 466 | 460 | 449 | 460 |

|  | BCG | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for BCG) | Match with targets in table 4 | 23,782 | 24,376 | 25,512 | 26,419 |
| B | Number of doses per child (or BCG | # | 1 | 1 | 1 | 1 |
| C | Number of …… doses | A x B | 23,782 | 24,376 | 25,512 | 26,419 |
| D | AD syringes (+10% wastage) | C x 1.11 | 26,398 | 27,058 | 28,318 | 29,325 |
| E | AD syringes buffer stock | D x 0.25 | 6,599 | 6,764 | 7,079 | 7,331 |
| F | Total AD syringes | D + E | 32,997 | 33,822 | 35,397 | 36,656 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 4.00 | 4.00 | 3.33 | 3.33 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 10559 | 10832 | 9430 | 9765 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 483 | 496 | 498 | 515 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| WHO | Surveillance, Training and other technical assistance | On-going |
| JICA | Sterilisation equipment | Ending by 2002 end, no commitment yet for future |
| DANIDA | Disposable syringes for HepB | Ending by 2002 end, no commitment yet for future |
| UNICEF | Training and social mobilisation | On-going |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes | 2003 |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refers to the introduction of new and under-used vaccines.

## Section 3.4 of MYPOA refers to Extension of the scope of the present EPI with the following points for action:

- New vaccines to be added to the EPI schedule, as appropriate

- Disease burden studies to be conducted before new vaccines are added to the schedule.

- Social mobilisation with progressive involvement of community /VHWs to create client demand and to ensure community awareness of other available effective health interventions

- EPI planning to focus not only on its own sustainability but on measures to extend its benefits to other health care programs.

- Additional studies to become an integral part of EPI planning and development.

- Assessment of burden of relevant diseases (if available) : (Report Attached)

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Haemophilous influenzae B meningitis and pneumonia | Bhutan, Haemophilous B disease burden rapid assessment, using the WHO Hib rapid assessment tool | 21-28 June 2002 | Hib is the leading cause of bacterial meningitis in childhood accounting for 44% culture-confirmed bacterial meningitis |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

HepB is being used from 1996 and it is well accepted. The additional injection initially was a problem as the illiterate parents were concerned that two injections at a time may result in some harm or increased pain to their children. This however, disappeared with time as the confidence of parents grew. There had been no report of logistic problems. A possibility of vaccine damage due to freezing has been identified in the recent cold chain assessment and activities have been initiated to avoid this problem.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

Section 3 of MYPOA

3.1	General principles

- Immunization services will be planned to be sustainable.

- Parallel with completing present commitment to polio eradication, MNT and measles  elimination, focus will be placed more on ensuring system development  for disease surveillance.

- Emphasis on promoting a local capacity to plan and to solve problems.

3.2	Devolution of responsibility and strengthened planning

- Planning and executive authority further devolved to the districts.

- EPI Section primarily to fulfil a role for technical co-ordination, policy development, and procurements.

- Districts to establish their own, realistic targets, within the overall national targets.

- Key management level to be the district, with DMO being fully responsible and accountable for planning monitoring and progress in the district

- Operational level to be the BHU, the In charge BHU being responsible and accountable for planning and guaranteeing immunization services for all communities within the  catchment of the BHU.

- At all level, written plans of action to exist and be regularly updated.

- Special emphasis, for development of routine services to be directed at high risk and un reached populations.

3.3	Improving the quality of EPI services

- Major emphasis to be placed on ensuring the quality of all aspects of immunization, with special note on staff training, vaccine storage and the safety of injection practices

- Supervision and monitoring to be strengthened, with written documentation on findings to allow follow-up.

- Coverage in each district to be assessed at least every three years through cluster sampling .

- Existing network of ORCs to be extended , and re planned in the areas where a new static centre is established

- An assessment of the training needs to form the basis for a comprehensive training plan.  A training impact assessment to monitor the quality to be undertaken after 3-4 yrs.

- All immunization staff to receive technical and management training, as appropriate, with refresher courses at least every three to four years.

- Consensus on the district wise target population to be reached among DOH (HMIS) and CSO.

- Increased emphasis on infant registration with improved and reliable follow up of defaulters.

- Active surveillance to be extended to include NNT and Measles

- The surveillance system to explore how the HMIS can develop and as an effective operational tool for EPI disease control

- A system for surveillance and investigation of adverse events after immunization (AEFI) to be developed.

3.4	Extension of the scope of the present EPI

- New vaccines to be added to the EPI schedule, as appropriate

- Disease burden studies to be conducted before new vaccines are added to the schedule.

- Social mobilisation with progressive involvement of community /VHWs to create client demand and to ensure community awareness of other available effective health interventions

- EPI planning to focus not only on its own sustainability but on measures to extend its benefits to other health care programs.

- Additional studies to become an integral part of EPI planning and development.

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses  of   DPT+HepB+Hib   vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 22343 | 23142 | 24215 | 24820 | 25440 |  |
| B | Percentage of vaccines requested from The Vaccine Fund ( for estimated coverage) | % | 95 | 96 | 98 | 98 | 98 |  |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 |  |
| D | Number of doses | A x B/100 x C | 63678 | 66649 | 71192 | 72971 | 74794 |  |
| E | Estimated wastage factor | see list in table  | 1.11 | 1.11 | 1.11 | 1.05 | 1.05 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 70682 | 95460 | 98070 | 93820 | 96166 |  |
| G | Vaccines buffer stock | F x 0.25 | 17671 | 23865 | 24518 | 23455 | 24042 |  |
| H | Total vaccine doses requested | F + G | 88353 | 119325 | 122588 | 117275 | 120208 |  |
| I | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 |  |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 90296 | 100470 | 106238 | 107033 | 109707 |  |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 | 49036 | 66225 | 68036 | 65088 | 66715 |  |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 1547 | 1850 | 1934 | 1911 | 1958 |  |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

If it is not possible to switch over to pentavallent vaccine in 2003, the pentavallent combination be approved form 2004 January. In such an event, DPT-HepB combination already approved will be used and the switch over made from 2004

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number 11, Plan of action for Hib vaccine introduction |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

There is a commitment of the Government, partners and public alike to raise funds for the “Health Trust Fund”, which when it reaches the intended level will sustain the cost of vaccine and essential drugs for all times to come. Government of Japan has been approached through the UNICEF-Japan Government Multi-Bilateral cooperation for continuing support for the cold chain equipment supplies, OPV, Measles and BCG vaccine. The existing partners of health system of Bhutan and the EPI, including WHO and UNICEF, have committed their support for the medium term, which looks into the surveillance, training need and social mobilisation need of EPI. With the completion of the on-going major hydropower project, by the end of this five-year plan period, it is anticipated that the Government revenue will increase. Even with the same share of allocation to the health sector then, the health a will be able to take up a higher share of funding of vaccination programme in the next development plan. Further, the ICC partners are also expected to put in some resources. A detail sustainability plan will be developed in 2005 with the assistance of GAVI/WHO.

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document No.9, MYPOA and Annex-1 |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

Vaccine wastage is high currently. With smaller dose vials it is expected to come down. As VVM become available in the combo-vaccine, open vial policy will be adopted to reduce the wastage. The district and facility level health worker will be trained on vaccine wastage and will be made to develop local strategy for vaccine wastage reduction. With this, the wastage will be brought down. Further, local level target setting, improved information management and utilization, and stringent monitoring of supplies and timely re-mobilisation will be done to reduce vaccine and vaccination equipment expiry and wastage.

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Bhutan, considering that its DTP3 coverage for 2001 was …86……%  corresponding to 17474 number of children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

Not applicable

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

Not applicable

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| DTP+HepB, | 10 doses vials | Jan 2003 |  |  |
| DTP+HepB+Hib | 2 doses vials | Subject to timing of GAVI approval and possibility of changing from approved DPT-HepB to pentavallent vaccine | Subject to timing of GAVI approval and possibility of changing from approved DPT-HepB to pentavallent vaccine | 92,165 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                              By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | - | 22343 | 23142 | 24215 |
|  |  | for other vaccines Measles and TT | - | 174190 | 174190 | 183396 |
| I | Total of reconstitution syringes |  | - | 14364 | 13439 | 11097 |
| J | Total of safety boxes |  | - | 4218 | 4215 | 4374 |

* Includes supplies for supplementary immunization with measles and TT

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

- The ICC is concerned by the Hib burden in under-five children and strongly recommends the introduction of Hib vaccine in form of pentavallent DTP+HepB+Hib;

- The ICC also recommends switching over to AD syringes for all vaccination;

- As the resources of existing partners and Government are limited, GAVI is being approached for support for new vaccine and injection safety. However, the Royal Government of Bhutan and the ICC partners have agreed to work together to ensure sustainability; and

- The ICC partners will continue to advocate and work to mobilize resources for other EPI activity and the Health system.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - BCG, DPT, Measles, OPV and TT |  |  |  | Japan |  |  |  |  | $ 61,499 |
| 1.2 | - HepB |  |  |  | DANIDA |  |  |  |  | 29,166 |
|  | - Disposable syringes |  |  |  | DANIDA |  |  |  |  | 2,083 |
|  | Lab.supplies |  |  |  | DANIDA |  |  |  |  | 16,666 |
|  | IEC activity |  |  |  | DANIDA |  |  |  |  | 4,166 |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators |  |  |  | Japan |  |  |  | Japan | 20,000 |
|  | - Cold boxes |  |  |  | Japan |  |  |  |  |  |
|  | - Vaccine carriers |  |  |  | Japan |  |  |  |  | 1,950 |
|  | - Miscellaneous spares |  |  |  | Japan |  |  |  |  | 13,800 |
|  | - Sterilisation equipment |  |  |  | Japan |  |  |  |  | 4,340 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - WHO Support |  |  |  |  |  |  |  |  | 139,875 |
| 3.2 | - UNICEF |  |  |  |  |  |  |  |  | 126,720 |
| Total expenditure |  |  |  |  |  |  |  |  |  | 420,265 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - BCG, DPT, Measles, OPV and TT |  |  |  | Japan |  |  |  |  | $ 61,499 |
| 1.2 | - HepB |  |  |  | DANIDA |  |  |  |  | 29,166 |
|  | - Disposable syringes |  |  |  | DANIDA |  |  |  |  | 2,083 |
|  | Lab.supplies |  |  |  | DANIDA |  |  |  |  | 16,666 |
|  | IEC activity |  |  |  | DANIDA |  |  |  |  | 4,166 |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators |  |  |  | Japan |  |  |  | Japan | 20,000 |
|  | - Cold boxes |  |  |  | Japan |  |  |  |  |  |
|  | - Vaccine carriers |  |  |  | Japan |  |  |  |  | 1,950 |
|  | - Miscellaneous spares |  |  |  | Japan |  |  |  |  | 13,800 |
|  | - Sterilisation equipment |  |  |  | Japan |  |  |  |  | 4,340 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - WHO Support |  |  |  |  |  |  |  |  | 139,875 |
| 3.2 | - UNICEF |  |  |  |  |  |  |  |  | 126,720 |
| Total expenditure |  |  |  |  |  |  |  |  |  | 420,265 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number 1 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number 2 |
| - Terms of reference of the ICC | Document number 3 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 4,5 and 6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 7 and 8 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 8, Section I, Executive summary |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 9 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 10 Document number 11 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number 12 |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of ………………………………….., hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

The wastage estimate is based on the assumption that 2 dose vials of DPT+HepB+Hib will be provided form 2003. The wastage will be higher with higher dose vials

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

The assistance is through UNICE-Japan Government Multi-Bilateral support

The assistance is through UNICE-Japan Government Multi-Bilateral support

Please submit hard copy documents with an identical electronic copy whenever possible