Revision  4

August  2002

The Government of

Burkina Faso

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

In 2000, when Burkina Faso submitted its proposal for the strengthening of immunization services, 266,917 children had been vaccinated with DTP3, or 57% of the 467,459 children targeted at the beginning of the year. Burkina Faso’s proposal was accepted, and the country received the  first tranche of US$ 874,000 in June 2001. The steps taken with the help of the ICC and the funds allocated enabled the country to improve its performance in 2001 and to immunize 323,986 children, or more than 60% of children, with DTP3. For 2002, Burkina Faso’s objective under the strategic plan is to obtain a coverage rate of at least 65% in December 2002. However, in order to be in line with the other countries of the West Africa epidemiological block, measures are being taken to attain a coverage rate of 70% at national level and of at least 50% in all the districts. The strategies on the basis of which the programme hopes to meet those objectives are essentially:

- a resumption of supervision; 90% of all districts were visited at least once this year, and those that made the poorest showing were the object of follow-up and monitoring;

- financial support using GAVI funds for districts in which the microplans were not financed in 2002;

- reinforcement of the cold chain via the purchase of 150 SIBIR refrigerators for the health units, to be financed by the State (Highly Indebted Poor Country);

- the acquisition of 72 motor scooters for the out-reach strategy implemented by the vaccination centres;

- the availability in the districts of syringes for free immunization so as to lower the financial barrier;

- training for regional and district EPI managers;

- monitoring of activities during decentralized meetings involving EPI managers and the managers of the regional and health district Information and Epidemiological Surveillance Centres.

Involvement of the ICC in drawing up the proposal: the institutions members of the ICC were involved at different levels in preparing the proposal documents. After an exchange of views on the initial drafts with the resources persons identified in the institutions as members of the technical group, a meeting was held to amend and adopt the documents.

This application concerns the reinforcement of injection safety. Burkina Faso has already received funds to strengthen immunization services. Given that the EPI review took place in 1998, it plans to conduct a programme review before submitting an application in 2003 for the introduction of new vaccines (hemophilus influenzae and hepatitis B).

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of Burkina Faso commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	Minister of Health

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health | Jean Gabriel OUANGO Secretary General |  |
| WHO | Mohamed M. HACEN Representative |  |
| UNICEF | Mrs. JOAN-FRENCH Representative |  |
| Save the Children Netherlands | Yacouba ZINA Representative |  |
| Rotary | Marcel SORGHO Chairman |  |
| ARIVA (Support for the Strengthening of Vaccine Independence in Africa) EDF project | Hamidine Mahamane Coordinator |  |
| World Bank | Mr. Ibrahim MAGAGI Representative |  |
| Plan Burkina Faso | Jean Baptiste KOAMA Representative |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Jean Gabriel G. OUANGO	Title/Address: Secretary General, Ministry of Health

Tel. No.: 24 01 95   (226) 32 41 64

Fax No.: (226) 32 41 85

E-mail: ouango@yahoo.fr

Alternative address:

Name: Dr. André YAMEOGO	Title/Address: Head, Immunization Prevention Service

Tel. No.: (226) 32 46 69

Fax No.: (226) 32 46 67

E-mail: spv@burkinaonline.bf

Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population |  | GNP per capita | $US |
| Surviving Infants* |  | Infant mortality rate | / 1000 |
| Percentage of GDP allocated to Health |  | Percentage of Government expenditure for Health Care |  |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  |  |  |  |  |  |  | Tuberculosis |  |  |
| DTP | DTP1 |  |  |  |  |  |  |  | Diphtheria |  |  |
|  | DTP3 |  |  |  |  |  |  |  | Pertussis |  |  |
| OPV3 |  |  |  |  |  |  |  |  | Polio |  |  |
| Measles |  |  |  |  |  |  |  |  | Measles |  |  |
| TT2+ (Pregnant women) |  |  |  |  |  |  |  |  | NN Tetanus |  |  |
| Hib3 |  |  |  |  |  |  |  |  | Hib |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  |  |  |  |  |  |  |  | hepB seroprevalence (if available) |  |  |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) |  |  |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) |  |  |  |  |  |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

- Summary of health system development status relevant to immunization:

| - Attached are the relevant section(s) of strategies for health system development | Document number………….. |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC:…………………………………………………………………………………………

- Date of constitution of the current ICC:…………………………………………………………………

- Organisational structure (e.g., sub-committee, stand-alone):…………………………………………….

- Frequency of meetings:…………………………………………………………………………………

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair |  |  |
| Secretary |  |  |
| Members | …………. |  |

- Major functions and responsibilities of the ICC:

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number……. |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number……. |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |

- The three major strengths identified in the assessments:

- The three major problems identified in the assessments:

- The three major recommendations in the assessments:

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number….. |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number….. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number……. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| Vitamin A |  |  |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births (crude birth rate 46.1/1000) |  | 535,016 | 547,857 | 561,005 |  | 574,470 | 588,257 | 602,375 | 616,832 | 631,636 |
| Infants’ deaths (mortality rate: 105.3/1000) |  | 56,337 | 57,689 | 59,074 |  | 60,492 | 61,943 | 63,430 | 64,952 | 66,511 |
| Surviving infants |  | 478,679 | 490,167 | 501,932 |  | 513,978 | 526,313 | 538,945 | 551880 | 565,125 |
| Pregnant women |  | 580,278 | 594,205 | 608,466 |  | 623,069 | 638,023 | 653,335 | 669,015 | 685,071 |
| Infants vaccinated with BCG* |  | 425,838 *** | 406,839 **** | 476,855 |  | 502,661 | 514,725 | 542,137 | 555,149 | 568,472 |
| Infants vaccinated with OPV3** |  | 323,986 *** | 318,609 **** | 376,449 |  | 398,333 | 421,051 | 458,103 | 482,895 | 508,612 |
| Infants vaccinated with DTP** |  | 323,986 *** | 318,609 **** | 188,224 |  | - | - | - | - | - |
| Infants vaccinated with measles** |  | 329,943 *** | 318,609 **** | 376,449 |  | 398,333 | 421,051 | 458,103 | 482,895 | 508,612 |
| Infants vaccinated with yellow fever** |  | 261,947 *** | 318,609 **** | 376,449 |  | 398,333 | 421,051 | 458,103 | 482,895 | 508,612 |
| Infants having received the three doses of DTP-Hib |  | - | - | 188,224 |  | 398,333 | 421,051 | 458,103 | 482,895 | 508,612 |
| Infants having received the four doses of hepatitis |  | - | - | 188,224 |  | 398,333 | 421,051 | 458,103 | 482,895 | 508,612 |
| Pregnant women vaccinated with TT+ |  | 234,904 *** | 267,392 | 289,021 |  | 311,534 | 350,912 | 392,001 | 434,860 | 462,423 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) |  |  |  |  |  |  |  |  |  |
|  | Infants (> 6 months) |  |  |  |  |  |  |  |  |  |
| * Target of children out of total births *** Number of children/women immunized in 2001 according to administrative data |  |  |  |  | ** Target of children out of surviving infants **** Estimates based on the coverage targets set forth in the strategic plan and the target population according to the 1996 census forecast |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate |  |  |  |  |  |  |  |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 |  |  |  |  |  |  |  |  |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

# 7. Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

In 2000, the analysis of the injection safety situation in Burkina Faso revealed inter alia not only that the health units had an insufficient supply of adequate injection material, that health personnel did not apply measures of hygiene, and that nothing was being done to monitor and treat adverse events following immunization, but also that there was no proper system for collecting and destroying waste material. In order to ensure that injections are safe for the patients who receive them, the agents that administer them and the communities that can be victims, Burkina Faso has adopted a general injection safety policy and plan (2002-2005).

The strategies that will be implemented to guarantee injection safety are as follows:

- health centres will be provided with sufficient quantities of good quality material for injections and to collect and destroy waste;

- the system for collecting and destroying waste material will be improved and adapted to safety regulations;

- training/information activities on injection safety will be used to promote a safe injection culture among health agents and the community;

- a culturally sensitive injection safety communication strategy will be developed for the community and the volunteers involved in providing health services;

- a system will be established for monitoring and managing adverse events following immunization;

- the progress made towards injections safety will be monitored;

- a unit will be set up to monitor implementation of injection safety activities.

Implementation of these strategies implies close cooperation between the Ministry of Health, the country’s development partners, including the ICC members, and the FOCUS project.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 1 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for BCG vaccination | Match with targets in table 4 | 476,855 | 502,661 | 514,725 | 542,137 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 476,855 | 502,661 | 514,725 | 542,137 |
| D | AD syringes (+10% wastage) | C x 1.11 | 529,309 | 557,954 | 571,344 | 601,773 |
| E | AD syringes buffer stock | D x 0.25 | 132,327 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 661,636 | 557,954 | 571,344 | 601,773 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 2 | 2 | 2 | 2 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 105,862 | 111,591 | 114,269 | 120,355 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 8,519 | 7,432 | 7,610 | 8,016 |

| Table 6.2: Estimated supplies for safety of vaccination with DTP |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for DTP vaccination | Match with targets in table 4 | 188,224 | - | - | - |
| B | Number of doses per child | # | 3 | - | - | - |
| C | Number of DTP doses | A x B | 564,673 | - | - | - |
| D | AD syringes (+10% wastage) | C x 1.11 | 626,787 | - | - | - |
| E | AD syringes buffer stock | D x 0.25 | 156,697 | - | - | - |
| F | Total AD syringes | D + E | 783,484 | - | - | - |
| G | Number of doses per vial | # | 10 | - | - | - |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | - | - | - |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | - | - | - | - |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 8,697 | - | - | - |

| Table 6.1: Estimated supplies for safety of vaccination with DTP-Hib |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for DTP-Hib vaccination | Match with targets in table 4 | 188,224 | 398,333 | 421,051 | 458,103 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 |
| C | Number of DTP-Hib doses | A x B | 564,673 | 1,194,999 | 1,263,152 | 1,374,309 |
| D | AD syringes (+10% wastage) | C x 1.11 | 626,787 | 1,326,448 | 1,402,099 | 1,525,483 |
| E | AD syringes buffer stock | D x 0.25 | 156,697 | - | - | - |
| F | Total AD syringes | D + E | 783,484 | 1,326,448 | 1,402,099 | 1,525,483 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 100,286 | 212,232 | 224,336 | 244,077 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 9,810 | 17,079 | 18,053 | 19,642 |

| Table 6.4: Estimated supplies for safety of vaccination with hepatitis |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for hepatitis vaccination | Match with targets in table 4 | 188,224 | 398,333 | 421,051 | 458,103 |
| B | Number of doses per child | # | 4 | 4 | 4 | 4 |
| C | Number of hepatitis doses | A x B | 752,897 | 1,593,331 | 1,684,203 | 1,832,413 |
| D | AD syringes (+10% wastage) | C x 1.11 | 835,716 | 1,768,598 | 1,869,465 | 2,033,978 |
| E | AD syringes buffer stock | D x 0.25 | 208,929 | - | - | - |
| F | Total AD syringes | D + E | 1,044,645 | 1,768,598 | 1,869,465 | 2,033,978 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 133,715 | 282,976 | 299,114 | 325,436 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 13,080 | 22,772 | 24,071 | 26,189 |

| Table 6.5: Estimated supplies for safety of vaccination with measles |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for measles vaccination | Match with targets in table 4 | 376,435 | 398,241 | 420,872 | 430,889 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 |
| C | Number of measles doses | A x B | 376,435 | 398,241 | 420,872 | 430,889 |
| D | AD syringes (+10% wastage) | C x 1.11 | 417,843 | 442,048 | 467,168 | 478,287 |
| E | AD syringes buffer stock | D x 0.25 | 104,461 | - | - | - |
| F | Total AD syringes | D + E | 522,304 | 442,048 | 467,168 | 478,287 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 66,855 | 70,728 | 74,747 | 76,526 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 6,540 | 5,692 | 6,015 | 6,158 |

| Table 6.6: Estimated supplies for safety of vaccination with yellow fever |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for anti amaril vaccination | Match with targets in table 4 | 376,435 | 398,241 | 420,872 | 430,889 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 |
| C | Number of anti amaril doses | A x B | 376,435 | 398,241 | 420,872 | 430,889 |
| D | AD syringes (+10% wastage) | C x 1.11 | 417,843 | 442,048 | 467,168 | 478,287 |
| E | AD syringes buffer stock | D x 0.25 | 104,461 | - | - | - |
| F | Total AD syringes | D + E | 522,304 | 442,048 | 467,168 | 478,287 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 66,855 | 70,728 | 74,747 | 76,526 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 6,540 | 5,692 | 6,015 | 6,158 |

| Table 6.7: Estimated supplies for safety of vaccination with TT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of pregnant women for TT vaccination | Match with targets in table 4 | 289,021 | 311,534 | 350,912 | 392,001 |
| B | Number of doses per woman | # | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 578,042 | 623,069 | 701,825 | 784,002 |
| D | AD syringes (+10% wastage) | C x 1.11 | 641,627 | 691,606 | 779,026 | 870,242 |
| E | AD syringes buffer stock | D x 0.25 | 160,407 | - | - | - |
| F | Total AD syringes | D + E | 802,034 | 691,606 | 779,026 | 870,242 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | - | - | - | - |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 8,903 | 7,677 | 8,647 | 9,660 |

7.3	Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| National budget | AD syringes, re-constitution syringes, safety boxes | 2001 |
| WHO | Safety boxes | 2002 |
| GAVI/Vaccine Fund | AD syringes, re-constitution syringes and safety boxes | 2002 |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses  of   ………...   vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  |  |  |  |  |
| B | Percentage of vaccines requested from The Vaccine Fund | % |  |  |  |  |  |  |
| C | Number of doses per child | # |  |  |  |  |  |  |
| D | Number of doses | A x B/100 x C |  |  |  |  |  |  |
| E | Estimated wastage factor | see list in table  |  |  |  |  |  |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 |  |  |  |  |  |  |
| G | Vaccines buffer stock | F x 0.25 |  |  |  |  |  |  |
| H | Total vaccine doses requested | F + G |  |  |  |  |  |  |
| I | Number of doses per vial | # |  |  |  |  |  |  |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  |  |  |  |  |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  |  |  |  |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  |  |  |  |  |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number…… |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number .…. |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Burkina Faso, considering that its DTP3 coverage for 2001 was 67.68%, corresponding to 323,986 children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		NO

- Support for New and Under-used vaccines                               NO

- Support for Injection Safety                                                      YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		X The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002* | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | 564,489 | 661,636 | 557,954 | 571,344 |
|  |  | for other vaccines | 2,951,106 | 4,458,253 | 4,670,748 | 4,984,925 |
| I | Total of reconstitution syringes |  | 281,248 | 473,572 | 748,253 | 787,213 |
| J | Total of safety boxes |  | 42,145 | 62,087 | 66,344 | 70,413 |

* With the support of its partners, Burkina Faso has met the needs for syringes in 2002. GAVI support, anticipated over three years, is required as of 2003.

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

The ICC notes with satisfaction GAVI’s decision to support the country’s efforts to ensure injection safety. It nevertheless notes that to date that support has been provided in the form of syringes and safety boxes. While this is certainly appreciated, if countries are to meet the objective of safe injections they need not just donations of appropriate consumables for their health units but also to strengthen the capacities of their agents and organize a system to collect and destroy waste. The ICC therefore recommends that:

- GAVI and the Fund grant countries additional sums to strengthen the capacities of their agents;

- GAVI and the Fund grant sums to construct incinerators in health facilities.

These sums should be in addition to those allocated to the country to strengthen health services. Given the need to provide all children with safe injections without delay, and in the light of the high cost of those measures and until such time as the countries have organized to ensure funding of all components, the ICC would like consideration to be given to those recommendations.

The ICC observes that not only do breakdowns in the supply of syringes have a negative impact on the use of services, they also foster the use of syringes that do not guarantee safe injections. The ICC would therefore like GAVI and the Fund, if Burkina Faso’s application is accepted, to set up a reliable supply circuit enabling the country to receive the consumables requested without interruption.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2001 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number……. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Terms of reference of the ICC | Document number…… |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number…… |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number…… |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number…… |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…… |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…… Document number 1 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number…… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of Burkina Faso hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  | MINISTRY OF HEALTH |  |  |  |  |  |  |  |  |
| #### Address: |  | 03 BP 7009 OUAGADOUGOU 03 |  |  |  |  |  |  |  |  |
| #### City – Country: |  | Ouagadougou, Burkina Faso |  |  |  |  |  |  |  |  |
| Telephone No.: |  | 31 41 64 |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  | Expanded Programme on Immunization |  |  |  |  |  |  |  |  |
| Bank account No.: |  | 305 1000 5235 C 00 |  |  |  |  |  |  |  |  |
| At: Bank’s name |  | BCEAO |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( x ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  | The Minister of Health |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: | Bédouma Alain YODA |  |  |  |  |  |  |  | Seal: |  |
| #### Title: | Minister of Health |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  | BCEAO |  | FEDERAL RESERVE BANK OF NEW YORK – 33 LIBERTY STREET |  |
| Branch Name: |  | OUAGADOUGOU |  | NEW YORK 10045 (USA) |  |
| Address: |  | BURKINA FASO |  |  |  |
| City – Country: |  | OUAGADOUGOU |  |  |  |
| Swift code: |  | BCEAOBFBFAXXX |  | FBNY11533 |  |
| Sort code: |  |  |  | ACCOUNT NO. 021085457 |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  | (226) 31 08 00 / 30 60 15/16 |  |  |  |
| Fax No.: |  | (226) 31 11 22 |  | (212) 720 63 31 |  |
| I certify that the account No. 305 1000 5235 C00 is held by (Institution name) THE MINISTRY OF HEALTH at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least 2 (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: | Bédouma Alain YODA |  | Signature: |  |  |
|  | Minister of Health |  | Date: |  |  |
| 2 Name: Title: | Dr. Jean Gabriel OUANGO |  | Seal: National Director BCEAO |  |  |
|  | Secretary General, Ministry of Health |  |  |  |  |
| 3 Name: Title: | Emmanuel LALSOMDE |  |  |  |  |
|  | Director of Administrative and Financial Affairs |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  | Bédouma Alain YODA |  |  | Minister of Health |
| Bank’s authorizing official |  |  |  |  | National Director |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name | Mrs JOAN-FRENCH |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible