Revision  4

August  2002

The Government of

REPUBLIC OF CAMEROON

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Government of the Republic of Cameroon submitted its first request for GAVI support in January 2001. That request consisted of assistance from the Fund to support the vaccination services, and for the introduction of hepatitis B and yellow-fever vaccine. The Government thanks the Executive Committee of GAVI for its favourable response, which enabled Cameroon to receive the first tranche of funds to support an improvement of its vaccination services.  The request for support for the introduction of yellow-fever vaccine and for hepatitis B vaccine was accepted conditionally.

The initial report on EPI activities in the first year following support from the Fund and also details of how the funds received were used was submitted to the GAVI secretariat during the first quarter of 2002.

This submission is a request to GAVI / The Fund for support for the inclusion of yellow-fever vaccine in the routine EPI and also for the introduction of an appropriate mechanism for vaccination injection safety. The details of this request are as follows:

1) Introduction of yellow-fever vaccine in July 2003:

| Year | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| Vaccination coverage | 60% | 67% | 72% | 76% | 80% |
| Estimated wastage | 1.75 | 1.49 | 1.33 | 1.25 | 1.18 |
| Total doses | 870,426 | 681,253 | 672,431 | 686,440 | 701,885 |

2) Vaccination  injection safety;

It is planned to introduce auto-destruct syringes throughout the routine EPI from January 2003.  The requirements for injection equipment and safety boxes for the five next years are shown below:

| Summary of total supplies for safety of vaccinations with BCG, DTP, TT, and MEASLES, requested from GAVI and the Vaccine Fund (fill in the total sums of rows “F”,”H” and “ I” of tables 6.1,6.2, 6.3, and 6.4). |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| F | Total AD syringes | for BCG | 747,696 | 656,537 | 700,910 | 738,616 | 760,036 |
|  |  | for other vaccines | 4,163,746 | 3,741,949 | 4,103,786 | 4,447,371 | 4 69,886 |
| H | Total syringes of reconstitution |  | 261,789 | 293,400 | 322,661 | 351,335 | 373,078 |
| I | Total of safety boxes |  | 57,423 | 52,080 | 56,914 | 61,464 | 64,657 |

As is explained in the initial report of the Government of Cameroon to GAVI / The Fund of April 2002, vaccine supplies were disrupted following a delay in the release of State funds for the purchase of vaccines, which resulted in a sharp drop in DTC3 vaccination coverage. Efforts were made to ensure that this situation is not repeated, and also to ensure that vaccination coverage returns rapidly to its expected level.

A detailed plan for the introduction of hepatitis B vaccine will be drafted and submitted to GAVI / The Fund once the efforts to raise EPI vaccination coverage have produced results.

The Government of Cameroon would like to take this opportunity to thank the Executive committee of GAVI / The Fund for its support to the efforts to give fresh impetus to the EPI/Cameroon for the protection of the children of Cameroon against vaccine-preventable diseases.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of ………… THE REPUBLIC OF CAMEROON …………….. commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	Mr. Urban OLANGUENA AWONO

Title:	Minister for Public Health...................

Date:	……30 August 2002…………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry for Public Health | Dr KOLLO Basile Vice-Chairman ICC |  |
|  | Dr NOMO Emmanuel Permanent Secretary EPI |  |
| WHO | Dr H. MAMBU-ma-Disu Representative of WHO |  |
| UNICEF | Dr NDIAYE Jean Michel Representative of UNICEF |  |
| European Union | Dr Paolo MAX OPERTI Health Unit Coordinator Program of Support to the Health Sector |  |
| French Cooperation | Dr GARDE Xavier Regional Health Advisor |  |
| GTZ | Dr STADLER Andreas Principal Tech. Advisor on GTZ health projects |  |
| Japanese Cooperation | Not committing |  |
| ROTARY INTERATIONAL | Mr BIELEU Jean Richard Chairman of the National Polio Plus Commission |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Dr  NOMO Emmanuel	Title/Address: Permanent Secretary of the EPI.

Tel.No.: (+237) 223 09 47…………….		(+237) 223 09 42……………..

Fax No.:… (+237) 223 09 47……….. 		            ………………………………..

E-mail:…… muser@camnet.cm ……                         ……………………………….

Alternative address:

Name: Dr  C. SHEY UMARU WIYSNGOE	Title/Address: Deputy Permanent Secretary  of the EPI

Tel.No.: …(+237) 223 09 42….   		            ………………………………..

Fax No.:… (+237) 223 09 47…….. 	            ………………………………..

E-mail:…… wiysNGOe@yahoo.com …                         ……………………………….

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 16,112,300 | GNP per capita | 684 USD |
| Surviving Infants* | 644,492 | Infant mortality rate | 77 / 1000 |
| Percentage of GDP allocated to Health | n.a. | Percentage of Government expenditure for Health Care | 4.5 % |

* Surviving infants = Infants surviving the first 12 months of life

The figures given are estimates for 2002

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| #### Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 69% | 66% | 78% | 12-23 months |  |  | Tuberculosis | n.a. | n.a. |
| DTP | DTP1 |  | 67% | 54% | 69% | 12-23 months |  |  |  | n.a. | n.a. |
|  | DTP3 |  | 54% | 43% | 45% | 12-23 months |  |  |  | n.a. | n.a. |
| OPV3 |  |  | 53% | 45% | 50% | 12-23 months |  |  | Polio |  |  |
| Measles |  |  | 49% | 45% | 62% | 12-23 months |  |  | Measles | 14,626 | 23,934 |
| TT2+ (Pregnant women) |  |  | 40% | 36% | 67% | 12-23 months |  |  | NN Tetanus | 279 | 208 |
| Hib3 |  |  | n.a. | n.a. | n.a. |  |  |  | Hib | n.a. | n.a. |
| Yellow Fever |  |  | n.a. | n.a. | n.a. |  |  |  | Yellow fever | n.a. | n.a. |
| HepB3 |  |  | n.a. | n.a. | n.a. | 12-23 months |  |  | hepB seroprevalence (if available) | n.a. | n.a. |
| Vit A supplementation |  |  |  | 8,9% |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) |  |  |  |  |  |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage amNGO infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: the figures are the official figures compiled in the EPI at various levels. The figures were corroborated by those of the Multi-Indicator Cluster Survey (MICS) for 2000.

- Summary of health system development status relevant to immunization:

In 1982, after the Alma Ata Conference of 1978, Cameroon started the reform of its health system with the primary health care (PHC) strategy. With the reorientation of Primary Health Care started in 1989 and the Declaration on the National Reorientation Policy of 1993, inspired by the Bamako Initiative, the country acquired an appropriate institutional framework for pursuing the reform of its health system. Under this new approach, the health system is modeled on a pyramidal structure with decentralized management. The pyramid consists of three levels:

- Central - for policy  orientation;

- Intermediate or provincial  - for strategic support to the districts, and

- Peripheral or district - for operational technical support to the health areas.

The country consists of 150 health districts. The Integrated Health Center is the level of first contact with the population, dispensing a minimum package of activities (MPA) of promotional, preventive and curative care. Medical establishments are classified by level as follows:

Central  Level:

In 1982, after the Alma Ata Conference of 1978, Cameroon started the reform of its health system with the primary health care strategy.  With the reorientation of PHC started in 1993, we have at this level :

- the General Hospitals (3) including a Hospital and University Center (CHU), and the Central Hospitals (3) including a denominational hospital

Intermediate Level:

- The provincial and similar hospitals (09)

Peripheral Level:

- the District Hospitals, the 97 District Medical Centers (DMC), and the 1,277 Integrated Health Centers (IHC) 7

The major challenge is to get the 150 Health Districts up and running, thus enabling the country to achieve the objectives of its priority programs, including those of the Expanded Program of Immunization.

Relevant sections of strategies for Health  system development  Document number CAE 1

Sectoral Health Strategy, Section on the Expanded Program of Immunization   (Document CAE 1, annexed)

| - Attached are the relevant section(s) of strategies for health system development | Document number… CAE 1….. |
| --- | --- |

# Following the external review of the EPI of 1999, the Ministry of Public Health of Cameroon has developed the five-year plan for 2001-2005 for the program.

# The overall objective is to reduce infant and juvenile mortality and morbidity due to vaccine-preventable diseases. The specific objectives are:

- To achieve vaccination coverage of 80% of children 0 - 11 months old (DTP3, MEAS, OPV3, BCG, HVB, AAV) and of pregnant women (TT2)

- To ensure 100% injection safety

- To reduce mortality and morbidity by 95% and 90% respectively

- To eliminate maternal and neonatal tetanus

- To eradicate poliomyelitis.

The plan will focus on the following strategic axes:

- Strengthening EPI management capabilities at all levels

- Establishment of contracts with the districts

- Renovation/replacement of equipment, vehicles and cold chains

- Development of communication to bring about behavioral change

- Implementation of a strategy for injection safety and management of used injection equipment

- Introduction of new vaccines in the routine EPI (yellow fever and viral hepatitis B)

- Intensification of integrated epidemiological surveillance of the target diseases

- Closer monitoring and supervision.

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC:… Inter Agency Co-ordinating Committee …………………………

- Date of constitution of the current ICC:…… 01 August 2002…………………………………

- Organisational structure (e.g., sub-committee, stand-alone):… Independent body….

- Frequency of meetings: Six-monthly regular sessions and extraordinary sessions convened by the Minister For Public Health, Chairman of the ICC

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister For Public Health | Mr Urban Olanguena Awono |
| Vice-Chairman | Vice-Chairman | Dr Kollo Basile |
| Secretary | Permanent secretary of the EPI | Dr Nomo Emmanuel |
| Members | - Representative of WHO - Representative UNICEF - Representative of French Cooperation - Representative of the European Union - Representative of the GTZ - Representative of Japanese Cooperation - Representative of Rotary International - Chairman of the Red Cross | Dr Mambu Ma Disu Dr Ndiaye Jean Michel Dr Garde Xavier Dr Paolo MAX OPERTI Dr Andreas Stadler Not committing Mr Jean Richard Bieleu Mr William Eteki Mboumoua |

- Major functions and responsibilities of the ICC:

- Approval of the annual and five-year plans of action of the EPI.

- Coordination of EPI activities between the various partners.

- Monitoring and evaluation of the execution of EPI activities.

- Mobilization of the resources necessary for implementation of the program.

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Six-monthly meetings or on request for monitoring of execution of the plan.

- Adoption of the budgets for EPI activities and for a variety of documents.

- Putting the case for the mobilization of resources for the EPI

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Reduction of drop-out rates

- Rate of implementation of the programmed activities per year

- Reduction of vaccine wastage

- Number of meetings held by the ICC compared with the number planned

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number CAE 2 |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number CAE 3. |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number CAE 4-6 |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| External Global Review of the Expanded Program of Immunization in Cameroon | WHO; UNICEF; French Cooperation; Rotary; European Union | September 1999 |

- The three major strengths identified in the assessments:

- Supplies of vaccines channeled through UNICEF and the European Union are satisfactory and are moving towards vaccination independence

- Vaccination activity reports are produced by the Health Districts

- There is a cold chain in the majority of medical establishments

- The three major problems identified in the assessments:

- Lack of visibility of the EPI in the organization chart of the Ministry of Health

- Absence of any EPI policy document, norms and standards

- The lack of  EPI management capabilities

- The three major recommendations in the assessments:

- Restructuring of the EPI and improvement of its visibility in the organization chart of the Ministry of Health - Drafting of the EPI policy document and of norms and standards - Training at all levels

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number CAE 7*. |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number CAE 8. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Survey of injection safety | February 2003 |
| Assessment of vaccine wastage | April 2003 |
| Behavioral study of communities in relation to vaccination in the provinces | November 2002 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number CAE 9* |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Support for customization of the MLM modules | May 2003 | WHO |
| Logistics consultant support | September 2002 | WHO |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | Birth | X |  |  |
| OPV | Birth, 6,10,14 weeks | X |  |  |
| DTP | 6,10,14 weeks | X |  |  |
| MEAS | 9 months | X |  |  |
| AAV | 9 months | X |  | From January 2003 |
| TT 2+ | Pregnant women (during ante-natal consultations | X |  |  |
| Vitamin A | 9 months (1 dose by the EPI, the remainder by PCIME) | X |  | Since April 2002 |

- Summary of major action points and timeframe for improving immunization coverage:

- Stepping up of social mobilization activities

- Establishment of contract plans financed with the health districts.

- Renewal/replacement of cold chain equipment and vehicles.

- Giving new impetus to the system for the collection, analysis  and transmission of data.

- Regular supplies of vaccines and consumables to health centers.

- Intensification of the outreach strategies

- Training  staff in program management

- Regular supervision

- Introduction of incentive measures for vaccination staff.

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births |  | 678,579 | 698,258 | 718,507 |  | 739,343 | 760,784 | 782,847 | 805,550 |  |
| Infants’ deaths |  | 52,251 | 53,766 | 55,325 |  | 56,929 | 58,580 | 60,279 | 62,027 |  |
| Surviving infants |  | 626,328 | 644,492 | 663,182 |  | 682,414 | 702,204 | 722,568 | 743,522 |  |
| Infants vaccinated with BCG* |  | 66% 447,862, | 70% 488,780 | 75% 538,880 |  | 80% 591,474 | 83% 631,450 | 85% 665,419 | 85% 684,717 |  |
| Infants vaccinated with OPV3** |  | 43% 269,321 | 55% 354,471 | 65% 431,068 |  | 70% 477,690 | 75% 526,653 | 80% 578,054 | 82% 609,688 |  |
| Infants vaccinated with DTP3** |  | 43% 269,321 | 55% 354,471 | 65% 431,068 |  | 70% 477,690 | 75% 526,653 | 80% 578,054 | 82% 609,688 |  |
| Infants vaccinated with Measles** |  | 47% 294,374 | 50% 322,246 | 60% 397,909 |  | 67% 457,217 | 72% 505,587 | 76% 549,152 | 80% 594,818 |  |
| Infants vaccinated with yellow fever*** |  | NA | NA | 60% 397,909 |  | 67% 457,217 | 72% 505,587 | 76% 549,152 | 80% 594,818 |  |
| Infants vaccinated with Hep B |  | NA | NA | NA |  | 70% 477,690 | 75% 526,653 | 80% 578,054 | 82% 609,688 |  |
| Pregnant women vaccinated with TT+ |  | 36% 281,848 | 46% 370,583 | 55% 455,938 |  | 60% 511,811 | 63% 552,986 | 65% 587,086 | 65% 604,112 |  |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | NA | NA | NA |  | NA | NA | NA | NA |  |
|  | Infants (> 6 months) | NA | 50% 322,246 | 60% 397,909 |  | 67% 457,217 | 72% 505,587 | 76% 549,152 | 80% 594,818 |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

- Purchase of vaccines in small-volume vials

- Application of the policy on opened vials

- Training of staff in vaccine management

- Ensuring there is a suitable cold chain at all levels

- Monitoring of vaccine wastage at all levels / Use of vaccine wastage management tools

- Regular training supervision

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate of DTP | 50% | 47% | 45% | 36% | 27% | 20% | 15% |  |
| Wastage rate of MEAS | 53% | 48% | 43% | 33% | 25% | 20% | 15% |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 12% | 10% | 8% | 5% | 5% | 5% | 5% |  |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

- Low routine vaccination coverage

- Scarcity of financial resources

- Weariness of the population after several rounds of NIDs requiring a review of social mobilization strategies.

- Proximity to countries where PHAs move around

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

- Publicizing the National Injection Safety Policy.

- Training of health staff involved in vaccination safety.

- Provision of a sustainable mechanism for the supply of auto-destruct syringes and safety boxes.

- Provision of an effective system for the management of used vaccination equipment at all vaccination sites.

- Closer monitoring and supervision of vaccination activities including injection safety.

- Community involvement in / awareness-building for injection safety.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number CAE 10-11 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Target of children for BCG vaccination |  | 538,880 | 591,475 | 631,451 | 665,420 | 684,717 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 538,880 | 591,475 | 631,451 | 665,420 | 684,717 |
| D | AD syringes (+10% wastage) | C x 1.11 | 598,157 | 656,537 | 700,911 | 738,616 | 760,036 |
| E | AD syringes buffer stock | D x 0.25 | 149,539 |  |  |  |  |
| F | Total AD syringes | D + E | 747,696 | 656,537 | 700,911 | 738,616 | 760,036 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 29,907 | 32,827 | 35,046 | 36,931 | 38,002 |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 8,631 | 7,652 | 8,169 | 8,609 | 8,858 |

| Table 6.2: Estimated supplies for safety of vaccination with DTP |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Target of children for DTP vaccination |  | 431,068 | 477 690 | 526 653 | 578 054 | 609 688 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 |
| C | Number of DTP doses | A x B | 1,293,204 | 1,433,070 | 1,579,959 | 1,734,162 | 1,829,064 |
| D | AD syringes (+10% wastage) | C x 1.11 | 1,435,456 | 1,590,708 | 1,753,754 | 1,924,919 | 2,030,261 |
| E | AD syringes buffer stock | D x 0.25 | 358,864 |  |  |  |  |
| F | Total AD syringes | D + E | 1,794,320 | 1,590,708 | 1,753,754 | 1,924,919 | 2,030,261 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 143,546 | 159,071 | 175,375 | 192,492 | 203,026 |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 21,510 | 19,423 | 21,413 | 23,503 | 24,789 |

| Table 6.3: Estimated supplies for safety of vaccination with MEAS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Target of children for MEAS vaccination |  | 397,909 | 457,217 | 505,587 | 549,152 | 594,818 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of MEAS doses | A x B | 397,909 | 457,217 | 505,587 | 549,152 | 594,818 |
| D | AD syringes (+10% wastage) | C x 1.11 | 441,679 | 507,511 | 561,202 | 609,559 | 660,248 |
| E | AD syringes buffer stock | D x 0.25 | 110,420 |  |  |  |  |
| F | Total AD syringes | D + E | 552,099 | 507,511 | 561,202 | 609,559 | 660,248 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 44,167 | 50,751 | 56,120 | 60,956 | 66,025 |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 6,618 | 6,197 | 6,852 | 7,442 | 8,062 |

| Table 6.4: Estimated supplies for safety of vaccination with AAV |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Target of children for AAV vaccination |  | 397,909 | 457,217 | 505,587 | 549,152 | 594,818 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of AAV doses | A x B | 397,909 | 457,217 | 505,587 | 549,152 | 594,818 |
| D | AD syringes (+10% wastage) | C x 1.11 | 441,679 | 507,511 | 561,202 | 609,559 | 660,248 |
| E | AD syringes buffer stock | D x 0.25 | 110,420 |  |  |  |  |
| F | Total AD syringes | D + E | 552,099 | 507,511 | 561,202 | 609,559 | 660,248 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 44,167 | 50,751 | 56,120 | 60,956 | 66,025 |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 6,618 | 6,197 | 6,852 | 7,442 | 8,062 |

| Table 6.5: Estimated supplies for safety of vaccination with TT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Target of women for TT vaccination |  | 455,938 | 511,811 | 552,986 | 587,087 | 604,113 |
| B | Number of doses per woman | # | 2 | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 911,876 | 1,023,622 | 1,105,973 | 1,174,174 | 1,208,225 |
| D | AD syringes (+10% wastage) | C x 1.11 | 1,012,182 | 1,136,220 | 1,227,630 | 1,303,333 | 1,341,130 |
| E | AD syringes buffer stock | D x 0.25 | 253,046 |  |  |  |  |
| F | Total AD syringes | D + E | 1,265,228 | 1,136,220 | 1,227,630 | 1,303,333 | 1,341,130 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 0 | 0 | 0 | 0 | 0 |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 14,044 | 12,612 | 13,627 | 14,467 | 14,887 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes | January 2003 |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Yellow-fever vaccine will be introduced throughout the country from 2003. The main strategies / activities selected are as follows:

- Greater accessibility of services

- Improved staff capabilities.

- Regular supplies of vaccines and injection equipment.

- Improvement of injection safety.

- Improvement of vaccine management

- Closer monitoring, supervision and evaluation

- Better communication / social mobilization

- Greater collaboration, coordination and partnership

- More intensive disease surveillance

- Operational research

- Efforts will be made to improve vaccination services with the aim of bringing vaccination coverage up to 80% in 2007.

Hepatitis B vaccine will be introduced in a combined form with DTP (tetravalent) from 2004.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| YF | n.a. |  |  |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

N.a. for new vaccines .

The introduction of yellow-fever vaccine does not raise any problems of conservation.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

Storage, cold chain and logistics capabilities :

An inventory of the cold chain carried out 1998 is being updated, as is the renovation plan; 3 cold chambers are being acquired.

Measures to prevent  freezing of vaccines, and reduce vaccine wastage and drop-out rates

  - Training  of staff at all levels in vaccine management

  - Intensification of the use of temperature sheets and other vaccine management tools (stock cards, etc..)

  - Implementation of the EPI communication plan (social mobilization) that has already been drafted to promote communication and generate demand

  - Regular training supervision visits

  - Application of the policy on opened vials

  - Orders of vaccines in small-volume (10-dose) vials if  possible

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

|  | Table 7.1 : Estimate of the number of doses of yellow-fever vaccine, 2003 - 2007 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2003 | 2004 | 2005 | 2006 | 2007 |
|  | Vaccination coverage objective |  | 60% | 67% | 72% | 76% | 80% |
| A | Number of children for VAA vaccination |  | 397,909 | 457,217 | 505,587 | 549,152 | 594,818 |
| B | Number of doses per child |  | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage | (%) | 43% | 33% | 25% | 20% | 15% |
| D | Equivalent wastage factor |  | 1.75 | 1.49 | 1.33 | 1.25 | 1.18 |
| E | Number of doses | ( A x B x D ) | 696,341 | 681,253 | 672,431 | 686,440 | 701,885 |
| F | Buffer stock of the vaccine | ( A x B x D x 0,25 ) | 174,085 |  |  |  |  |
| G | Estimated stock of vaccine at the start of 2003 |  |  |  |  |  |  |
| H | Total number of doses of vaccine required | (E + F - G) | 870,426 | 681,253 | 672,431 | 686,440 | 701,885 |
| I | Percentage of vaccine required from the Fund | (%) | 100,00 | 100 | 100 | 100 | 100 |
| J | Number of doses required from the Fund | (H x I / 100) | 870,426 | 681,253 | 672,431 | 686,440 | 701,885 |
| K | Number of doses per vial |  | 10 | 10 | 10 | 10 | 10 |
| L | Number of AD syringes (+wastage of 10%) | [(AxB)+F]x1,11xI/100 | 634,914 | 507,511 | 561,202 | 609,559 | 660,248 |
| M | Buffer stock of AD syringes | L x 0,25 | 158,728 |  |  |  |  |
| N | Total number of AD syringes required from the Fund | L + M | 793,642 | 507,511 | 561,202 | 609,559 | 660,248 |
| O | Syringes for reconstitution (+wastage 10%) | J x 1,11 / K | 96,617 | 75,619 | 74,640 | 76,195 | 77,909 |
| P | Total number of safety boxes (+wastage 10% of additional needs) | (N+O) x 1,11 / 100 | 9,882 | 6,473 | 7,058 | 7,612 | 8,194 |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

N.a.

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number CAE 12 |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

There is a budget line of 764,000,000 CFAF provided by the Government for the purchase of vaccines and consumables, which currently covers all requirements.

HIPC funds are to be used for:

Routine EPI:

Purchasing cold chain equipment, vehicles  and computing equipment.  It also makes it possible to motivate staff

Social mobilization :

Producing and distributing social mobilization tools, drawing up and implementing a social mobilization plan

Surveillance/monitoring and evaluation :

Organizing the monitoring and supervision of EPI activities at all levels.

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number CAE 13 |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

Strategies :

- Improvement of vaccine storage capacity at all levels

- Purchase of vaccines in small-volume vials ( e.g. DTP  in vials of 10 doses);

- Introduction and publicizing of the policy on opened vials;

- Improvement of the knowledge and capabilities of staff concerning vaccine management

Activities :

- Providing health centers with suitable cold-chain equipment

- Ordering vaccines in small-dose vials;

- Adopting the policy on opened vials

- Training workers in charge of the EPI in vaccine and cold chain management

- Making vaccine management tools available at all levels

- Intensifying training supervision visits

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of … CAMEROON,

considering that its DTP3 coverage for 2001 was …43%  corresponding to …269,321 children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

N.a., since Cameroon has already qualified for this support and the first tranche of funds was received in April 2002.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:) YES

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, lNGO-term sustainability and empowerment of the government in using the funds:

GAVI funds are deposited in a bank account in Yaoundé. For any activity programmed and to be performed by the EPI, a data sheet is prepared accompanied by a corresponding budget. The dossier is submitted for assessment by the Minister for Public Health, Chairman of the ICC, who authorizes funding of the activity.

A check co-signed by the Permanent Secretary of the EPI and the Director of Community Health enables withdrawal of the funds.

As funds that are to be used for the management of the public welfare, GAVI funds are subject to the same control and verification rules. Viability is still a current concern of the Government, which is making use of HIPC funds for the time being.

The contract document has been drawn up and each Health District has been asked to submit its plan of action. The target population has been determined from the 2001 population. Funds have been allocated to each District on the basis of the number  of children to be vaccinated. The contract has been signed between the EPI and the HDs on the one hand and between the HDs and the NGOs on the other. Supervision visits have been organized at all (i.e. central, provincial and district) levels.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Yellow-fever vaccine | 10 | January 2003 | 870,426 | 681,253 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system: N.a.

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund..

Support is required for the introduction of yellow-fever vaccine. Banking details are already available to the GAVI secretariat.

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

X

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG |  | 747,696 | 656,537 | 700,910 |
|  |  | for other vaccines |  | 4,163,746 | 3,741,949 | 4,103,786 |
| I | Total of reconstitution syringes |  |  | 261,789 | 293,400 | 322,661 |
| J | Total of safety boxes |  |  | 57,423 | 52,080 | 56,914 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund.

Banking details are already available to the GAVI secretariat.

# Additional comments and recommendations from the ICC

The ICC approves the introduction of yellow-fever vaccine for January 2003

The ICC approves the National Injection Safety Strategy and requests its application in all the sectors concerned.

The ICC approves the principle of appropriate waste disposal but expresses reservations as to the use of Montfort incinerators. It would like local studies to be carried out to find the appropriate equipment for the destruction of waste in Cameroon

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | WHO (USD) | GAVI | JICA | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… | 1,O91,428 |  |  |  |  | 285,714 |  |  |  |
| 1.1 | - Line item … | HIPC |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 | HIPC |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) | 178,571 |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … | HIPC |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 | HIPC |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  | 16,000 |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  | 60,000 | 19,428 |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  | 341,162 | 7,000 |  |  |  |  |
| Total expenditure |  |  |  |  | 417,162 |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2002 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO (USD) | GAVI | JICA | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  | 285,714 |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  | 55,000 |  |  |  |  |  |
| 3.2 | - Campaign support |  |  |  | 3,600,000 |  |  |  |  |  |
| Total commitment |  |  |  |  | 3,655,000 |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number CAE1. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number CAE 3. |
| - Terms of reference of the ICC | Document number CAE 2 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number CAE 4-6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number CAE 7 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number CAE 8 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number CAE 9 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number CAE 12 Document number CAE 10-11 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number Annex 1 |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: | Urban OLANGUENA AWONO |  | Signature: |  |  |
|  | MINISTER FOR PUBLIC HEALTH |  | Date: |  |  |
| 2 Name: Title: | DR KOLLO Basile |  | Seal: |  |  |
|  | VICE-CHAIRMAN OF THE ICC |  |  |  |  |
| 3 Name: Title: | DR NOMO Emmanuel |  |  |  |  |
|  | PERMANENT SECRETARY OF THE EPI |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

# Document CAE 8: Status of implementation of the recommendations 
of the external review of the EPI in Cameroon

(12 July-9 September 1999)

| Recommendations | Execution period | Responsible agency and level of implementation | State of advancement | Observations |
| --- | --- | --- | --- | --- |
| INSTITUTIONAL ASPECTS |  |  |  |  |
| 1- Consolidate the position of the EPI in the organization chart of the MPH and provincial delegations so as to confirm its priority nature | July - August 2002 | Minister for Public Health | Two tests of organization chart signed - Decision N° 0333 of 29/07/02 reorganizing the EPI - Decision N° of 1/07/02 organizing the Central Technical Group of the EPI | A firm commitment by the Minister for Public Health in favor of the program and of strengthening it is noted |
| 2- Accompany this restructuring of the organization chart with as detailed and clear a description as possible of posts and tasks, thus determining the role of each structure of the organization chart | Feb-02 | SP-CTG of the EPI | Contained in the Ministerial Decision organizing the CTG-EPI | Description of tasks and posts already done. Still to be consolidated by the appearance of the official text |
| 3- Continue the effort to reorient the health structures that the MPH has started, until medical coverage of the whole country is complete | 2001 | MPH | In progress: - The sectoral health strategy adopted in 2001. - The EPI is currently regarded as the spearhead of PHC implementation | The creation of a budget line in the FS has been recommended to enable the EPI to play this role. |
| PROGRAM MANAGEMENT |  |  |  |  |
| 1- Draft, distribute and make available at all levels the Cameroon National Immunization Policy document accompanied by the document on norms and standards relating to vaccination | Nov 2001 to March 2002 | - Minister for Public Health - the development partners | - Document Norms and Standards already drawn up and available in the HD; - EPI policy document (draft) | Finalization of the EPI policy document is subject to the appearance of the new organization chart |
| 2- Prepare systematically and as exhaustively as possible an inventory of all potential partners for involvement in the EPI (NGOs) similarly to what was done during the National Immunization Days. Using their knowledge of the field, defining together with these partners strategies to complement the traditional stationary, outreach and mobile strategies | 2001-2002 | DPSP; CSSD | Under way at various levels | EPI micro planning under way in the HD |
| 3- Strengthen the central technical group of the EPI by recruiting additional staff and also by creating a technical unit consisting of the epidemiologist and other technicians from the partner agencies of the ICC. The first job of this technical unit will be give thought to and plan the implementation of the recommendations of this review | since December 2001 | Minister for Public Health | Technical kernel functioning. A service note from the MPH has provided the EPI with additional doctors including an epidemiologist and a public health physician. | Team being strengthened |
| 4- Organize consensus workshops (with the aim of tailoring the product better) to prepare and adopt training and supervision tools based on existing tools and on WHO modules. The use of WHO/UNICEF/BASICS experts to support these workshops is strongly advised. | Mar-02 | SP-GTC of the EPI | Management tools and supervision sheet designed in the Norms and Standards document. A number of people have been trained as trainers for the MLM secondary course. A plan of action is already available for the training of other health staff. | MLM training modules still to be customized. |
| 5- Make training supervision visits a priority and extend them as far as possible to include the private structures. To make these supervision visits effective, increase the size of the vehicle fleets by providing new units or by improving the maintenance of units | 17 Sept to 30 Oct | SP-GTC of the EPI/partners | Activity partly implemented. - Supervision has been effective since April 2002. - The central EPI has just received 5 new supervision vehicles; 80 motorcycles were also delivered. | Vehicle fleets in the provinces and HDs still to be strengthened |
| 6- Extend the system of surveillance of AFP to the other diseases of the EPI and to other potentially epidemic diseases | Since April 2001 | SP-GTC of the EPI | under way - Field staff have been trained in 7 provinces for measles. - It should be noted that the tools for gathering data on tetanus and measles are available and are being used at present in the field - This aspect of integration is taken into account in the monitoring meetings |  |
| 7- Include the EPI in the basic training course for health staff |  |  | Included in the EPI management training plan for health staff |  |
| LOGISTICS |  |  |  |  |
| 1- The Government of Cameroon should involve the national structure responsible for the EPI in the supply of vaccines at the central level. The EPI should collaborate more closely with CENAME and the DPM, which should be represented on the Inter-Agency Coordinating Committee, and supplies should be reported to them. | Feb-02 | SP-GTC of the EPI; Director of CENAME | For the 2002 account, the routine EPI vaccines were purchased by the MPH through the State CENAME structure. Consumption for 2003 is under way | The director of CENAME and the DPM attended 2 meetings of the ICC |
| 2- The MPH and development partners will introduce vaccine identification cards in all vaccine depots. In the cold chain, these identification cards should contain the name of the antigen, the batch number and the use-by date. | Mar-02 | Ministry of Health and partners | Tools drawn up, pre-test done. These tools have been included in the Norms and Standards document . | Only training and reproduction still to be done |
| COMMUNICATION TO SUPPORT THE SOC/MOB PROGRAM AND THE CASE FOR IT |  |  |  |  |
| 1- The MPH must be sure that those responsible for communication working for the EPI perform (in consultation with the EPI technical managers) an analysis of the situation of the EPI, focusing on the identification and consideration of behavior. |  | SP-GTC of the EPI | A behavioral study has been scheduled since 2000. Meanwhile the EPI team attended the International Communication Workshop for the EPI in Douala in 2000, and message-tailoring workshops, and there is a media plan that is currently being implemented. | A provisional media plan is being implemented. |
| 2- The behavior patterns identified and other problems brought to light by the analysis of the situation will require further in-depth research before planning communication activities. |  | SP-GTC of the EPI | No | A provisional media plan is being implemented. |
| 3- The plan should give attention to the disparity of the situation in the provinces and should endeavor to understand the specific characteristics of each province or district from the data collected in the field. |  | # SP-GTC of the EPI | No | A provisional media plan is being implemented. |
| 4- Ensure that each district drafts its own EPI communication plan containing all three EPI system components, NIDs and disease surveillance. Make greater use of the resources of traditional means. |  |  | Under way in the HD - subject to the behavioral survey being held. |  |
| 5- Prepare a detailed practical guide to the planning of systematic EPI activities that will provide practical guidelines for its implementation. |  | # SP-GTC of the EPI | Under way: but a planning outline is available in the HD | Because of the existence of the planning unit |
| 6- Systematize the ways to mark recognition of communities (by letter from the Chief Medical Officer, DPSP, Minister passing through, etc.) for the quality of work done. |  |  |  |  |
| 7- Rely on religious and traditional authorities and community leaders to get the message over on systematic vaccination. |  | Social mobilization section | Currently under way in some health districts | Progressive |
| COST AND FUNDING OF THE EPI |  |  |  |  |
| 1- The Government should improve the EPI management environment by more rigorous requirements planning, better stock management, suitable training of health staff, and strengthening the EPI management structures. |  |  | Under way as part of the emergency plan to strengthen the EPI |  |
| 2- Increase EPI credits so as to: - satisfy all vaccine and consumables needs - ensure the regular operation of the program (supervision, evaluation, analysis, etc.). |  | Minister for Public Health in collaboration with the partners | Under way: - State budget - GAVI funds | No independent management of State credits yet |
| 3- The DPSP must be reinforced with staff with a health programs management or administration profile who are capable of improving manage-ment of the EPI and other aspects of the health system in the light of the integration of activities. |  |  |  |  |
| 4-Include in the operating budget of the MPH the overall amount of the country’s total vaccine and consumables requirements, regardless of which development partner will be paying the invoices for the orders. | Since 2001 | SP-GTC of the EPI | Done |  |
| 5- Change, in the context of the vaccination independence initiative, the current procedures for financing vaccines and consumables by giving the Government greater responsibility for the purchase and supply of vaccines and consumables. This could be done by reducing over the years the contributions of the partners to the purchase of vaccines and consumables while increasing steadily Government’s contribution until it is paying the whole of this expenditure line at the end of, for example, 5 years, thus ensuring the total vaccine independence of the Government of Cameroon. |  | MPH | Done for 2002 | The State contributed to vaccine purchases at the beginning of this year, the long-term mechanism still has to be introduced |
| 6- The ICC partners should provide financial and technical support for the efforts to revive the EPI. During this phase, support from the development partners is critical and they should mainly support investment programs. | Every year | ICC | Under way | They participate in the purchase of vaccines, vehicles and cold chain supplies (UNICEF), funding of certain activities and technical support (WHO) etc. |

Document CAE 10-11 : The injection safety plan, and the national injection safety strategy.

Document CAE 12 : Plan for the introduction of yellow-fever vaccine.

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

Please submit hard copy documents with an identical electronic copy whenever possible