Revision 3

August 2001

WHO/ UNICEF SOMALIA

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

Somalia has been in the grip of complex emergencies since the civil war that began in 1991. The UN agencies divided Somalia into four operational, which have a combined population of about 6,2 million. North/West and North/East Somalia are at present relatively politically stable, with both regions having self-declared governments. South and Central Somalia still suffer from highly fragmented political structures and sporadic armed conflicts.

Because of the absence of a central recognized government, the SACB (Somali Aid Coordination Body) health and nutrition committee, which is a combination of all local, international, NGOs, donors and representatives of Somali communities, has tried for the past five years to streamline activities related to health and nutrition in order to avoid overlapping of activities, ensure good coordination, standardization of protocols e.g. EPI and exchange of information.

Immunization services are provided, mainly through support from UNICEF, on routine basis through MCH centres and through EPI  ‘intensification’ activities in areas where MCH centres are not available. A strategy of giving priority to the most populous areas has been adopted for epidemiological as well as for operational reasons.

EPI performance is still poor in Somalia, as revealed by the last MICS conducted in 1999. Results showed that the percentage of children who had all eight recommended vaccination by their first birthday is very low at only 10 percent. Approximately 69 percent of children aged 12-23 months received a BCG vaccination by the age of 12 months and 57 % received the first dose of DPT. By 12 months, only 32.6 percent received the third dose of DPT. The coverage for measles vaccine by 12 months was 16 percent.

More additional resources are needed to build a sustainable system for EPI activities. WHO/ UNICEF on behalf of SACB and the Somali population will apply to get support from the Global Fund for Children’s Vaccines. New GAVI rules enable UN agencies to apply in case there is no formal recognized government.

The process for GAVI application was a participatory one involving partners in the SACB Health & Nutrition committee. The EPI working group prepared the application and finalize all required documents. The final application as well as the EPI review and the multi-year plan were discussed and adopted by the SACB Health & Nutrition Committee.

WHO/ UNICEF are applying for the following types of support from GAVI:

- Support for Immunization Services

- Support for Injection Safety

Immunization-related fact sheet

| Table 1 : Basic facts (For the year 2000 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 6,360,000 (2000) ** | GNP per capita | 176 $US |
| Surviving Infants* | 262278 (2000) | Infant mortality rate Crude birth rate | 132 / 1000 47.5/1000 |
| Percentage of GDP allocated to Health | 1.5 % (1997) | Percentage of Government expenditure for Health Care |  |

* Surviving infants = Infants surviving the first 12 months of life

** Human Development Report 2001

| Table 2: Trends of immunization coverage and disease burden by 12 months of age as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage ( in percentage ) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 1999 | 2000 | 1999 | Age group | 2000 | Age group |  | 1999 | 2000 |
| BCG |  |  |  | 26 | 69.3 | 1 year |  |  | Tuberculosis | 4802 | 5662 |
| DTP | DTP1 |  |  | 47.2 | 56.9 | 1 year |  |  | Diphtheria |  |  |
|  | DTP3 |  |  | 26.1 | 32.6 | 1 year |  |  | Pertussis |  |  |
| OPV3 |  |  |  | 26.1 | 36.9 | 1 year |  |  | Polio* |  | 46 |
| Measles |  |  |  | 48.7 | 15.6 | 1 year |  |  | Measles |  | 3965 |
| TT2+ (Pregnant women) |  |  |  | 25 | NA |  |  |  | NN Tetanus |  | 966 |
| Hib3 |  |  |  | NC | NA |  |  |  | Hib |  |  |
| Yellow Fever |  |  |  | NC | NA |  |  |  | Yellow fever |  |  |
| HepB3 |  |  |  | NC | NA |  |  |  | HepB seroprevalence (if available) |  |  |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) |  | NA |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) |  | NA |  |  |  |  |  |  |  |

- Virologically confirmed

- Reported vaccine coverage in the table is different from UNICEF/WHO joint report form: in fact in the form  calculations were wrong ( using under five population as denominator instead of surviving)

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: …Best estimate coverage is the MICS conducted in 1999. Administrative coverage estimates are not accurate because of problems in numerators ( health information system is been functional for only one year, the reporting system is relying on so many partners) and in denominators ( the last population census was carried out in the seventies and as such has no statistical value anymore. ……………………………………………………………………………………………………………………

- Summary of health system development status relevant to immunization:

Somalia has been in the grip of complex emergencies since the civil war that began in 1991 with the overthrow of Siad Barre. The UN Agencies divided Somalia into four operational zones, the North/West, North/East, South and Central zones, which have a combined population of about 6.2 million (a much disputed figure).  North/West and North/East Somalia are at present relatively politically stable, with both regions having self-declared governments.  South and Central Somalia still suffer from highly fragmented political structures and sporadic armed conflict.

There is no National Health system development plan available. However in the states of Somaliland and Puntland some steps have been undertaken in order to draw a health system development plan. The existing development plans have different levels of implementation.

For both entities (Somaliland and Puntland) the components of the health system development plan are the following:

- Five year strategic plan (in progress for Puntland achieved for Somaliland)

- Regional and District health planning and implementation (in progress for Somaliland to be implemented for Puntland)

- Cost sharing strategy (implemented in Somaliland, to be fully developed and implemented for Puntland)

- Human resource development plan (in progress for Somaliland to be fully developed and implemented for Puntland)

- Increasing geographic accessibility by redistributing the existing health facilities and expanding the network where needed.

- Ensuring equity

For south and central regions a health sector development plan is not available due to the security situation and the lack of an effective health authority.

| - Attached are the relevant section(s) of strategies for health system development 1. Five year Health strategy plan 2. Puntland docs | Document number…I. Document number…II |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC……… Somalia Aid Coordination Body   (SACB)………………………………………

- Date of constitution of the current ICC   December   1993…………………………………………

- Organisational structure (e.g., sub-committee, stand-alone) Established in December 1993, at the 4th Coordination meeting on Humanitarian Assistance for Somalia, the SACB is a voluntary body, which aims to provide a framework to develop a common approach for the allocation of international aid to Somalia. Given his voluntary nature, the SACB reaches decisions by consensus. All decision are therefore issued in the form of recommendations, emphasising the non-authoritarian nature of the body. However, in the continued absence of legitimate and internationally recognized forms of governance in Somalia, the SACB became, over time, a reference point, a source of information and advice for the formulation of decisions by external actors in the majority of situations.

The SACB works through a network of committees supported by a Secretariat. There are three main committees: Executive, Steering and Consultative, and five sectoral committees (Health &Nutrition, Education, Food Security &Rural Development, Water/sanitation & Infrastructure, Local Administration)

The Health &Nutrition committee is the one dealing with EPI/PEI issues. Several working groups including an ad hoc EPI one were created within the health &Nutrition committee. The EPI working group meets only on special request and especially for NIDs issues. The Health & Nutrition committee is also organizing monthly Health Sector Coordination General Meeting attended by all health NGOs and international agencies. Those meetings are aimed to review the health situation, comment on working groups outputs and make recommendations to the health& Nutrition committee.

- Frequency of meetings: The SACB Health Sectoral Committee meets every first Wednesday of the month following the Somalia Health Sector Coordination General Meetings.  The EPI working group doesn’t meet regularly since all EPI related issues are handled within the SACB Health & Nutrition committee and during the Health Sector Coordination General Meeting.

- Composition: The SACB comprises 117 partner agencies, which includes main donors, UN Agencies and International NGOs. Other international and regional bodies maintain ad hoc membership, mainly as observers. In addition there is a network of local Somali organisations, which regularly participate.

The Health& Nutrition committee is composed of UN agencies (UNDOS, UNICEF, UNDP/UNCU, UNFPA and WHO) donors (EC Somalia Unit, USAID and one rotational donor), representatives from the different regions in Somalia and NGOs members on rotational basis.

- The EPI technical working group is composed of the following partners:

* WHO/ UNICEF; ACF; MSF (H); GHC; CISP; AAH; IMC; SRCS/ IFRC; COSV

- Major functions and responsibilities of the ICC:

The Health & Nutrition committee has the following functions and responsibilities:

- Develop a work plan for a twelve month period

- To promote, guide and lead the work on the adoption of a common health policy for international intervention in the Health Sector for Somalia;

- To promote and facilitate the activities of technical working groups charged with the development and adoption of standards and guidelines for the Health Sector with a public health perspective;

- To encourage and monitor the application of the standards and guidelines among NGOs, agencies, donors and Somali authorities;

- To promote coordinated and integrated area based (zonal/ regional/ district) health planning by Health Coordination group members with full Somali participation;

- To promote through the SACB Sectoral Steering Committee coordinated and integrated inter-sectoral strategies;

- To encourage and monitor the application of the standards and guidelines among NGOs, agencies, donors and Somali authorities

- To promote adherence to and active participation in the coordination process of all implementing organizations, donors and Somali authorities;

- To facilitate Interagency cooperation and promote understanding among agencies;

- To draw to the attention of the relevant agencies and donors the need for support in the priority activities related to the Health Sector; and

- To be responsible for screening and preparing statements on major health issues for forwarding to the SACB Executive Committee for press release.

TOR of EPI technical working group (ETWG):

- ETWG will provide advice and technical leadership to the providers of health services to assist them with the establishment and operation of immunization activities.

- ETWG will monitor the implementation of immunization in Somalia.

- ETWG will ensure realization of all objectives set fort in the multi year plan:

- Objective 1: To increase DTP3 coverage to 60%

- Objective 2: Ensure injection safety and waste disposal

- Objective 3: Develop social mobilisation activities

- Objective 4: Contribute to the achievement of polio eradication

- Objective 5: Reduce by 25% the incidence of NNT

- Objective 6: Reduce measles morbidity and mortality by 40% and 20% respectively

- Objective 7: Improve Vit A coverage

- Objective 8: Improve the surveillance system

- Objective 9: Strengthen the logistics and cold chain system

- Objective 10: Improve vaccine management and quality

- Objective 11: Strengthen the EPI managerial process

- Objective 12: Supporting cost minimization of  EPI activities.

- Objective 13: Increase human resource capacity

- Objective 14: To strengthen co-ordination and partnership between  all partners

- ETWG will ensure coordination of all EPI related activities in Somalia

- EPI routine

- Acceleration activities

- ETWG will set and constantly review the administration of the present programme of childhood immunisation and make recommendations on measures having regard to both cost and quality issues and on options to improve the present uptake of immunisations. The latter respecting the WHO and UNICEF rules and regulations.

- ETWG will recommend standards and guidelines and describe best practices for immunization in Somalia.

- ETWG will provide a forum for exchange of ideas and information about immunization.

- ETWG will provide regular updates to stakeholders regarding technical developments and progress in routine EPI activities in Somalia.

Twelve month work-plan:

| Month | Specific issue to be discussed |
| --- | --- |
| April | - Injection safety and waste disposal |
| May | - Training needs at various levels |
| June | - Review social mobilization activities |
| July | - Overview acceleration activities carried out so far |
| August | - Strategies for reduction of drop out |
| September | - Measles control mechanisms guidelines |
| October | - Health management information system |
| November | - Update Polio eradication initiative |
| December | EPI financial sustainability |
| January | - Surveillance system |
| February | - Review human resource capacity |
| March | - Review Vit. A supplementation efforts through regular EPI activities |
| April | - logistics and cold chain system |
| May | - vaccine management and quality |
| June | - EPI managerial process |

- Three major strategies to enhance ICC’s role and functions in the next 12 months:

- The Ad hoc EPI working group to be a permanent one, with clear terms of reference and composition

- Create Zonal EPI working group in all Somalia

- To organize EPI specific health coordination general meeting twice per year, in order to properly discuss all recommendations from the EPI working group

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal:

- Drop out rates national and by regions

- Wastage rates at all level.

- Proportion of agencies and or regions implementing social mobilisation activities.

Attached are the supporting documents :

| - Terms of reference of the SACB included in the ‘Somalia Aid coordination Body Handbook’’ - EPI Working group TOR if approved | Document number III Document number IV |
| --- | --- |
| - SACB Health Committee (EPI Working group) work plan of next 12 months. (one page bullet points meetings planned for etc issues to discuss) | Document number…V |
| - Minutes of the three most recent health &Nutrition committee meetings and minutes of the last three Somali Health Sector Coordination General meetings | Document number…VI |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| MICS | UNICEF | 1999 |
| Health Nutrition evaluation (including EPI component) | UNICEF | 2001 |
| Operational assessment of PEA in Somalia | WHO | 2000 |
| Somalia EPI review | WHO/ UNICEF | 2002 |

- The four major strengths identified in the assessments:

- The existence of a functional and effective inter-agencies body (SACB Health & Nutrition Committee)

- The introduction of AD syringes and safety boxes for the whole country

- The cold chain capacity and vaccine procurement

- Strong commitment from the international agencies involved in EPI activities

- The three major problems identified in the assessments:

- Data accuracy: no exact figures on population exist which makes planning and evaluation difficult. Coverage data can only be used when it was a result of a coverage survey. Morbidity data related to vaccine preventable diseases are fragmented.

- Access to immunization services:  According to MICS conducted in 1999, coverage rates are very low, reflecting a restricted access to immunization services. Security concern, lack of basic infrastructure and human resources and population movements are the main constraints to better access.

- Human resources availability: National human resources are hard to come by. Most qualified health staff took refuge abroad or left to the safer northern areas.

- The three major recommendations in the assessments:

- To increase coverage through a sustainable EPI system delivery

- To strengthen social mobilization activities

- To reinforce the capacity building activities at the regional and district levels

- Attached are complete copies (with an executive summary) of:

| - The most recent assessment reports on the status of immunization services: MICS Somalia 2000 Health Nutrition evaluation 2001 Polio assessment 2000 Somalia EPI review, 2002’ | Document number…VII Document number…VIII Document number… IX Document number….X . |
| --- | --- |
| - A list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. (list of implemented in progress implemented one page) | Document number…XI |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Cold chain assessment | 2002 |
| Injection safety and waste disposal | 2002 |
| Social Mobilisation: Assessment and action-plan | 2002 |

# Multi-Year Immunisation Plan.

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

In the absence of a central government in Somalia, the international donor community and stakeholders in the health sector in Somalia, decided to develop a common vision and policy framework to guide and coordinate external assistance to the health sector in Somalia. To achieve that objective, the SACB Health Sector Committee organized in May 1999 a workshop in Nakuru (Kenya) and developed the SACB strategic framework in support of health sector in Somalia. The document is a strategic multi year plan for the entire health sector. Most of international agencies and NGOs participated to that workshop.

Following that workshop, the EPI Working group, developed with WHO STCs a Multi-Year Immunization plan taking in consideration the major strategic components of the health sector plan and results of many other workshops organized in different regions of Somalia. Those workshops were intended to assess the current EPI situation and develop general orientations for planning. Local EPI staff and different international partners attended them. All those workshops were organized in 2001 and supported by the SACB Health Sector Committee.

| - Attached is a complete copy of the ‘ strategic framework in support of the health sector in Somalia, 1999’ - Attached is a complete copy of the ‘Somalia EPI Multi year plan of action, 2002-2004’ | Document number…XII Document number…XIII |
| --- | --- |

| - Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Cold chain assessment | 2002 | UNICEF |
| Injection safety assessment | 2002 | WHO |
| Development of Social mobilisation work-plan | 2002 | UNICEF |

| Table 3 : Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG, OPV zero | Birth | X |  |  |
| DPT-1 , OPV-1 | 6 weeks | X |  |  |
| DPT-2 , OPV-2 | 10 weeks | X |  |  |
| DPT-3, OPV-3 | 14 weeks | X |  |  |
| Measles | 9 months | X |  |  |
| Vitamin A | 6-59 months | X |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

The different strategies for improving immunization coverage are summarized below. (See details in the multi-year plan)

- Reduce the number of defaulters

- Reduce missed opportunities to vaccination

- Increase the number of health facilities providing immunization activities

- Implement acceleration activities to boost the current coverage

- Reorganize the implementation of health facilities

- Develop strategies to reach the un-reached

- Involve the private sector in EPI activities

| Table 4 : Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of |  | Baseline | Targets |  |  |  |  |  |  |  |
|  |  | 2000 | 2001 | 2002 |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| Population size |  | 6360000 | 6550800 | 6747324 |  | 6949744 | 7158236 | 7372983 | 7594173 | 7821998 |
| Crude Birth Rate |  | 47.51 | 47.51 | 47.51 |  | 47.51 | 47.51 | 47.51 | 47.51 | 47.51 |
| Births |  | 302164 | 311229 | 320565 |  | 330182 | 340088 | 350290 | 360799 | 371623 |
| IMR |  | 132 | 130 | 120 |  | 115 | 110 | 105 | 100 | 95 |
| Infants’ deaths |  | 39886 | 40460 | 38468 |  | 37971 | 37410 | 36780 | 36080 | 35304 |
| Surviving infants |  | 262278 | 270769 | 282098 |  | 292211 | 302678 | 313510 | 324719 | 336319 |
| Infants vaccinated with BCG* |  | 211515 | 224085 | 240424 |  | 257542 | 275471 | 294244 | 313895 | 334461 |
| Infants vaccinated with OPV3** |  | 97043 | 108308 | 126944 |  | 160716 | 196741 | 235132 | 259775 | 285871 |
| Infants vaccinated with DTP3** |  | 85503 | 89354 | 110018 |  | 143184 | 178580 | 200646 | 224056 | 252239 |
| Infants vaccinated with**: (use one row for any new vaccine) |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated with Measles** |  | 40915 | 51446 | 70524 |  | 102274 | 136205 | 172430 | 211067 | 252239 |
| Pregnant women vaccinated with TT+ |  | 66476 | 77807 | 96170 |  | 132073 | 170044 | 210174 | 234519 | 260136 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | NA |  |  |  |  |  |  |  |  |
|  | Infants (> 6 months) | NA |  |  |  |  |  |  |  |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Remarks:

- Population size was calculated assuming Crude growth rate as three percent per year.

- The crude birth rate was assumed to remain stable during the next years. (Family planning is not very well accepted in Somalia)

- Considering the expected improved child health status, infant mortality rate will gradually decrease during the next years.

- Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate. :

- Conduct a study to properly assess wastage rates at all levels

- Include wastage rate indicators in all periodic reports

- Reinforce supervision

- Conduct training on open vial policy

- Revise supervision checklist to include vaccine wastage issue

- Introduce the open vial policy according to WHO guidelines

- Review and improve cold chain equipment, vaccine ordering and distribution (see relevant sections)

- Reinforcing cold chain maintenance (see relevant sections)

- Raising demand for immunization (see relevant sections)

- Support implementing partners in obtaining accurate village population figures

| Table 5 : Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual | Targets |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate |  | 30 | 30 | 25 | 23 | 20 | 15 | 15 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 42.7 | 42.7 | 40 | 35 | 30 | 30 | 25 | 25 |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

Plans:  In order to achieve higher polio coverage the following strategies have been adapted. (Refer to multi year plan for more details)

- Increase the level of community participation in immunization activities.

- Conduct house-to-house NID’s, and mop-up activities based on surveillance reports.

- Strengthen AFP surveillance at all levels.

- Establish National and zonal expert Committee.

Constraints:

- Lack of Ministry of Health

- Deteriorating security and lack of access.

- Low EPI coverage.

- NID fatigue.

- Inaccessibility of most of nomadic population.

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

The different strategies for improving injection safety and waste disposal are the followings:

- Develop a comprehensive policy for injection safety and waste disposal

- Assess the current situation

- Ensure a continuous supply of AD syringes and safety boxes

- Ensure a proper use of injection safety material

- Improve the safety of waste disposal

- Monitor the program progress

- Increase awareness among clients and the general population

- Implement a system for detecting and investigating adverse events following

#### immunization

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…XIV |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support).

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG…… ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 240,424 | 257,542 | 275,471 | 294,244 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 |
| C | Number of …… doses | A x B | 240,424 | 257,542 | 275,471 | 294,244 |
| D | AD syringes (+10% wastage) | C x 1.11 | 266,871 | 285,872 | 305,773 | 326,611 |
| E | AD syringes buffer stock | D x 0.25 | 66718 | 71468 | 76443 | 81653 |
| F | Total AD syringes | D + E | 333588 | 357340 | 382216 | 408264 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 26687 | 28587 | 30577 | 32661 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 3,999 | 4,284 | 4,582 | 4,894 |

| Table 6.2: Estimated supplies for safety of vaccination with …DTP… ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 110,018 | 143,184 | 178,580 | 200,646 |
| B | Number of doses per child (for TT woman) | # | 3 | 3 | 3 | 3 |
| C | Number of …… doses | A x B | 330,054 | 429,552 | 535,740 | 601,938 |
| D | AD syringes (+10% wastage) | C x 1.11 | 366,360 | 476,803 | 594,671 | 668,151 |
| E | AD syringes buffer stock | D x 0.25 | 91,590 | 119,201 | 148,668 | 167,038 |
| F | Total AD syringes | D + E | 457,950 | 596,003 | 743,339 | 835,189 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 36,636 | 47,680 | 59,467 | 66,815 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 5,490 | 7,145 | 8,911 | 10,012 |

| Table 6.3: Estimated supplies for safety of vaccination with TT…… ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 96,170 | 132,073 | 170,044 | 210,174 |
| B | Number of doses per child (for TT woman) | # | 2 | 2 | 2 | 2 |
| C | Number of …… doses | A x B | 192,340 | 264,146 | 340,088 | 420,348 |
| D | AD syringes (+10% wastage) | C x 1.11 | 213,497 | 293,202 | 377,498 | 466,586 |
| E | AD syringes buffer stock | D x 0.25 | 53,374 | 73,301 | 94,374 | 116,647 |
| F | Total AD syringes | D + E | 266,872 | 366,503 | 471,872 | 583,233 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 10,675 | 14,660 | 18,875 | 23,329 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 3,081 | 4,231 | 5,447 | 6,733 |

| Table 6.4: Estimated supplies for safety of vaccination with …Measles… ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 70,524 | 102,274 | 136,205 | 172,430 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 |
| C | Number of …… doses | A x B | 70,524 | 102,274 | 136,205 | 172,430 |
| D | AD syringes (+10% wastage) | C x 1.11 | 78,282 | 113,524 | 151,188 | 191,397 |
| E | AD syringes buffer stock | D x 0.25 | 19,570 | 28,381 | 37,797 | 47,849 |
| F | Total AD syringes | D + E | 97,852 | 141,905 | 188,984 | 239,247 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 7,828 | 11,352 | 15,119 | 19,140 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 1,173 | 1,701 | 2,266 | 2,868 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| UNICEF | AD syringes, safety boxes and waste disposal boxes | 1993 |
| GAVI/Vaccine Fund | Training | 2002 |
| GAVI/Vaccine Fund | Supervision | 2002 |
| GAVI/Vaccine Fund | Assessment | 2002 |
| GAVI/Vaccine Fund | Incinerator | 2003 |

(Use as many rows as necessary

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan by the time of the mid-term review. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief :

One of the main objective of the health sector multi year plan prepared by the SACB  is  to increase sustainability of health care system by supporting development and implementation of adequate health financing strategies. The major strategies are the followings: (see details in the multi-year plan of action)

1.To support the development of effective coordination mechanisms between donors, local authorities and implementing agencies, in order to optimise financial resource utilization.

- Assure a wide distribution of the five-year plan to all potential donors

- Organize a workshop with all partners to discuss EPI cost benefit ratio’s and financial sustainability

- Assess the current cost of EPI and the estimated direct and indirect contribution of each partner

2.To support development of appropriate local resource mobilization efforts

- Identify resources available in the area/region.

- Support the development of local plans and guidelines, based on recommendations of the 1997 SACB Health Care Financing study

- Support and follow up of implementation of Health Financing strategies in pilot projects to support development of prioritization of financial resources allocation to cater for the basic health care needs (MPS)

| - Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number .XV |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

.

- Support the development of Health Management System (financial guidelines & tools, drug logistics and management…)

- Training in management of staff and community/boards

- Improve the EPI efficiency by identifying the compressible costs and inefficiencies

- Reinforce district implementation in order to optimize the use of resources between health units

- To support the development of appropriate mechanisms to broaden the resource base.

- Support community participation

- Involve the private sector

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, WHO/ UNICEF on behalf the SACB Somalia, considering that its DTP3 coverage for 2000 was 33 %  corresponding to 89353 number of children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, WHO/ UNICEF  hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES

- Support for New and Under-used vaccines                                                    NO

- Support for Injection Safety                                                          YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 110,018 (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

Since there is no recognized government is Somalia, WHO/ UNICEF will take full responsibility to manage the in country transfer of funds. Taking into account the existing auditing systems available.

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

See above.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 8

V	The equivalent amount of funds

| Table 8: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES requested from GAVI and the Vaccine Fund (fill in the total sums of rows “F”, “H” and “I” of tables 6.1,6.2, 6.3, 6.4. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | 333,588 | 357,340 | 382,216 | 408,264 |
|  |  | for other vaccines | 822,674 | 1,104,411 | 1,404,196 | 1,657,668 |
| H | Total of reconstitution syringes |  | 34,515 | 39,940 | 45,696 | 51,801 |
| I | Total of safety boxes |  | 13,218 | 16,669 | 20,336 | 23,507 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

# Additional comments and recommendations from the ICC

- Funding to be received by both agencies due to the nature of the actual ongoing programs. WHO and UNICEF agree based on the budget drafted together that 30% of the funds will be channeled through WHO and the remaining through UNICEF. The Polio eradication initiative has been and excellent example of an intense collaboration between UNICEF and WHO. For this initiative both agencies receive funds from similar donors for similar activities.

- We need to have a guarantee in place ensuring that the GAVI funds will be implemented according to the above agreement, regardless of the political or social changes that may take place within Somalia. This for the coming five years and any extension from GAVI based on the same conditions, bearing in mind the high turnover in international aid agency staff (who will be responsible for the GAVI implementation).

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expend-iture in 2001 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item …vaccines |  |  |  | 856,000 |  |  |  |  |  |
| 1.2 | - Line item AD syringes and safety boxes |  |  |  | 240,000 |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item …cold chain |  |  |  | 324,000 |  |  |  |  |  |
| 2.2 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item …SM |  |  |  | 115,000 |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure in 2001 |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. Donors include ECHO/ CDC/ Italian gov/ CIDA/ UNICEF Regular Resources/ UNF/ Rotary INT/ Polio plus 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2002 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item …vaccines |  |  |  |  |  |  |  | 150,000 |  |
| 1.2 | - Line item …3ad syringes |  |  |  |  |  |  |  | 140,000 |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item …cold chain and logistics |  |  |  |  |  |  |  | 80,000 |  |
| 2.2 | - Line item …3Operational costs |  |  |  |  |  |  |  | 1,600,000 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item …social mobilisation |  |  |  |  |  |  |  | 200,000 |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number: I, II, XII……. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number: V. |
| - Terms of reference of the ICC | Document number III |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number VI |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number: X, VIII, VII |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number: XI |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number: XIII, |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…… Document number: XIV |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2000 and resource needs (Annex 1) | Document number: XIII Bis |

ANNEX  3

UNICEF

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .. , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below : |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution : (Account Holder) |  | UNICEF Somalia |  |  |  |  |  |  |  |  |
| #### Address : |  |  |  |  |  |  |  |  |  |  |
|  |  | P O Box 01000 44145, NAIROBI KENYA |  |  |  |  |  |  |  |  |
| #### City – Country : |  | Nairobi, KENYA |  |  |  |  |  |  |  |  |
| Telephone No. : |  | 254 2 623950 / 254 2 623963 |  | Fax No. : |  |  |  | 254 2 623965 / 254 2 520640 |  |  |
| #### Amount in USD : |  | ( To be filled in by GAVI Secretariat ) |  |  | Currency of the bank account : |  |  |  |  | USD |
| For credit to : Bank account’s title |  | UNICEF |  |  |  |  |  |  |  |  |
| Bank account No. : |  | 014 – 1 – 076224 |  |  |  |  |  |  |  |  |
| At : Bank’s name |  | Chase Manhattan Bank |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( X ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official : |  |  |  |  |  |  |  |  |  |  |
| #### Name : |  |  |  |  |  |  |  |  | Seal : |  |
| #### Title : |  |  |  |  |  |  |  |  |  |  |
| #### Signature : |  |  |  |  |  |  |  |  |  |  |
| Date : |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 ( To be completed by the Bank ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name : |  | Chase Manhattan Bank |  |  |  |
| Branch Name : |  | New York |  |  |  |
| Address : |  | 270 Park Avenue, 43rd Floor, |  |  |  |
|  |  | New York, N.Y. 10017 |  |  |  |
| City – Country : |  | New York, USA |  |  |  |
| Swift code : |  | ### Swift CHASUS33 |  |  |  |
| Sort code : |  |  |  |  |  |
| ABA No. : |  | ### CHIPS ABA 0002 UID 259366 |  |  |  |
| Telephone No : |  |  |  |  |  |
| Fax No : |  |  |  |  |  |
| I certify that the account No. 014 – 1 - 076224 is held by (Institution name) UNICEF Somalia at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least … (number of signatories) of the following authorized signatories : |  |  | Name of bank’s authorizing official : |  |  |
| 1 Name : Title : |  |  | Signature : |  |  |
|  |  |  | Date: |  |  |
| 2 Name : Title : |  |  | Seal: |  |  |
| 3 Name : Title : |  |  |  |  |  |
| 4 Name : Title : |  |  |  |  |  |

WHO

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below : |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution : (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address : |  |  |  |  |  |  |  |  |  |  |
| #### City – Country : |  |  |  |  |  |  |  |  |  |  |
| Telephone No. : |  |  |  | Fax No. : |  |  |  |  |  |  |
| #### Amount in USD : |  | ( To be filled in by GAVI Secretariat ) |  |  | Currency of the bank account : |  |  |  |  |  |
| For credit to : Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No. : |  |  |  |  |  |  |  |  |  |  |
| At : Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited ? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official : |  |  |  |  |  |  |  |  |  |  |
| #### Name : |  |  |  |  |  |  |  |  | Seal : |  |
| #### Title : |  |  |  |  |  |  |  |  |  |  |
| #### Signature : |  |  |  |  |  |  |  |  |  |  |
| Date : |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 ( To be completed by the Bank ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name : |  |  |  |  |  |
| Branch Name : |  |  |  |  |  |
| Address : |  |  |  |  |  |
| City – Country : |  |  |  |  |  |
| Swift code : |  |  |  |  |  |
| Sort code : |  |  |  |  |  |
| ABA No. : |  |  |  |  |  |
| Telephone No : |  |  |  |  |  |
| Fax No : |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories : |  |  | Name of bank’s authorizing official : |  |  |
| 1 Name : Title : |  |  | Signature : |  |  |
|  |  |  | Date: |  |  |
| 2 Name : Title : |  |  | Seal: |  |  |
| 3 Name : Title : |  |  |  |  |  |
| 4 Name : Title : |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative : |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

(To be completed by WHO representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of WHO Representative : |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

Please submit hard copy documents with an identical electronic copy whenever possible