Revision  4

August  2002

The Government of

Viet Nam

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

The Government of Viet Nam requests GAVI/Vaccine Fund support to move to exclusive use of auto-disable syringes (ADs) for all EPI injections.  Viet Nam acquired the technology to produce ADs in 2001 from Star Syringe Company.  The Government requires support to assist with the purchase of the supplies, given the increased cost of ADs.

Over the three years of support the Government will procure an increasing proportion of injection supplies (50% in year 1; 60% in year 2; and 70% in year 3).  The Government  will procure all supplies by 2006.

The Government of Viet Nam request that the three years of support be given as cash equivalent.  The funds will be used to procure locally manufactured ADs and other injection supplies to make up the shortfall associated with the increased cost of ADs.  The funds will also enable support of additional injection safety activities.

Based on the calculation of injection safety supply needs, it is estimated that the cash equivalent is$1,457,464, $1,259,735, and $1,292,707 for 2003, 2004, and 2005 respectively.  The volume of supplies required are :(for routine EPI, excluding for the GAVI-supplied hepatitis B vaccine):

| ITEM | 2003 | 2004 | 2005 |
| --- | --- | --- | --- |
| Total AD syringe (BCG) | 2,236,341 | 1,822,618 | 1,849,958 |
| Total AD syringes (all other) | 17,080,797 | 14,825,460 | 15,237,512 |
| Total Reconst. Syringes | 465,159 | 472,136 | 479,218 |
| Total Safety boxes | 219,584 | 190,034 | 194,990 |

The Government of Viet Nam also requests that ADs to be given as part of support for hepatitis B vaccine, be given as cash equivalent to enable a single type of AD syringe to be used for all EPI injections.

The ICC discussed this application at its June meeting and reviewed and endorsed this application at its September meeting.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of Viet Nam commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with previous application. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| WHO |  |  |
| PATH |  |  |
| JICA |  |  |
| UNICEF |  |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: ……………………………	Title/Address: ……………………………….

Tel.No.: ………………………….   		            ………………………………..

Fax No.:………………………….. 		            ………………………………..

E-mail:……………………………                         ……………………………….

Alternative address:

Name: ……………………………	Title/Address: ……………………………….

Tel.No.: ………………………….   		            ………………………………..

Fax No.:………………………….. 		            ………………………………..

E-mail:……………………………                         ……………………………….

Immunization-related fact sheet

See 2001 application

# Profile of the Inter Agency Co-ordinating Committee (ICC)

See 2001 application

# Immunization services assessment(s)

See 2001 application

# Multi-Year Immunization Plan

See 2001 application

| Table 4 : Annual targets |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Infant Population | 1,671,535 | 1,696,608 | 1,722,057 | 1,747,888 | 1,774,106 | 1,800,718 |
| BCG Coverage (%) | 95 | 95 | 95 | 95 | 95 | 95 |
| Infants vaccinated | 1,587,958 | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 | 1,710,682 |
| OPV Coverage Targets (%) | 95 | 95 | 95 | 95 | 95 | 95 |
| Infants vaccinated | 1,587,958 | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 | 1,710,682 |
| Hep B3: Local (%) | 80 | 80 | 85 | 90 | 95 | 95 |
| Target children | 312,686 | 317,376 | 322,137 | 326,969 | 331,874 | 336,852 |
| Infants vaccinated | 250,149 | 253,901 | 273,816 | 294,272 | 315,280 | 320,009 |
| Hep B3: GAVI (%) | 80 | 80 | 85 | 90 | 95 | 95 |
| Target children | 924,253 | 1,379,232 | 1,399,920 | 1,420,919 | 1,442,232 | 1,463,866 |
| Infants vaccinated | 739,402 | 1,103,385 | 1,189,932 | 1,278,827 | 1,370,120 | 1,390,673 |
| DTP3 Coverage Targets (%) | 95 | 95 | 95 | 95 | 95 | 95 |
| Infants vaccinated | 1,587,958 | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 | 1,710,682 |
| Measles Coverage (%) | 95 | 95 | 95 | 95 | 95 | 95 |
| Infants vaccinated | 1,587,958 | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 | 1,710,682 |
| TT for PW Coverage (%) | 85 | 85 | 90 | 90 | 90 | 90 |
| PW vaccinated | 1,420,449 | 1,441,756 | 1,549,464 | 1,572,706 | 1,596,296 | 1,620,646 |

# Injection safety

7.1	Summary of the injection safety strategy for immunization

Following transfer of technology for manufacture of auto-disable syringes (ADs) in 2002, the strategy is for exclusive use of ADs by 2003 – contingent on GAVI support.

The GAVI support will be used to build additional incinerators, provide training and monitoring to improve practice, and for advocacy/

The Government is committed to procuring ADs for all EPI injections from 2006.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 2. |
| --- | --- |

  - Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

| Table 7.1 : Estimated supplies for BCG Vaccine |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2003 | 2004 | 2005 | 2006 |
| Target no. of children | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 |
| Doses per child | 1 | 1 | 1 | 1 |
| Total no. of doses | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 |
| AD syringes (+10%) | 1,789,073 | 1,815,909 | 1,843,148 | 1,870,795 |
| AD syringes buffer (25%) | 447,268 | 6,709 | 6,810 | 6,912 |
| Total AD syringes | 2,236,341 | 1,822,618 | 1,849,958 | 1,877,707 |
| Doses per vial | 20 | 20 | 20 | 20 |
| Wastage factor | 2.0 | 2.0 | 2.0 | 2.0 |
| Reconst.syringe | 178,907 | 181,591 | 184,315 | 187,080 |
| Safety boxes (+10%) | 26,809 | 22,247 | 22,580 | 22,919 |
| Table 7.2 : Estimated supplies for Measles Vaccine |  |  |  |  |
|  | 2003 | 2004 | 2005 | 2006 |
| Target no. of children | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 |
| Doses per child | 1 | 1 | 1 | 1 |
| Total no. of doses | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 |
| AD syringes (+10%) | 1,789,073 | 1,815,909 | 1,843,148 | 1,870,795 |
| AD syringes buffer (25%) | 447,268 | 6,709 | 6,810 | 6,912 |
| Total AD syringes | 2,236,341 | 1,822,618 | 1,849,958 | 1,877,707 |
| Doses per vial | 10 | 10 | 10 | 10 |
| Wastage factor | 1.6 | 1.6 | 1.6 | 1.6 |
| Reconst.syringe | 286,252 | 290,545 | 294,904 | 299,327 |
| Safety boxes (+10%) | 28,001 | 23,456 | 23,808 | 24,165 |
| Table 7.3 : Estimated supplies for DPT Vaccine |  |  |  |  |
|  | 2003 | 2004 | 2005 | 2006 |
| Target no. of children | 1,611,778 | 1,635,954 | 1,660,494 | 1,685,401 |
| Doses per child | 3 | 3 | 3 | 3 |
| Total no. of doses | 4,835,333 | 4,907,863 | 4,981,481 | 5,056,203 |
| AD syringes (+10%) | 5,367,219 | 5,447,728 | 5,529,444 | 5,612,385 |
| AD syringes buffer (25%) | 1,341,805 | 20,127 | 20,429 | 20,735 |
| Total AD syringes | 6,709,024 | 5,467,855 | 5,549,873 | 5,633,121 |
| Safety boxes (+10%) | 74,470 | 60,693 | 61,604 | 62,528 |
| Table 7.4 : Estimated supplies for TT Vaccine |  |  |  |  |
|  | 2003 | 2004 | 2005 | 2006 |
| Target no. of women | 1,442,117 | 1,549,851 | 1,573,099 | 1,596,696 |
| Doses per woman | 2 | 2 | 2 | 2 |
| Total no. of doses | 2,884,234 | 3,099,703 | 3,146,198 | 3,193,391 |
| AD syringes (+10%) | 3,201,499 | 3,440,670 | 3,492,280 | 3,544,664 |
| AD syringes buffer (25%) | 800,375 | 59,793 | 12,903 | 13,096 |
| Total AD syringes | 4,001,874 | 3,500,463 | 3,505,183 | 3,557,760 |
| No. Of safety box (+10%) | 44,421 | 38,855 | 38,908 | 39,491 |
| Table 7.5: Estimated supplies for local HepB Vaccine |  |  |  |  |
|  | 2003 | 2004 | 2005 | 2006 |
| Target no. of children | 301,507 | 306,030 | 310,621 | 315,280 |
| Doses per child | 3 | 3 | 3 | 3 |
| Total no. of doses | 904,522 | 918,090 | 931,862 | 945,840 |
| AD syringes (+10%) | 1,004,020 | 1,019,080 | 1,034,366 | 1,049,882 |
| AD syringes buffer (25%) | 251,005 | 3,765 | 3,822 | 3,879 |
| Total AD syringes | 1,255,025 | 1,022,845 | 1,038,188 | 1,053,761 |
| Safety boxes (+10%) | 13,931 | 11,354 | 11,524 | 11,697 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| Government and GAVI/Vaccine Fund | AD syringes and waste disposal boxes (50% of 2003 requirements, decreasing annually to 0% in 2006) | End 2002 |
| GAVI/Vaccine Fund | Incinerators (budget 1 series) | Q1 2003 |
| GAVI/Vaccine Fund | Training (budget 2 series) | Q1 2003 |
| GAVI/Vaccine Fund | Monitoring and Evaluation (budget 3& 4 series) | Q1 2003 |
| GAVI/Vaccine Fund | IEC materials (budget 5 seies) | Q1 2003 |

Budget from strategic plan:

| 1.1 Sicim incinerators for remote districts | $80,000 | $120,000 | $200,000 |
| --- | --- | --- | --- |
| 1.2 Incinerators for commune health centers | $10,000 | $30,000 | $60,000 |
| 2.1 Province level training for district staff | $30,000 | $40,000 | $32,000 |
| 2.2 District level training for commune staff | $300,000 | $300,000 | $300,000 |
| 2.3 Training of incinerator operators | $1,000 | $1,500 | $2,500 |
| 2.3 Printing of Materials for training courses | $30,000 | $40,000 | $45,000 |
| 3.1 Monitoring from national and four regions to lower levels | $50,000 | $50,000 | $50,000 |
| 3.2 Follow-up visit after training | $10,000 | $10,000 | $10,000 |
| 3.3 Establish computer network for surveillance | $5,000 | $50,000 | $5,000 |
| 4.1 Annual Review meeting | $15,000 | $15,000 | $15,000 |
| 4.2 Quarterly review meeting | $12,000 | $12,000 | $12,000 |
| 4.3 Additional evaluation for areas of concern |  | $30,000 | $30,000 |
| 4.4 Injection safety assessment |  |  | $15,000 |
| 5. Communication/advocacy materials | $10,000 | $20,000 | $30,000 |
| Sub-total for activities | $553,000 | $718,500 | $806,500 |
| Supplies (UNICEF price) | $1,457,464 | $1,259,735 | $1,292,707 |
| TOTAL needs | $2,010,464 | $1,978,235 | $2,099,207 |

# New and under-used vaccines

N/R

# Strategic directions to mobilise additional resources for immunization

See 2001 application

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Viet Nam hereby applies for the following types of support from GAVI and the Vaccine Fund.

- Support for Injection Safety                                                          YES

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

X	The equivalent amount of funds

| Table 7 : Summary of total injection safety supplies (NOT incl for GAVI HepB vaccine) |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM | 2003 | 2004 | 2005 | 2006 |
| Total AD syringe (BCG) | 2,236,341 | 1,822,618 | 1,849,958 | 1,877,707 |
| Total AD syringes (all other) | 17,080,797 | 14,825,460 | 15,237,512 | 15,707,094 |
| Total Reconst. Syringes | 465,159 | 472,136 | 479,218 | 486,407 |
| Total Safety boxes | 219,584 | 190,034 | 194,990 | 200,590 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC