Revision  4

August  2002

The Government of

THE REPUBLIC OF SENEGAL

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of  Senegal commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Pr Omar FAYE	Title/Address: Head of the Immunization and Epidemiological

Surveillance Division

Tel. No.: (221) 8247434 		            ………………………………..

Fax No.: (221) 8243533 		            ………………………………..

E-mail: ofaye1@telecomplus.sn                         ……………………………….

Alternative address:

Name: Dr Papa Coumba FAYE 	Title/Address: EPI Co-ordinator

Tel. No.: (221) 8247434     		            ………………………………..

Fax No.: (221) 8243533 		            ………………………………..

E-mail: papfaye@hotmail.com ; papfaye@yahoo.fr

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 10038006 | GNP per capita | 509 $SD |
| Surviving Infants* | 429380 | Infant mortality rate | 70.1/ 1000 |
| Percentage of GDP allocated to Health | 5.1% | Percentage of Government expenditure for Health Care | 6.99% |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | ND | 59% | 87.6% | 12-23 months |  |  | Tuberculosis | ND | ND |
| DTP | DTP1 |  | ND | 58% | 70.8% |  |  |  | Diphtheria | ND | 0 |
|  | DTP3 |  | ND | 44.7% | 52.1% |  |  |  | Pertussis | ND | 0 |
| OPV3 |  |  | ND | 44.7% | 49.8% |  |  |  | Polio | ND | 0 |
| Measles |  |  | ND | 42.2% | 52.6% |  |  |  | Measles | ND | 24789 |
| TT2+ (Pregnant women) |  |  | ND | 43.1% | 81,9% |  |  |  | NN Tetanus | ND | 45 |
| Hib3 |  |  | ND | ND | ND |  |  |  | Hib | ND | ND |
| Yellow Fever |  |  | ND | 32.9% | 43.1% |  |  |  | Yellow fever | ND | 18 |
| HepB3 |  |  | ND | ND | ND |  |  |  | hepB seroprevalence (if available) | ND | ND |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | ND | ND | ND |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) | ND | ND | ND |  |  |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: The figures obtained and transmitted to WHO/UNICEF in the joint report had been obtained after active reconstitution of the coverage data for the year 2001organised in all the districts of the country. This data would have been closer to reality if the information from the para-bublic and private vaccination centres had been more exhaustive.

- Summary of health system development status relevant to immunization:

Senegal has a pyramidal health system. At the peripheral level you have the health station which is the first-resort health structure. It is responsible for carrying out all primary health care activities (including immunisation). There are 803 (public and private) health stations. They are run by station nursing sisters (government-approved nurses or government-approved midwives).

The health district is the operational unit in charge of managing, supervising and assessing  health programmes, including immunisation in a zone under its responsibility, which on average comprises 20 health stations and one to two health centres. The health centre serves as reference for the health station. The district is headed by a senior physician who is sometimes assisted  by a deputy physician. There are 50 health districts.

There are 10 medical regions, and they constitute the intermediate level; they are run by regional senior physicians who are assisted by deputy physicians. With the creation of a new administrative region (Matam), the number of regions will increase to 11 and the number of districts to 52.

At the central level we have the central departments and services of the Ministry of Health. The Prevention Department is in charge of EPI management and administration,  through the Immunization and Epidemiological Surveillance Division. At the regional level there is an Inter-Agency Coordinating Committee (NCC/EPI) in charge of following up and carrying out immunisation activities. It comprises the central departments of the ministry and of the various partners.

At the regional level, the Regional Immunization and Epidemiological Surveillance Offices are responsible for monitoring immunisation activities. Immunisation programmes are implemented at the level of district health stations and health centres (within the framework of fixed, advanced and mobile strategy).

The main antigens used within the scope of the EPI are BCG, OPV, DTP, MEAS, and AAV. Since 1998, there are, within the framework of the fight against hepatitis B,  immunisation activities against hepatitis, with a centralised management system other than the EPI but using the public structures (health stations) at the peripheral level. The integration of these activities into the EPI is planned for 2003.

The development of the Senegalese health system has been done in several phases.  The State’s new health policy for the next years is reflected in the national health development plan (PNDS 1998/2007) which has as one of its priorities the reduction of infant mortality. The Expanded Programme of Immunisation helps attain this objective. An integrated health development programme has been created from this plan, with a support and monitoring unit (PDIS 1998/2002).

| - Attached are the relevant section(s) of strategies for health system development | Document number………….. |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC: National Coordinating Committee for  EPI Activities ( NCC/EPI)

- Date of constitution of the current ICC: 11 October 2000

- Organisational structure (e.g., sub-committee, stand-alone): NCC/EPI technical committee comprising the technicians of the Ministry of Health and partner agencies

- Frequency of meetings: every six months for NCC/EPI and every month for the technical committee

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister for Health and Prevention | Pr. Awa Marie COLL SECK |
| Secretary | EPI Coordinator | Dr Papa Coumba FAYE |
| Members | - Prevention Director - Head of DISE - DSSP representative - DEPS representative - Representative of national NGOs - Representative of international NGOs - European Union representative - WHO representative - UNICEF representative - JICA representative - BASICS representative - ROTARY representative | Dr. Col. Cheikh FALL Pr. Omar FAYE |

- Major functions and responsibilities of the ICC:

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

Drafting and following up a working schedule

Advocacy

Involving other sectors, persons and resources

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

Rate of abandonment

Wastage rate

Availability of vaccines

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number……. |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number……. |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| External review of the EPI | WHO, UNICEF, USAID/BASICS, CATR, CDC, Ministry of Health | December 1999 to January 2000 |
| Senegalese Health Indicator Study | Ministry of Health | September 1999 |
| Study of the end-of-decade childhood objectives (MICS-II-2000) | UNICEF, Government of Senegal | December 2000 |
| Demographic and Health Research (EDS III) | Government of Senegal | 1997 |
| Results of the external review of the EPI in the regions of St-Louis and Matam | Government of Senegal and CVP/PATH | July 2002 |

- The three major strengths identified in the assessments:

Increasing State involvement in EPI funding

Well-established planning process

Existence of operational community participation organs

- The three major problems identified in the assessments:

Bad vaccine management

Weak activity coordination and follow-up/assessment mechanisms

Obsolescence, inadequacy and/or inexistence of logistics and cold chain

- The three major recommendations in the assessments:

Working out a strategic plan for the EPI

Improving vaccine management

Rehabilitating/renewing the logistics and cold chain

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number….. |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number….. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number……. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Social mobilisation | First quarter of the year 2002 | WHO |
| Logistics | First half of the year 2002 | Unicef |
| Study of immunisation funding | Last quarter of the year 2002 | CATR/ARIVA; World Bank |
| Operational research on strategies to improve vaccine coverage | The year 2003 | CATR/ARIVA |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | X |  |  |
| DTP | 6 weeks, 10 weeks, and 14 weeks | X |  |  |
| OPV | At birth, 6 weeks, 10 weeks, and 14 weeks | X |  |  |
| MEAS | 9 months | X |  |  |
| AAV | 9 months | X |  |  |
| Hep B | At birth, 6 weeks, 10 weeks, and 14 weeks | X |  |  |
| Vitamin A | 6 months to 59 months |  |  | National supplementation campaigns organised on a 6-monthly basis |

- Summary of major action points and timeframe for improving immunization coverage:

Attainment of the target before the end of 2002 (census and active monitoring to reduce the rate of abandonment)

Revitalising and making the advanced and mobile strategies permanent

Organising massive and acceleration campaigns in low-coverage areas in 2002

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births |  | 461 748 | 474 215 | 487 019 |  | 500 168 | 513 672 | 527 542 | 541 786 | 556418 |
| Infants’ deaths |  | 32 368 | 33 242 | 34 140 |  | 35 062 | 36 008 | 36 981 | 37 979 | 39005 |
| Surviving infants |  | 429 380 | 440 973 | 452 879 |  | 465106 | 477664 | 490561 | 503807 | 517413 |
| Pregnant women |  | 461 748 | 474 215 | 487 019 |  | 500 168 | 513 672 | 527 542 | 541 786 | 556418 |
| Infants vaccinated with BCG* |  | 404491 | 415 412 | 438 317 |  | 450 152 | 462 305 | 474 788 | 487 607 | 500776 |
| Infants vaccinated with OPV3** |  | 212 972 | 242 535 | 271 727 |  | 325 574 | 381 891 | 416 977 | 428 236 | 439801 |
| Infants vaccinated with DTP3** |  | 223 707 | 242 535 | 271 727 |  | 325 574 | 381 891 | 416 977 | 428 236 | 439801 |
| Infants vaccinated with yellow fever**: (use one row for any new vaccine) |  | 185 063 | 264 584 | 294 371 |  | 348 831 | 381 891 | 416 977 | 428 236 | 439801 |
| Infants vaccinated with Measles** |  | 225 854 | 264 584 | 294 371 |  | 348 831 | 381 891 | 416 977 | 428 236 | 439801 |
| Infants vaccinated with Hep. B** |  | ND | ND | 271 727 |  | 325 574 | 381 891 | 416 977 | 428 236 | 439801 |
| Infants vaccinated with Hib. B |  | ND | ND | 271 727 |  | 325 574 | 381 891 | 416 977 | 428 236 | 439801 |
| Pregnant women vaccinated with TT+ |  | 378 172 | 403 083 | 413 966 |  | 425 143 | 436 621 | 448 411 | 460 518 | 472955 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | ND | ND |  |  |  |  |  |  |  |
|  | Infants (> 6 months) | ND | ND |  |  |  |  |  |  |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

Adopting and applying the open-vial policy  in 2002

Improving the immunisation session plan in 2002

Providing training on and supervising vaccine stock management in 2002

Monitoring the rate of wastage in the  immunisation units

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate | 30% | 20% | 10% | 10% | 10% | 10% | 10% | 10% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 25% | 20% | 15% | 10% | 10% | 10% | 10% | 10% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

Action plan:

Increasing the routine vaccine coverage to at least  80% in all the districts

Organising good-quality National Immunisation Days

Improving acute  flaccid paralysis surveillance activities

Organising search campaigns in high-risk areas

Constraints:

Funding of activities

Social mobilisation

# Injection safety

This section does not apply because Senegal has already been granted supported in this field.

7.1	Summary of the injection safety strategy for immunization (for all countries):

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number……. |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with …… ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 |  |  |  |  |
| B | Number of doses per child (or per woman in case of TT) | # |  |  |  |  |
| C | Number of …… doses | A x B |  |  |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E |  |  |  |  |
| G | Number of doses per vial | # |  |  |  |  |
| H | Vaccine wastage factor | Either 2 or 1.6 |  |  |  |  |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |  |  |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
|  | AD syringes and waste disposal boxes |  |
| GAVI/Vaccine Fund |  |  |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Senegal introduced the AAV in the routine EPI right from the beginning of the programme.

Anti-hepatitis B vaccines are given in the immunisation units but not free of charge. Since its inception, it has been run within the framework of the Fight Against Hepatitis B which is independent of the Prevention Department and the EPI.

The introduction and integration of the hepatitis B and Hib vaccine into the EPI is planned for 2003, and this in just one phase which would  include the entire country.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

With the start of immunisation against hepatitis B in Senegal, problems of  vaccine storage capacity have been encountered in some areas, especially in connection with the obsolescence of the cold chain (existence of single-dose vials).

Reduced wastage  rates have been noted, although staff  training has not been systematised.

See annexes (PNLH)

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

Training the staff on the use, preservation and management of new vaccines

Continuing with the cold chain rehabilitation plan

Implementing the Action Plan for the safety of injections

Monitoring the application of the open-vial policy

Supervising and assessing the activities

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses  of  liquid DTP Hib vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 271727 | 325574 | 381981 | 416977 | 428236 | 517413 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% | 100% | 80% | 60% | 40% | 20% |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 815181 | 976722 | 916755 | 750559 | 513883 | 310448 |
| E | Estimated wastage factor | see list in table  | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 904851 | 1084161 | 1017597 | 833120 | 570410 | 344597 |
| G | Vaccines buffer stock | F x 0.25 | 226213 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 1131064 | 1084161 | 1017597 | 833120 | 570410 | 344597 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 1155947 | 1084161 | 1017597 | 833120 | 570410 | 3445971 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 | % | 0 | 0 | 0 | 0 | 0 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 12831 | 120341 | 11295 | 9248 | 6332 | 3825 |

Table 7.1: Estimated number of doses  of  10d hepatitis B vaccine vials  (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 271727 | 325574 | 381981 | 416977 | 428236 | 517413 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% | 100% | 80% | 60% | 40% | 20% |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 815181 | 976722 | 916755 | 750559 | 513883 | 310448 |
| E | Estimated wastage factor | see list in table  | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 904851 | 1084161 | 1017597 | 833120 | 570410 | 344597 |
| G | Vaccines buffer stock | F x 0.25 | 226213 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 1131064 | 1084161 | 1017597 | 833120 | 570410 | 344597 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 1155947 | 1084161 | 1017597 | 833120 | 570410 | 3445971 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 | 0 | 0 | 0 | 0 | 0 | 0 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 12831 | 120341 | 11295 | 9248 | 6332 | 3825 |

Table 7.1: Estimated number of doses  of  1d hepatitis B vaccine vials  (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 438317 | 450152 | 462305 | 474788 | 487607 | 500776 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% | 100% | 80% | 60% | 40% | 20% |
| C | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses | A x B/100 x C | 438317 | 450152 | 462305 | 474788 | 487607 | 500776 |
| E | Estimated wastage factor | see list in table  | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 460233 | 472660 | 388336 | 299116 | 204795 | 105163 |
| G | Vaccines buffer stock | F x 0.25 | 115058 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 575291 | 472660 | 388336 | 299116 | 204795 | 105163 |
| I | Number of doses per vial | # | 1 | 1 | 1 | 1 | 1 | 1 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 614246 | 499669 | 410527 | 316209 | 216498 | 111172 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 | 0 | 0 | 0 | 0 | 0 | 0 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 6818 | 5546 | 4557 | 3510 | 2403 | 1234 |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number…… |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

Providing and increasing vaccine procurement funds regularly in the State budget

Taking advocacy initiatives within communities and local NGOs

Reinforcing health committees’ participation in the funding of immunization activities

Reinforcing the VII

Using the HIPC funds to support immunization

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number .…. |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

Reducing the rate of wastage (training and supervising the technical staff)

Building three interregional warehouses

Reinforcing the operational planning process (better organisation of immunization sessions)

Introducing a logistics maintenance and renewal plan (increasing  equipment service life, and reducing the cost of repairs)

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Senegal,

considering that its DTP3 coverage for 2001 was 44.7%  corresponding to 191,932  children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  already accepted

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          already accepted

10.1	SUPPORT FOR IMMUNIZATION SERVICES – (not applicable)

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Liquid DTP Hib | 10 | Jan. 2003 | 1131064 | 1084161 |
| Hepatis B | 10 | Jan. 2003 | 1131064 | 1084161 |
| Hepatis B | 1 | Jan. 2003 | 575291 | 472660 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                  X                                By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY (not applicable)

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |
| I | Total of reconstitution syringes |  |  |  |  |  |
| J | Total of safety boxes |  |  |  |  |  |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… | 642 857 |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific | 550 000 |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2001 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEXE 1

Statement of financing and of unmet needs for immunization (USD ,000)

| Budget for 2002 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | BASICS/ USAID | PATH/CVP |  |  |
| 1. | Vaccines, AD syringes… | 1 142 857 |  |  |  |  |  |  | 1 142 857 |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain |  |  |  |  | 150 000 |  | 60 000 | 210 000 |  |
| 2.2 | - Rolling stock |  |  |  | 60 000 | 100 000 |  | 100 000 | 260 000 |  |
|  | - Incinerators |  |  |  |  |  |  | 10 000 | 10 000 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Preparation of materials | 71 429 |  |  |  |  |  |  | 71 429 |  |
|  | - Follow-up, evaluation, planning |  |  |  | 70 000 | 100 000 | 94 457 | 20 000 | 284 457 |  |
|  | - Training |  |  |  | 40 000 | 100 000 | 14 207 | 200 000 | 354 207 |  |
| 3.2 | - Social mobilisation |  |  |  | 35 000 |  | 27 022 | 40 000 | 102 022 |  |
| Total commitment |  | 1 269 296 |  |  | 205 000 | 450 000 | 135 683 | 430 000 | 2 434 972 |  |

| Budget for 2003 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | BASICS/ USAID | PATH/CVP |  |  |
| 1. | Vaccines, AD syringes… | 1 150 000 |  |  |  |  |  |  | 1 150 000 |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain |  |  |  |  | 150 000 |  | 5 000 | 155 000 |  |
| 2.2 | - Rolling stock |  |  |  | 20 000 | 100 000 |  | 50 000 | 170 000 |  |
|  | - Incinerators |  |  |  |  |  |  | 6 500 | 6 500 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Preparation of materials | 72 000 |  |  |  |  |  |  | 72 000 |  |
|  | - Follow-up, evaluation, planning |  |  |  | 70 000 | 100 000 | 94 457 | 40 000 | 304 457 |  |
|  | - Training |  |  |  | 25 000 | 100 000 | 14 207 | 100 000 | 239 207 |  |
| 3.2 | - Social mobilisation |  |  |  | 30 000 |  | 27 022 | 40 000 | 97 022 |  |
| Total commitment |  | 1 222 000 |  |  | 145 000 | 450 000 | 135 686 | 241 500 | 2 194 186 |  |

| Budget for 2004 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | BASICS/ USAID | PATH/CVP |  |  |
| 1. | Vaccines, AD syringes… | 1 250 000 |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain |  |  |  |  | 150 000 |  |  | 150 000 |  |
| 2.2 | - Rolling stock |  |  |  |  | 100 000 |  | 36 000 | 136 000 |  |
|  | - Incinerators |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Preparation of materials | 80 000 |  |  |  |  |  |  | 80 000 |  |
|  | - Follow-up, evaluation, planning |  |  |  |  | 100 000 | 94 457 | 50 000 | 244 457 |  |
|  | - Training |  |  |  |  | 100 000 | 14 207 | 27 000 | 141 207 |  |
| 3.2 | - Social mobilisation |  |  |  |  |  | 27 022 | 26 000 | 53 022 |  |
| Total commitment |  | 1 330 000 |  |  |  | 450 000 | 135 686 | 139 000 | 2 054 686 |  |

| Budget for 2005 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | BASICS/ USAID | PATH/CVP |  |  |
| 1. | Vaccines, AD syringes… | 1 300 000 |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain |  |  |  |  | 150 000 |  |  | 150 000 |  |
| 2.2 | - Rolling stock |  |  |  |  | 100 000 |  |  | 100 000 |  |
|  | - Incinerators |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Preparation of materials | 85 000 |  |  |  |  |  |  | 85 000 |  |
|  | - Follow-up, evaluation, planning |  |  |  |  | 100 000 |  |  | 100 000 |  |
|  | - Training |  |  |  |  | 100 000 |  |  | 100 000 |  |
| 3.2 | - Social mobilisation |  |  |  |  |  |  |  |  |  |
| Total commitment |  | 1 385 000 |  |  |  | 450 000 |  |  | 1 835 000 |  |

| Budget for 2006 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | BASICS/ USAID | PATH/CVP |  |  |
| 1. | Vaccines, AD syringes… | 1 350 000 |  |  |  |  |  |  | 1 350 000 |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain |  |  |  |  | 150 000 |  |  | 150 000 |  |
| 2.2 | - Rolling stock |  |  |  |  | 100 000 |  |  | 100 000 |  |
|  | - Incinerators |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Preparation of materials | 85 000 |  |  |  |  |  |  | 85 000 |  |
|  | - Follow-up, evaluation, planning |  |  |  |  | 100 000 |  |  | 100 000 |  |
|  | - Training |  |  |  |  | 100 000 |  |  | 100 000 |  |
| 3.2 | - Social mobilisation |  |  |  |  |  |  |  |  |  |
| Total commitment |  | 1 435 000 |  |  |  | 450 000 |  |  | 1 885 000 |  |

| Budget for 2007 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | BASICS/ USAID | PATH/CVP |  |  |
| 1. | Vaccines, AD syringes… | 1 400 000 |  |  |  |  |  |  | 90 000 |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain |  |  |  |  |  |  |  |  |  |
| 2.2 | - Rolling stock |  |  |  |  |  |  |  |  |  |
|  | - Incinerators |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Preparation of materials | 90 000 |  |  |  |  |  |  | 90 000 |  |
|  | - Follow-up, evaluation, planning |  |  |  |  |  |  |  |  |  |
|  | - Training |  |  |  |  |  |  |  |  |  |
| 3.2 | - Social mobilisation |  |  |  |  |  |  |  |  |  |
| Total commitment |  | 1490 000 |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number……. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Terms of reference of the ICC | Document number…… |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number…… |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number…… |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number…… |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…… |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…… Document number…… |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number…… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of Senegal , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  | Ministry of Health and Prevention |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
|  |  | Second floor, Administrative building |  |  |  |  |  |  |  |  |
| #### City – Country: |  | Dakar, Senegal |  |  |  |  |  |  |  |  |
| Telephone No.: |  | 824 73 43 |  | Fax No.: |  |  |  | 824 35 32 |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  | Francs CFA |
| For credit to: Bank account’s title |  | Ministry of Health and Prevention / GAVI |  |  |  |  |  |  |  |  |
| Bank account No.: |  | 2200710659 / 7 RIB 97 |  |  |  |  |  |  |  |  |
| At: Bank’s name |  | Société Générale de Banques au Sénégal |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( X ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  | Director of Prevention / Director of General Administration and Equipment |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible