Revision 3

August 2001

The Government of

THE REPUBLIC OF BURUNDI

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

Burundi is a country situated in central East Africa. It is bordered by Rwanda to the north, the United Republic of Tanzania to the east and the Democratic Republic of Congo to the west.

It has an area of 27 834 km2. Its total population in the year 2000 was 6 664 835, including the following:

Children of 0-11 months old		: 261 669 or 3.92% of the total population

Children of 0 to 59 months old		: 1 207 618 or 18.11% of the total population

Pregnant women			: 303 889 or 4.56% of the total population

Women of child bearing age		: 1 551 661 or 23.28% of the total population

Average population growth rate per

annum for the period 2000 to 2006	: 2.9%

Gross birth rate (GBR)		: 45.6 / 1000 in the year 2000

Gross mortality rate (GMR)		: 15.8 / 1000 for the year 2000

Maternal mortality rate (MMR)	: 800 / 100 000 live births

Infant mortality rate (IMR) 		: 129 / 1000 in the year 2000

There was major progress with routine EPI during the period 1990 to 1992, with a coverage of 85% being achieved. In 1994, however, the rate fell sharply to less than 50% following the socio-economic problems resulting from the 1993 crisis. Since then, there has been a gradual improvement in coverage, particularly with regard to DTP3 (MICS), for which a rate of 57.2% was achieved in 2000.

In view of the fact that this coverage is over 50% and given that the epidemiological situation of infections due to hepatitis B and Haemophilus influenzae type b in the sub-region, Burundi wishes to benefit from the support of the Alliance in order to bring in the pentavalent vaccine (DTP-HB-Hib) on 1 January 2003.

In view of the low vaccination coverage for DTP3 (less than 60%), Burundi wishes to benefit from the support of the immunization service subsidiary account.

The objectives set for the programme in its strategic plan for the years 2002 –2006 are as follows:

- to increase the vaccination coverage for all the antigens to 90% by 2006

- to strengthen the process for the control of measles, the elimination of neo-natal tetanus and the eradication of polio

- to ensure the sustainability of the financing of the Expanded Programme on Immunization.

Coverage objectives for 2001 – 2006

| Antigens | Target population | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | 0-11 months | 75% | 80% | 85% | 90% | 90% | 90% |
| DTP 3 | 0-11 months | 60% | 65% |  |  |  |  |
| DTP-HiB-HB3 |  |  |  | 74% | 80% | 85% | 90% |
| OPV 3 | 0-11 months | 60% | 65% | 74% | 80% | 85% | 90% |
| Measles | 9-11 months | 65% | 70% | 75% | 80% | 85% | 90% |
| Tetanus 2+ | Pregnant women | 60% | 65% | 70% | 75% | 80% | 80% |

Estimate of Burundi's total needs in terms of routine EPI vaccines

| Antigens | Target population | 2002* | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| BCG | 0-11 months | 643 500 | 562 900 | 613 300 | 631 100 | 649 400 |
| DTP 3 | 0-11 months | 726 859 | 0 | 0 | 0 | 0 |
| DTP-HiB-HB3 |  | 0 | 840 300 | 747 800 | 817 600 | 890 800 |
| OPV | 0-11 months | 908 574 | 851 500 | 947 200 | 1 035 600 | 128 300 |
| Measles | 9-11 months | 326 200 | 287 700 | 315 700 | 345 200 | 376 100 |
| Tetanus | Pregnant women | 695 400 | 616 500 | 679 700 | 746 000 | 767 700 |

N.B. The wastage coefficient used for DTP-HIB-HB is 1.05, for BCG = 2 and for others = 1.33

*25% of the reserve stocks has been added during the first calendar year, with the exception of DTP

Presentation of vaccines

The vaccines to be used in the country have or will have the following presentation:

BCG			20 doses

DTP			10 doses

DTP-HB-Hib		  2 doses

OPV			10 doses

Measles		10 doses

Tetanus		10 doses

Nature of the ICC participation in developing this proposal

The committee which prepared this proposal included technical representatives from all the member agencies of the ICC.

This proposal has been developed by a committee appointed by the Ministry of Health, with the support of representatives from all the agencies concerned with the country's vaccination problem and of one external WHO consultant.

The group assessed the appropriateness of the data from the EPI review conducted in June 2001 and from the national strategic plan for the EPI by Burundian staff and the extent to which the recommendations of the said review have been implemented.

The socio-economic data, which used to be a real problem in the past, have been gathered by the ministries and agencies concerned. For example, with regard to the data relating to the reduction of the public debt and to the future financing of the health sector in general and the EPI in particular, the Minister of Finance in person provided the related contributions of the government and of the World Bank.

The Ministry of Health – the initiator of this application to GAVI - relied on the ICC throughout the process of drawing up the proposal, through its regular meetings with the committee.

Thus, during its meeting of 31 August 2001, the ICC examined the application and proposed amendments which related, among other things, to the drawing up of a summary of the EPI financing plan for the coming years with the costed commitments of all the partners. These amendments were introduced and submitted to the members of the ICC prior to signature of the application.

The signature of Burundi's application took place on the occasion of an extraordinary meeting of the ICC held on Wednesday 5 September 2001 in the conference room of the Ministry of Public Health.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of ………………………………………………………………….. commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : ……………………………	Title/Address : ……………………………….

Tel.No. : ………………………….   		            ………………………………..

Fax No. :………………………….. 		            ………………………………..

E-mail :……………………………                         ……………………………….

Alternative address :

Name : ……………………………	Title/Address : ……………………………….

Tel.No. : ………………………….   		            ………………………………..

Fax No. :………………………….. 		            ………………………………..

E-mail :……………………………                         ……………………………….

- Immunization-related fact sheet

| Table 1 : Basic facts (For the year 2000 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 6 664 835 | GNP per capita | USD 108.4 |
| Surviving Infants* | 264 647 | Infant mortality rate | 129 / 1000 |
| Percentage of GDP allocated to Health | 4.24% | Percentage of Government expenditure for Health Care | 2.85% |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage ( in percentage ) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 1999 | 2000 | 1999 | Age group | 2000 | Age group |  | 1999 | 2000 |
| BCG |  |  | 72.3 | 73 |  |  | 61 | 12-23 | Tuberculosis | 5 421 | 2 917 |
| DTP | DTP1 |  | 68.7 | 77 |  |  |  |  | Diphtheria | 0 | 0 |
|  | DTP3 |  | 63.7 | 68 |  |  | 57.2 | 12-23 | Pertussis | 354 | 92 |
| OPV3 |  |  | 59.6 | 69 |  |  | 48.5 |  | Polio | 0 | 0 |
| Measles |  |  | 47.2 | 61 |  |  | 51.7 | 12-23 | Measles | 2981 | 21758 |
| TT2+ (Pregnant women) |  |  |  |  |  |  | 49.8 | 12-23 | NN Tetanus | 40 | 16 |
| Hib3 |  |  |  | - |  |  |  |  | Hib | ND | ND |
| Yellow Fever |  |  |  | - |  |  |  |  | Yellow fever | 0 | 0 |
| HepB3 |  |  |  | - |  |  |  |  | hepB seroprevalence (if available) | ND | ND |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | ND | ND |  |  | 15.9 |  |  |  |  |
|  |  | Infants ( > 6 months) | 92 | 96 | ND | ND | 57.2 | 12-23 |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: # MICS:57.2% DTP 3 in 2000 # We consider that the findings of the MICS 2000 survey is the best official estimate for the following reasons: - well-prepared survey plan - sampling with a margin of error of 5% - sampling established at two levels: 1st sampling with probability proportional to the size and 2nd carried out through systematic sampling in 4 500 households

- Summary of health system development status relevant to immunization:

Burundi's  Ministry of Public Health is engaged in a thorough-going decentralisation of the health system with emphasis on primary health care. The main aims of the reforms in progress are as follows:

- to strengthen the institutional capacities

- to improve access to quality health care through the autonomous management of the health care structures from the national reference hospitals through to the primary health care centres

- to improve the financing of health care through the introduction of health insurance for the structured and non-structured private sectors

- to ensure the availability of essential medicines through:

- the establishment of a central unit for the purchase of essential medicines and medical supplies

- the establishment of community pharmacies

- to develop human resources

- to intensify curative care and health promotion activities, as well as preventive care, with special emphasis on vaccination activities:

- to restore the vaccination coverage rates achieved prior to the 1993 crisis

- to make use of community health care personnel to mobilize the population in favour of routine vaccination activities and during catch-up vaccination campaigns

- to ensure a healthy environment

- to assume responsibility for the health needs of the most vulnerable groups

| - Attached are the relevant section(s) of strategies for health system development | Document number 1 |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC: Inter-Agency Coordinating Committee (ICC)

- Date of constitution of the current ICC : 26 August 1999

- Organisational structure (e.g., sub-committee, stand-alone) …………………………………………….

- Frequency of meetings : once every three months

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister for Public Health | Dr Stanislas NTAHOBARI |
| Secretary | EPI Director | Dr Cassien NDIKUMANA |
| Members | Director General for Europe, North America and the International Organizations | Mr Balthazar HABONIMANA |
|  | United Nations Development Programme (UNDP) | Mr George CHARPENTIER |
|  | European Commission Delegation | Mr COSTE |
|  | UNICEF | Mr Sêne MALICK |
|  | WHO | Dr Manlan KASSI |
|  | World Bank | Mr Mathurin GBETIBOUO |
|  | UNFPA | Mr Michel TAILHADES |
|  | USAID | Mr David AASEN |
|  | Rotary | Mr Albert MUGANGA |
|  | NGO | A representative |

- Major functions and responsibilities of the ICC:

- Mobilization and coordination of external and local resources

- Coordinating the allocation and judicious use of resources

- Appealing for and obtaining sustained interest for the activities of the EPI (routine EPI, NIDs, Measles, NNT, etc.)

- Strengthening the partnership between the Agencies and the government

- Examining and approving EPI plans of action at national level

- Providing guidelines and directives for achieving objectives

- Deciding and assessing the internal audits and evaluations relating to the EPI

- Rendering account to the Government and the various funding bodies and partners concerned

- Three major strategies to enhance ICC’s role and functions in the next 12 months :

- Extending the activities of the ICC to the other health care priority programmes

- Focusing on the monitoring of EPI financing (mobilization of resources, follow-up and monitoring of implementation)

- Advocacy and development of communication and involvement of the various parties in implementation, including the private sector.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Reduction of the general drop-out rate from 20% to 10% (DTP1 – Measles)

- Reduction of the specific drop-out rate from 10.4% to 5% (DTP1- DTP3)

- Reduction of vaccine wastage rate from 50% to 25% for the BCG and measles and from 31% to 5% for DTP and OPV

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number 2 |
| --- | --- |
| - ICC workplan of next 12 months | Document number 3 |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number 4, 5, 6 |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| External review of the EPI – Burundi 2001 | Government of Burundi / WHO / UNICEF / EU | 18 June to 31 June 2001 |
| Plan for rehabilitation of the EPI logistics support system | Government of Burundi / WHO / UNICEF / EU | March 2001 |

- The three major strengths identified in the assessments :

1. The increase - despite the security problems - in the geographical cover and the availability of the vaccination services, thanks to the political commitment of the authorities, the motivation of the personnel and the support of partners (366 health centres in operation, AFP surveillance having achieved certification level).

2. The government contribution to the operation of the EPI and the purchase of vaccines within the framework of the Vaccine Independence Initiative (VII), as well as its commitment to strengthening the operation of the EPI over the coming years.

3. The high degree of political awareness and acceptance of the EPI at the level of the administrative authorities and the population at large..

- The three major problems identified in the assessments :

- The heavy dependence of the EPI on external financing

- The lack of provision of a post of head of EPI at intermediate level (provinces and health sectors)

- The shortage of qualified personnel, arising from the cessation of training and supervision activities.

- The three major recommendations in the assessments :

- Overhaul the materials for staff training, increase the number of personnel and train the provincial teams, the sector heads and health workers in the management of the EPI and the new strategies and innovations.

- Increase and secure Government support for the purchase of vaccines (from the current 6% to 100% by 2006) and exert greater efforts to win over and raise the awareness of the national authorities with regard to the need for long-term financing of the EPI.

- Construct and/or renovate infrastructures, including the EPI headquarters, the EPI Central Store and the Health Centres which have been destroyed or have become dilapidated.

- Attached are  complete copies (with an executive summary) of :

| - the most recent assessment reports on the status of immunization services | Document number 7, 8, 9 |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 10 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Financing and costs of the EIP | June 2001 |
| Injection safety | June 2001 |
| APIR (adverse post-immunization reactions) | June 2001 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 11, 12 |
| --- | --- |

| - Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools, etc) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Computerisation of management at EPI level | January 2002 | WHO |
| Injection safety survey | June 2002 | UNICEF |

| Table 3 : Schedule of immunizations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | xx |  |  |
| OPV | At birth, 6, 10 and 14 weeks | xx |  |  |
| DTP | 6, 10 and 14 weeks | xx |  | For the year 2002 |
| DTP+HepB+Hib | 6, 10 and 14 weeks | xx |  | From 2003 |
| Measles | 9 months | xx |  |  |
| Vitamin A | Infants>6 months | xx |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

- Improving services from the point of view of availability (rehabilitation of the health centres, cold chain equipment and logistics) and quality (reduction of drop-out rate, remote areas, etc.)

- Training of personnel in EPI management, including the innovations and new vaccines

- Resumption of supervision and monitoring activities

| Table 4 : Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of |  | Baseline | Targets |  |  |  |  |  |  |  |
|  |  | 2000 | 2001 | 2002 |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births |  | 303 889 | 312 702 | 321 770 |  | 331 101 | 340 703 | 350 584 | 360 751 | 371 213 |
| Infants’ deaths |  | 39 242 | 40 339 | 41 508 |  | 42 712 | 43 951 | 45 225 | 46 537 | 47 886 |
| Surviving infants |  | 261 669 | 272 363 | 280 262 |  | 288 389 | 296 753 | 305 358 | 314 214 | 323 326 |
| Infants vaccinated with BCG* |  | 221 839 | 234 526 | 257 416 |  | 281 436 | 306 633 | 315 525 | 324 676 | 334 091 |
| Infants vaccinated with OPV3** |  | 149 675 | 163 418 | 182 170 |  | 213 408 | 237 402 | 259 555 | 282 793 | 282 793 |
| Infants vaccinated with DTP3** |  | 149 675 | 163418 | 182 170 |  |  |  |  |  |  |
| Infants vaccinated with**: (use one row for any new vaccine) |  |  |  |  |  | 213 408 | 237 402 | 259 555 | 282 793 | 282 793 |
| Infants vaccinated with Measles** |  | 159 618 | 177 036 | 196 183 |  | 216 292 | 237 402 | 259 555 | 282 793 | 282 793 |
| Pregnant women vaccinated with TT+ |  | 151 337 | 187 621 | 209 151 |  | 231 771 | 255 528 | 280 467 | 288 601 | 296 970 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | 0 |  |  |  |  |  |  |  |  |
|  | Infants (> 6 months) | 140 939 | 177 036 | 196 183 |  | 216 292 | 237 402 | 259 555 | 282 793 | 282 793 |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

- Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate. :

- The reorganisation of the provision of services:

- organize immunization sessions in fixed and advanced strategies in the various health-related fields

- implement the opened vial policy

- increase demand for the service through involvement of community workers to raise awareness and mobilize the population and introduce the new vaccines, factors which will motivate both health care employees and the population

- Staff training

- Establishment of a system for monitoring and assessing vaccine wastage rates

- Organisation and prudent distribution of vaccines

- Maintenance of the cold chain

- Particular attention will be paid to the safety of vaccines which could be of use to the non-targeted population.

| Table 5 : Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual | Targets |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate | 27% | 27% | 25% | 5% | 5% | 5% | 5% | 5% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 11.6 | 11 | 10 | 7 | 5 | 5 | 3 | 3 |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

- Plan of action for the eradication of  polio

The plan of action for the eradication of polio is based on the following strategies:

- Increase OPV coverage and maintain it at over 80%

- Organize NIDs and mop-up campaigns (5th round, the first of which took place in August)

- Maintain proper monitoring of AFP

- Obstacles

- People moving in from the Democratic Republic of Congo, a country where the circulation of the wild polio virus has not yet been halted

- Low routine immunization coverage (Polio 3 = 48.5% in 2000 according to MICS)

- Areas where access is difficult (lack of security) and hygiene is poor (camps for refugees or displaced persons)

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

The main aim of the national five-year plan (2001-2005) for injection safety is to ensure that all injection-related practices are risk-free by 2005.

This aim will be achieved through the following strategies:

- changing over gradually to the use of AD syringes in routine immunization

- establishing reliable estimates of equipment requirements and minimum stock levels and supplies, as well as an efficient distribution system for injection and incineration equipment

- ensuring the destruction of used injection equipment through the gradual introduction of safety boxes and appropriate incinerators

- introducing monitoring and supervision processes to ensure the availability of adequate supplies at all levels and to correct health worker practices

- improving the training of health workers in injection safety and the procedures for the destruction of equipment

- insisting on a solid budget for injection safety, including the safe handling of used equipment.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 13 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support).

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with TT vaccine |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | TT target for women | Match with targets in table 4 | 209 151 | 231 771 | 255 528 | 280 601 | 288 601 |
| B | Number of TT doses for women | # | 2 | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 418 400 | 463 600 | 511 100 | 561 000 | 577 300 |
| D | AD syringes (+10% wastage) | C x 1.11 | 464 424 | 514 596 | 567 321 | 622 710 | 640 803 |
| E | AD syringes buffer stock | D x 0.25 | 116 106 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 580 530 | 514 596 | 567 321 | 622 710 | 640 803 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 46 442 | 51 460 | 56 732 | 62 271 | 64 080 |
| I | Number of safety boxes (+10% extra needs) | ( F + H ) x 1.11 / 100 | 6 960 | 6 290 | 6 930 | 7 610 | 7 830 |

| Table 6.2: Estimated supplies for safety of vaccination with BCG |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for BCG | Match with targets in table 4 | 257 416 | 281 436 | 306 633 | 315 525 | 324 676 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 257 500 | 281 500 | 306 700 | 315 600 | 324 700 |
| D | AD syringes (+10% wastage) | C x 1.11 | 285 825 | 312 465 | 340 437 | 350 316 | 360 417 |
| E | AD syringes buffer stock | D x 0.25 | 71 456 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 357 300 | 312 500 | 340 500 | 350 400 | 360 500 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 14 291 | 15 623 | 17 022 | 17 516 | 18 021 |
| I | Number of safety boxes (+10% extra needs) | ( F + H ) x 1.11 / 100 | 4 130 | 3 650 | 3 970 | 4 090 | 4 210 |

| Table 6.3: Estimated supplies for safety of vaccination with DTP |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for DTP | Match with targets in table 4 | 182 170 | 0 | 0 | 0 | 0 |
| B | Number of doses per child | # | 3 | 0 | 0 | 0 | 0 |
| C | Number of DTP doses | A x B | 546 600 | 0 | 0 | 0 | 0 |
| D | AD syringes (+10% wastage) | C x 1.11 | 606 726 | 0 | 0 | 0 | 0 |
| E | AD syringes buffer stock | D x 0.25 | 151 682 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 758 408 | 0 | 0 | 0 | 0 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G |  |  |  |  |  |
| I | Number of safety boxes (+10% extra needs) | ( F + H ) x 1.11 / 100 | 8 420 | 0 | 0 | 0 | 0 |

| Table 6.4: Estimated supplies for safety of vaccination with measles vaccine |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for measles vaccine | Match with targets in table 4 | 196 183 | 216 292 | 237 402 | 259 555 | 282 793 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of doses of measles vaccine | A x B | 196 200 | 216 300 | 237 500 | 259 600 | 282 800 |
| D | AD syringes (+10% wastage) | C x 1.11 | 217 782 | 240 093 | 263 625 | 288 156 | 313 908 |
| E | AD syringes buffer stock | D x 0.25 | 54 446 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 272 228 | 240 093 | 263 625 | 268 156 | 313 908 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 21 778 | 24 009 | 26 363 | 28 816 | 31 391 |
| I | Number of safety boxes (+10% extra needs) | ( F + H ) x 1.11 / 100 | 3 270 | 2 940 | 3 220 | 3 520 | 3 840 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| UNICEF | AD syringes and waste disposal boxes | 2002 |
| WHO | Training and supervision | 2002 |
| GAVI/Vaccine Fund | AD syringes and safety boxes | 2003 |
| GAVI/Injection Safety Fund | Overhaul of health centre incinerators | 2003 |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

The introduction of new vaccines should make it possible, on the one hand, to give new impetus to the programme as a whole with a view to protecting the greatest number of the target populations against vaccine preventable diseases and, on the other, to establish a durable immunization system after the long years of social tension which the country has experienced.

As indicated earlier, with access to basic health services in the order of 80%, it is hoped that as peace gradually extends to the whole of the national territory, it will be possible to attain a vaccination coverage of at least 90% in order to meet the objectives laid down for the country, which include in particular:

- the eradication of polio

- the elimination of neo-natal and maternal tetanus

- the control/elimination of measles

- the reduction of mortality and morbidity due to hepatitis B and Haemophilus influenza type b meningitis.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | Survey on the seroprevalence of the HBS antigen in Burundi | 1985 (Dr Kabondo, Dr Kochelef and Dr Maupas Kamenge University Hospital Centre (KUHC) and MPH) | cf. summary at foot of table* |
| Hib | Routine laboratory test at the KUHC, Bujumbura | 1995-2000 | cf. summary** |

*	 Hepatitis B: Very little work has recently been undertaken on the seroprevalence of  Hep B in Burundi. In 1985, a mixed team consisting of researchers from France, Belgium and Burundi carried out a national seroprevalence survey in certain regions, particularly in the high plateaux in the centre of Burundi. The number of HBs Ag carriers was estimated at 70%.

In 1990, a study was carried out by Professor P. Aubry and Dr L. Gahimbare with the aim of making an assessment of the association Hep B-Hep C chronic hepatopathy in Burundi.

The part played by Hep B in primitive cancers of the liver and chronic hepatopathies was estimated at 60%, ahead of Hep C.

In 1999, a study was carried out among 5 000 blood donors on the seroprevalence of Hep B, Hep C and HIV by Pr. J.B. Ndihokubwayo and Dr D. Ntirandekura. The Hep BS agent was found in 4.8% of this group which voluntarily gives blood to the National Blood Transfusion Centre.

It may be concluded, therefore, that despite the lack of recent studies, particularly among children and the population at large, Hep B poses a major public health problem in Burundi. The etiological part in chronic hepatopathies (cirrhoses, chronic hepatitis) and primitive cancer of the liver is very high. However, there remains the task of determining how much of this is due to Hep B (which has been known and studied in Burundi for a long time) and how much to Hep C, for which systematic screening among blood donors did not begin until September 1997, while serological diagnosis is only just beginning.

**	 Haemophilus influenzae b: systematic screening by LCR culture is carried out among children of 0-5 years old. The work is carried out in a single microbiological laboratory in Burundi, namely that of the Kamenge University Hospital Centre in Bujumbura.

Compared to the other bacteria causing purulent meningitis among children (Streptococcus pneumoniae and Neisseria meningitidis) Hep B ranks second after S. pneumoniae.

We have consulted the records of the microbiological laboratory of KUHC for the last 6 years (1995 to 2000) and found as follows:

| Years | Isolated bacteria |  |  |  |
| --- | --- | --- | --- | --- |
|  | Number of samples | S. Pneumoniae | Hib | N. Meningitidis |
| 1995 | 190 | 12 | 5 | 1 |
| 1996 | 159 | 17 | 4 | 2 |
| 1997 | 200 | 10 | 2 | 0 |
| 1998 | 285 | 14 | 6 | 1 |
| 1999 | 157 | 9 | 2 | 0 |
| 2000 | 195 | 13 | 3 | 1 |
| Total | 637 | 75 | 22 | 5 |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- extension of the cold chain to accommodate new stocks arising from the introduction of new vaccines

- training of health workers at all levels in the methods to reduce vaccine wastage rates

- regular monitoring of vaccine wastage

- maintenance of the cold chain

- estimate of the basic vaccine wastage prior to introducing new vaccines

- application of the opened vial policy

- organisation and prudent distribution of vaccines

- vaccine safety

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulas)

| Table 7.1: Estimated number of doses of DTP + HB+ Hib vaccine |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to receive new vaccine | match with targets in table 4 | 0 | 213 408 | 237 402 | 259 555 | 282 793 | 282 793 |
| B | Number of doses per child | # | 3 | 3 |  | 3 | 3 | 3 |
| C | Estimated wastage rate in percent | % | 0 | 5 |  | 5 | 5 | 5 |
| D | Equivalent wastage factor | See list in table  | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| E | Number of doses | A x B x D | 0 | 672 236 | 747 817 | 817 597 | 890 796 | 890 796 |
| F | Number of vaccines buffer stock | E x 0.25 | 0 | 168 059 | 0 | 0 | 0 | 0 |
| G | Total of vaccine doses needed | E + F | 0 | 840 300 | 747 80 | 817 600 | 890 800 | 890 800 |
| H | Percentage of vaccines requested from the Vaccine Fund | % | 0 | 100 | 10 | 100 | 100 | 100 |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 | 0 | 840 300 | 747 800 | 817 600 | 890 800 | 890 800 |
| J | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 | 0 | 897 194 | 790 549 | 864 317 | 941 699 | 941 699 |
| L | Number of AD syringes buffer stock | K x 0.25 | 0 | 224 299 | 0 | 0 | 0 | 235 425 |
| M | Total of AD syringes | K + L | 0 | 1 121 500 | 790 549 | 864 317 | 941 699 | 1 177 124 |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J | 0 | 466 400 | 415 029 | 453 768 | 494 394 | 494 394 |
| ##### O | Number of safety boxes (+10% extra needs) | (M + N) x 1.11 / 100 | 0 | 17 600 | 13 382 | 14 631 | 15 941 | 18 554 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulas as per table 7.1)

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number 14 |
| --- | --- |

# Strategic plans to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan by the time of the mid-term review. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief :

- Government undertaking to increase the budget currently allocated to vaccine independence from 6% to 25% in the year 2002 and 100% in 2006

- Priority given to the social sectors in the plan for poverty reduction in Burundi and the use of the funds released through the lightening of the debt burden

| - Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number 15 |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- application of the opened vial policy

- maintenance of the cold chain

- gradual increase of the government's contribution towards vaccine independence

- monitoring, training and raising awareness of health workers on methods to reduce vaccine wastage rates

- vaccine safety

- improving vaccine management (distribution, transport, etc)

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the Republic of Burundi,

considering that its DTP3 coverage for 2000 was 57.2% corresponding to 149 675 children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for immunization services                       		  YES           NO

- Support for new or under-used vaccines                                  YES           NO

- Support for injection safety                                                      YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 18 752 children. Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

Improving the functioning of the health services is one of the priorities set by the Government and it falls within the national programme of action for the development of Burundi (2001-2010). It is for this reason that the budget package allocated to the EPI has increased to more than BIF 23 million for the financial year 2001, compared to less than BIF 10 million granted by the Government in the previous year. Thus, despite the uncertainties of the external environment, the Government of Burundi has decided, within its health policy, to allocate an increased budget each year.

The management of the funds intended for the EPI is fully transparent. The funds are credited to a bank account opened with the Central Bank of the Republic of Burundi and jointly managed by senior officials of the Ministry of Public Health and the Ministry of Finance, namely the Director of the EPI, the Human Resources Manager of the Ministry of Public Health and the Accounts Director of the Ministry of Finance.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 9 : New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Combined DTP+Hib+HB | 2 | January 2003 | 840 300 | 747 800 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

x

By UNICEF    x                                        By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are entitled to receive USD 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		x	The amount of supplies listed in table 8

The equivalent amount of funds

| Table 8: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES requested from GAVI and the Vaccine Fund (fill in the total sums of rows “F”, “H” and “I” of tables 6.1,6.2, 6.3, 6.4. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | 357 300 | 312 500 | 340 500 | 350 400 |
|  |  | for other vaccines | 1 611 165 | 1 643 105 | 1 621 599 | 1 775 223 |
| H | Total for reconstitution syringes |  | 82 512 | 91 092 | 100 116 | 108 602 |
| I | Total for safety boxes |  | 22 780 | 22 750 | 22 900 | 24 820 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

# Additional comments and recommendations from the ICC

During the meetings held on Friday 31 August and Wednesday 5 September 2001, which were attended by the majority of the committee members, the ICC examined the proposal of the Government of Burundi to the Global Alliance for Vaccines and Immunization (GAVI) and the Global Fund for Children's Vaccines (the Fund) with regard to the financing of its expanded  programme on immunization over the next five years.

Considering the relevance of the proposal, which meets the current concerns of the Government of Burundi in its struggle to improve the health of the population,

Considering that the Ministry of Health of Burundi has taken into account the recommendations of the ICC in the preparation of this proposal, particularly with regard to continuing the process of decentralisation of the health services and conducting a detailed study on the financing of the EPI,

Considering the undertaking given by the Government of Burundi gradually to improve the financing of  health sector expenditure and, in particular, the EPI Programme in such a way as to ensure the sustainability of the actions undertaken with the assistance of GAVI and the Fund intended, in particular, to cover EPI vaccine requirements fully by the end of 2006,

The ICC strongly recommends to GAVI and the Fund that they should accept the proposal of Burundi on the occasion of their next meeting of 1 October 2001 for the following 3 components:

- Support for the health services

- Support for the new and under-used vaccines

- Support for injection safety.

The members of the ICC undertake to continue providing technical and financial support for the EPI through the financing of the headings indicated in the annexed EPI financing plan.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD 000s)

Table 1

| Expenditure in 2000 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | UNICEF1 | WHO | NGO | Donor 4 | Donor n.. 2 | Total Expenditure in 2000 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccines | 16 322* |  |  | 526. 336 |  |  |  |  |  |
| 1.2 | - AD syringes |  |  |  | 127.328 |  |  |  |  |  |
| 1.3 | - Dilution syringes |  |  |  |  |  |  |  |  |  |
| 1.4 | - Safety boxes |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators |  |  |  |  |  |  |  |  |  |
| 2.2 | - Freezers |  |  |  |  |  |  |  |  |  |
| 3. | Other immunization specific items |  |  |  |  |  |  |  |  |  |
| 3.1 | - NID |  |  |  | 235.214 | 290.000 |  |  |  |  |
| 3.2 | - LID – Measles |  |  |  | 28 .025 |  | 509.270 |  |  |  |
| 3.3 | - Paraffin |  |  |  | 43. 154 |  |  |  |  |  |
| 3.4 | - Diesel |  |  |  | 24. 000 |  |  |  |  |  |
| 3.5 | - Monitoring |  |  |  |  | 40. 492 |  |  |  |  |
| Total expenditure in 2000 |  |  |  |  | 1 034.056 | 330.492 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission * 15.000.000 Burundi Francs (1 $US = 919 Fbu) |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2000 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | UNICEF1 | WHO | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccines | 16.322 |  |  | 260.000 |  |  |  |  |  |
| 1.2 | - AD syringes |  |  |  | 175.000 |  |  |  |  |  |
| 1.3 | - Dilution syringes |  |  |  |  |  |  |  |  |  |
| 1.4 | - Safety boxes |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators |  |  |  | 12.000 |  |  |  |  |  |
| 2.2 | - Spare parts |  |  |  |  |  |  |  |  |  |
| 3. | Other immunization specific items |  |  |  |  |  |  |  |  |  |
| 3.1 | - Paraffin |  |  |  | 43.000 |  |  |  |  |  |
| 3.2 | - Diesel |  |  |  |  |  |  |  |  |  |
|  | - Polio NID + measles LID |  |  |  | 624.000 |  |  |  |  |  |
|  | - Monitoring |  |  |  |  |  |  |  |  |  |
|  | - Vaccination cards |  |  |  | 30.000 |  |  |  |  |  |
|  | - Mobile team organisation |  |  |  | 32.000 |  |  |  |  |  |
|  | - Training |  |  |  | 12.000 | 5.000 |  |  |  |  |
|  | - Follow-up and assessment |  |  |  |  | 15.000 |  |  |  |  |
|  | - Promotion / communication |  |  |  |  | 5.000 |  |  |  |  |
| Total commitment |  |  |  |  | 1 207.000 | 25.000 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number 1 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number 3 |
| - Terms of reference of the ICC | Document number 2 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 4, 5 & 6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 7, 8 & 9 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 10 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 11 & 12 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 14 Document number 13 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2000 and resource needs (Annex 1) | Document number 15 |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative : |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

Please submit hard copy documents with an identical electronic copy whenever possible