The Government of

MOZAMBIQUE

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

# Signatures of the Government

The Government of Mozambique, represented by the Vice Minister of Health, Dr. Aida Lebombo commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:	…………………………………………...

Title:	Vice Minister of Health………………...

Date:	…………………………………………...

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |
| MOH/Nat. Dir. of Health | Dr.Alexandre Manguele National Director of Health |  |
| USAID | Dr.Okey Nwanyanwu Chief of HPN and SO3 Team leader |  |
| UNICEF | Dr.Mark Stirling Representative |  |
| WHO | Dr.Carlos Tiny Representative |  |
| GTZ | Dr.Angelika Stre. Reproductive Health Adv. |  |
| Rotary International | Eng.Oscar Carvalho President |  |
| UNFPA | Dr.Georges Georgi Representative. |  |
| Swiss Cooperation | Mrs. Fatima Aly Chief of the health section |  |
| DFID |  |  |
| World Bank | Dr. Kees Kostermans Health Officer |  |
| Dutch Cooperation |  |  |
| European Union |  |  |
| Irish Cooperation | Dr. Bert Schreuder Health Advisor |  |

Signed this day of : _____/________/2000

In case the GAVI Secretariat have queries on this submission, please contact :

Name : …Mr.Manuel Matusse……	Title/Address : …National EPI Manager…….

Tel.No. : …00258 1 491798…….   		            ………………………………..

Fax No. :…00258 1 491798…….. 		            ………………………………..

E-mail :misaudns@tropical.co.mz or rmacaule@virconn.com

- Immunization-related fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 17,690,585 | GNP per capita | $140 US |
| Infants 0-11 months | 707,623 | Infant mortality rate | 134/ 1000 |
| Percentage of GDP allocated to Health |  | Percentage of Government expenditure for Health Care | 5% (92-98) The state of world children 2000 |

| Health system development status |  |
| --- | --- |
| Please find attached background documentation on: |  |
| - Overall government health policies and strategies | Document number………….. |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number………….. |
| - Status of the ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number………….. |
| - Government policies and practices on private sector participation, as it relates to immunization | Document number………….. |

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 99 % | 100 % |  |  | Diphtheria |  |  |  |  |
| DTP3* | 77 % | 80 % |  |  | Pertussis | 123 | 82 |  |  |
| OPV3 | 77 % | 80 % |  |  | Polio | 0 | 0 |  |  |
| Measles | 87 % | 89 % |  |  | Measles | 16,443 | 3,954 |  | 3.4% Source: CFR of Rural Hospital |
| TT2+ Pregnant Women |  | 41 % |  |  | NN Tetanus | 44 | 32 |  |  |
| Hib |  |  |  |  | Hib |  |  |  |  |
| Yellow Fever |  |  |  |  | Yellow fever |  |  |  |  |
| HepB |  |  |  |  | HepB seroprevalence |  |  |  |  |

Note: In connection with the DTP3 coverage in the country, the MoH considers that the real coverage varies between 60-65 %. The high coverage reported through the HIS, is due to the denominator based on census data. The DHS conducted in 1997 reported a national DPT3 coverage of 59,6% ranging from 28,9% in Cabo Delgado to 88,1% in Maputo City. Thus, the coverage considered above would be most realistic for the country. A national survey for MCH in which EPI coverage survey is included, is schedule to take place in September 2000. We will wait for the result of this survey to have a most updated figure of DPT3 coverage in the country.

# Profile of the Inter Agency Coordinating Committee (ICC)

- Name of the ICC…Interagency Coordinating Committee for EPI……………………………………

- Date of constitution of the current ICC  …in 1998………………………………………………………

- Organizational structure (e.g., sub-committee, stand alone) : Technical sub-committee, IEC sub-committee and Epidemiological and Research sub-committee………………………………………….

- Frequency of meetings : …meets quarterly, but more frequently if and when necessary..……………..

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | National Director of Health/MoH | Dr.Alexandre Managuele |
| Secretary | National EPI Manager/MoH | Mr.Manuel Matosse |
| Members | - UNICEF-Project officer - USAID - WHO - UNFPA - GTZ - Rotary Mozambique - DFID - EU - Swiss Coop - Irish Coop - World Bank - Dutch Cooperation - Pharmaceutical Dept. - IEC Unit - Epidemiology Unit - Maintenance Dept. - Family Health Dept. - Planning Dept. - Supply Unit …………. | Dr.Alejandro Gonzalez Dr.Rose Macauley Dr.Lieve van der Paal Dr.Laura Guarenti Dr.Angelika Str. Ing.Oscar de Carvalho Dr.Kees Kostermans Dr.Joaquim Durão Mrs.Isabel Ngomane Mr.Jose Chivale Ing.Momade Sumalgy Dr.Lilia Jamisse Mr. Fortunato |

- Major functions and responsibilities :

- Assist the Government in assuming its role of providing technical oversight in the development of national policy framework for vaccines and immunization programs with prioritization of immunization activities, setting of attainable targets and the appropriate guidelines. - Mobilize financial and other resources necessary to attain and maintain high quality and coverage of the EPI in a sustainable manner. - Evaluate the efficient and effective use of available resources - Advocate for increased national commitment to immunization services - Raise public awareness on importance of immunizations through social mobilization efforts - Strengthening the role and capacity of the government to take ownership in the administration and delivery of national immunization services

- The following diagram shows the ICC functional relationships with other institutions in health sector :

See diagram in annex 1

Find attached the following documents :

| - Terms of reference of the ICC | Document number…………. |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings in which partners participated that concerned improving and expanding the national immunization program | Document number…………. |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| EPI National Assessment | MoH/NIH/UNICEF/ WHO/USAID | Nove. to December 1998 |

- The following are the three major problems identified in the assessments :

- Limited coverage of services nationwide, only 51% of health facilities have vaccination services. - Lack of financial resources and equipments including cold chain and spare parts. The program had not been able to procure cold chain equipment or provide supervision for more than 3 years before the review because there was no money to do so. - Insuficient staff and need for training for vaccination activities.

- The following are the three major recommendations in the assessments :

- Establishing mechanism for sustainable funding. - Training health workers - Extension of vaccination services.

- Find attached a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number….. |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in workplan, implemented, not implemented, in progress…. | Document number….. |

- The following components or areas of immunization services are yet to be reviewed (or studied). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |
| Coverage survey | 2000 | 80,000 |
| Injection safety assessment | 4th Q of 2000 | 30,000 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number……. |
| --- | --- |

- As per 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 503,164 |
| Used doses of DTP | 2,260,000 |

- Estimated annual targets

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Children planned to be vaccinated with DTP3 | 523,164 | 549,322 | 576,788 | 605,627 | 635,908 | 667,703 |
| Doses of DTP planned to be used | 2,400,000 | 2,610,000 | 2,700,000 | 2,800,000 | 2,870,000 | 2,935,000 |

# New and under-used vaccines

Find below a summary of those aspects of the plan, mentioned in section five,  that refer to introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepat.B | Hepatitis B in Mozambique | Junho, 1992 | 10% prev. |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of monovalent vaccine :

According to the Hepatitis B sero prevalence study in pregnant women conducted by the NIH in Mozambique, a monovalent antigen of HepB vaccine would be beneficial. But the considering the limited coverage of health system mostly in rural areas, it may not be wise to start the monovalent dose at the moment. The MoH will consider administrating the monovalent HepB in the provincial capital starting in 2003, after the tetravalent vaccine administarion is running well in the whole country.

- Planning for hepB vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 271,582 | 576,788 | 605,627 | 635,908 | 667,703 |
| Total vaccine doses required | 1,310,000 | 2,700,000 | 2,800,000 | 2,870,000 | 2,935,000 |
| Hep B monovalent vaccine |  |  | 210,000 | 215,000 | 220,000 |
| Preferred vial size(s) 10 dosis vial | 10 dosis | 10 dosis | 10 dosis | 10 dosis | 10 dosis |
| Estimated wastage rate | 30% | 30% | 25% | 25% | 25% |
| % of vaccines requested from the Fund | 100% | 100% | 100% | 100% | 100% |
| AD syringes | 1,132,500 | 2,320,000 | 2,590,000 | 2,655,000 | 2,720,000 |

*: Target group of each year (4% of population) x 80%(coverage) x 3 dosis x wastage rate (1.3-

1.25) x 15% of stock.

** : Target group (4% of population) x 30% urban population x 70% of institutional births x wastage rate (1.3-1.25) x 15% stock.

*** :  Serynges for tetra and monovalent vaccine including 15% of wastage and 15% of stock.

| - Find attached the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number…… |
| --- | --- |

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each line item and for each year are attached in Annex 1. | Document number .…. |
| --- | --- |

- Find below a list of financial sustainability strategies and of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative). The relevant documents are attached.

(USD ,000)

| Strategy title / Line item | Partner1 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Document number |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Specify contributions in USD made by each partner sharing the strategy (Government, name of donor…) |  |  |  |  |  |  |  |  |  |  |

| - We summarize hereunder the support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached. | Document number…… |
| --- | --- |

According to WB information, the Government will allocate 40-50 millions dollars (USD) every year to the social sectors in which health is included. It is still not clear what percent of that this amount will be allocated to the health sector.

# Preferred channel of funds

(Only for countries seeking support from the immunization services sub-account)

- From the immunization services sub-account, funds will be transferred to the country through the following channel or system (tick only one) :

| Directly to the Government | X | Through a partner agency |  | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the following box we describe how the mechanism will operate and how it will address transparency, standards of accounting, long-term sustainability and empowerment of the government.

The MOH will prepare a budget for the available funds and said budget will be presented to the ICC for a consesus. Once approved, the funds will be administered according to the budget. A quarterly financial report will be presented to the ICC. . In addition every year an independent company is hired to conduct audit to this process and other in the MoH. GAVI initiative will benefit for this control mechanisms already established.

# Country concerns

The following are the ICC’s concerns and recommendations while submitting this proposal :

1) The disposal of needles and serynges. The MoH considers that intensive training of health workers and supervision will help in solving this problem. 2) Currently, there exist no quality control institution in Mozambique for vaccines importation. In collaboration with the NIH the Government can guarantee the quality control of vaccines supported by a South African Lab. Meanwhile, the government will request UNICEF to procure the vaccines and supplies for year 1. Decision for the mechanism of procurement for subsequent years will be made later.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Privatsector | Pooling | USAID | UNICEF | Donor 4 | Donor n.. 2 | Total Expend-iture in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccines |  |  |  | 820,776 |  |  |  |  | 820,776 |
| 1.2 | - Line item n3… |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Sterlization and serynges |  |  |  | 750,000 |  | 64,029 |  |  | 810,029 |
| 2.2 | - Cold chain |  |  |  |  |  | 42,382 |  |  | 42,382 |
| 2.3 | - Mantainance of Nat. Vac. Storage |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - EPI National Seminar |  |  |  |  | 40,000 | 7,106 |  |  | 47,106 |
| 3.2 | - EPI 5-year Plan |  |  |  |  |  | 41,150 |  |  | 41,150 |
| 3.3. | - Vaccine delivery |  |  |  | 15,000 |  | 23,781 |  |  | 38,781 |
| 3.4 | - EPI guideline reproduction |  |  |  | 30,000 |  |  |  |  |  |
| 3.5 | - Motorcycles |  |  |  |  |  | 135,629 |  |  | 135,629 |
| 3.6 | - Spare parts for Motor. |  |  |  |  |  | 19,842 |  |  | 19,842 |
| 3.7 | - Supervision |  |  |  |  | 10,000 | 44,029 |  |  | 54,290 |
| 3.8 | - Stationary national office |  |  |  |  | 3,500 |  |  |  | 3,500 |
| 3.9 | - Training of health workers |  |  |  |  |  |  |  |  |  |
| 3.10 | - Outreach services |  |  |  |  |  | 36,188 |  |  | 36,188 |
| 3.11 | - Develop NNT stratgey, guidelines and studies |  |  |  |  |  | 18,750 |  |  | 18,750 |
| 3.12 | - Devlope. Meales strategy |  |  |  |  |  |  |  |  |  |
| 3.13 | - Social Mobilization |  |  |  |  |  |  |  |  |  |
| Total expenditure in 1999 |  |  |  |  | 1,585,776 | 53,500 | 432,886 |  |  | 2,072,162 |

Note: This expenditure did not include the running costs at provincial and district level namely  staff salary, supervision, transport, fuel, petrol for refrigerators and stationary. Financial support for Bilateral and NGOs at provincial and district level is missed. Supervision, outreach services fromUNICEF funds were allocated at district level.

The expenditure for NID’s will be sent later on.

Table 2

| Budget for 1999 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Privatsector | Pooling | USAID | UNICEF | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccine |  |  |  | 737,980 |  |  |  | 737,980 |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Esterilization and Serynges |  |  |  | 912,188 |  |  |  | 912,188 | -102,159 |
| 2.2 | - Cold chain and spare parts |  |  |  | 425,000 |  | 236,000* |  | 610,000 | -567,618 |
| 2.3 | - Mantainance of Nat. Vac. Storage |  |  |  | 35,000 |  |  |  | 35,000 | -35,000 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - EPI National Seminar |  |  |  |  | 40,000 |  |  | 40,000 |  |
| 3.2 | - EPI 5-year Plan |  |  |  |  |  | 11,300 |  | 11,300 |  |
| 3.3. | - Vaccine delivery |  |  |  | 35,000 |  |  |  | 35,000 |  |
| 3.4 | - EPI guideline reprodution |  |  |  | 30,000 |  |  |  | 30,000 |  |
| 3.5 | - Motorcycles |  |  |  | 600,000 |  |  |  | 600,000 | -464,371 |
| 3.6 | - Spare parts for Motor. |  |  |  | 130,000 |  |  |  | 130,000 | -110,158 |
| 3.7 | - Supervision |  |  |  | 28,113 |  | 18,100 |  | 46,213 |  |
| 3.8 | - Stationary national office |  |  |  | 15,000 |  |  |  | 15,000 | -11,500 |
| 3.9 | - Training of health workers |  |  |  | 46,654 |  |  |  | 46,654 | -46,654 |
| 3.10 | - Outreach services |  |  |  |  |  |  |  |  |  |
| 3.11 | - Develop NNT stratgey, guidelines and studies |  |  |  |  |  | 25,000 |  | 25,000 | -6,250 |
| 3.12 | - Devlope. Meales strategy |  |  |  |  |  | 25,000 |  | 25,000 |  |
| 3.13 | - National workshop NNT and Meales strategy |  |  |  |  |  | 35,000 |  | 35,000 |  |
|  | - Social Mobilization |  |  |  |  |  | 17,300 |  | 17,300 |  |
| Total commitment |  |  |  |  | 2,962,935 | 40,000 | 367,700 |  | 3,370,635 | -1,343,710 |

* Includes cold chain, motorcycles and spare part.

ANNEX 2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number…… |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number…… |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number…… |
| - Government policies on private sector participation, as it relates to Immunization. | Document number…… |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC | Document number…… |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number…… |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document number…… |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number…… |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…… |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | Document number…… |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number…… |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Document number…… |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Document number…… |

Please submit hard copy documents with an additional electronic copy wherever possible