The Government of

THE UNITED REPUBLIC OF TANZANIA

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.ch or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Signatures of the Government

The Government of …THE UNITED REPUBLIC OF TANZANIA (MAINLAND)

commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:	…………………………………………...

Title:  MINISTER OF HEALTH.

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |
| Government of Tanzania. Ministry of Health |  |  |
| WHO |  |  |
| UNICEF |  |  |
| DANIDA |  |  |
| WORLD BANK |  |  |
| IRELAND AID |  |  |
| JICA |  |  |
| ROTARY INTERNATIONAL |  |  |
| DFID |  |  |

Signed this day of : _____________/2000

In case the GAVI Secretariat have queries on this submission, please contact :

Name : Dr. Ali A. Mzige  Title/Address :Director of Preventive Services – Ministry of Health.

Tel.No. : 	+255 –051 –120261 (cont…120266)

Mobile tel.	+255 –0811- 410531.

Fax No:	 +255 – 051 - 123676.

E-mail :……………………………

Immunization-related fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 31-34 million (estimates vary –low estimate from projections from 1988 census and high estimate from demographic survey) | GNP per capita | 217$US (1997) |
| Infants 0-11 months | Year 2000: 1,260,000 (extrapolated from 1988 Census) 1,319,964 (aggregated regional estimates from head counts and doses administered during NIDS) | Infant mortality rate | 88/1000 LB (1998) |
| Percentage of GDP allocated to Health | GDP 4-6% Government spending to MOH = $1.31 per capita in 2000 | Percentage of Government expenditure for Health Care | 6.9% (1999) |

| Health system development status |  |
| --- | --- |
| Please find attached background documentation on: |  |
| - Overall government health policies and strategies - United Republic of Tanzania Ministry of Health, National Health Policy - Health Sector Reform – Plan of Work | Document number……1…..… Document number……3…….. |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number……2…….. |
| - Status of the ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services - Main report of the joint MOH/partners health sector, Review of implementation progress of health sector plan of action 1999/2000 - A Review of the situation of expanded programme of immunization in Tanzania February 2000, Dr G.Msamanga EPI – Summarized Report. | Document number……18…..… Document number….17…….. |
| - Government policies and practices on private sector participation, as it relates to immunization - Health Sector Reform report – Plan of Work - Summary from EPI Manager on status of private/public sector participation in immunizations | Document number……3…….. Document number..…4…….. |

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 85% | 87% | NA | 93% | Diphtheria | 0 | 0 | No data available for use in estimation |  |
| DTP3 | 74% | 76% | NA | 82% | Pertussis | 0 | 0 |  |  |
| OPV3 | 82% | 74% | NA | 81% | Polio | 0 | 0 | 0 | 0 |
| Measles | 72% | 72% | NA | 79% | Measles | 1O,O23 | 5,887 | 293,328/4,440 | 253,423/3801 |
| TT2+ Pregnant Women | NA | 77% | NA | 83% | NN Tetanus | 11 | 41 | 846/677 | 846/677 |
| Hib | NA | NA | NA | NA | Hib | NA | NA | NA | NA |
| Yellow Fever | NA | NA | NA | NA | Yellow fever | NA | NA | NA | NA |
| HepB | NA | NA | NA | NA | HepB seroprevalence (if available) | 5% - 10% see table, doc #___13 | 10% + | 12,000-27,000 deaths | 12,000-27,000 deaths |

# Profile of the Inter Agency Coordinating Committee (ICC)

(Various agencies and partners supporting immunization services in the country are coordinated and organized through an inter-agency coordinating mechanism which is referred to in this document as ICC)

- Name of the ICC :  EPI – Interagency  Coordinating Committee.

- Date of constitution of the current ICC  ……July 3, 1997

- Organizational structure (e.g., sub-committee, stand alone)    Stand alone

- Frequency of meetings   Monthly

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Director of Preventive Services, Ministry of Health | DR ALI A. MZIGE. |
| Secretary | EPI – Manager, Ministry of Health | DR CAROLINE S. AKIM. |
| Members | - GOT, Medical Stores Department - GOT, Tanzania Food and Nutrition Centre - JICA - WHO - DFID - UNICEF - DANIDA - ROTARY INTERNATIONAL - WORD BANK - IRELAND AID - DANISH EMBASSY - AMREF | Ex officio |

- Major functions and responsibilities :

- To foster a strong partnership by coordinating all inputs and resources for the good of the child. - To support the national level to review and endorse work plans such as plans of action for national immunization days, EPI annual plans, five year strategic plans, surveillance plans etc. - To support the EPI programme to mobilize resources, both within the country and externally for use in the programme - To ensure that the programme manager receives both technical and political support that helps to validate his or her authority on issues pertaining to EPI. - To support the EPI programme staff in addressing technical issues arising as problems in the implementation of immunization services in the country. - To support the EPI programme staff technically in monitoring the programme’s performance.

- The following diagram shows the ICC functional relationships with other institutions in health sector :

See attached diagram: Document number…14…….

Find attached the following documents :

| - Terms of reference of the ICC | Document number……5… |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings in which partners participated that concerned improving and expanding the national immunization program | Document number…6…….. |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Rapid assessment of injection safety (KAP survey and observations related to safety of injections and waste disposal among health workers, EPI managers and the public) | MOH, WHO, BBC, UNICEF | March 24-April 6, 2000 |
| Assessment of immunisation services (2000) | Ministry of health, WHO, UNICEF, CDC, DFID, BASICS, Abt..Associates, DANIDA, Ireland Aid | 14th - 28th February, 2000. |
| Cold chain review | Ministry of Health, UNICEF, WHO, Ireland Aid. | January, 1998. |
| Review of USAID support to UNICEF for immunization in TANZANIA | WHO/AFRO, UNICEF/NEWYORK, BASICS/USAID | 17th – 26th June, 1997 |

- The following are the three major problems identified in the assessments :

- Vaccine forecasting, supply and quality, failure of cold chain equipment - Injection safety and safe disposal of injection waste - Improving management (health system) and supervision of immunization services at all levels.

- The following are the three major recommendations in the assessments :

- Improve vaccine forecasting, storage and distribution, adopt the WHO/UNICEF “multi-dose vial policy”, introduce monitoring of vaccine wastage. - Ensure that all injections are safe and that injection waste is safely disposed. MOH should study the feasibility of introducing auto-disable syringes and safety boxes with consideration of safe disposal. - Conduct a training needs assessment and provide appropriate training for supervisors and staff (immunization services providers) at all levels on EPI and planning and management issues including introduction of hepatitis B vaccine.

- Find attached a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number…7. |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in workplan, implemented, not implemented, in progress…. | Document number…8. |

- The following components or areas of immunization services are yet to be reviewed (or studied). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. - Five Year National EPI Strategic Planning Tanzania | Document number…9. |
| --- | --- |

- As per 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 921,776 |
| Used doses of DTP | 3,758,845 |

- Estimated annual targets

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Children planned to be vaccinated with DTP3 | 945,000 | 1,042,772 | 1,126,241 | 1,185,680 | 1,247,558 | 1,326,713 |
| Doses of DTP planned to be used | 4,429,688 | 4,887,992 | 5,279,255 | 5,557,873 | 5,847,929 | 6,218,969 |

# New and under-used vaccines

Find below a summary of those aspects of the plan, mentioned in section five, that refer to introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | Hepatitis b vaccine and its use in Tanzania J. Wenger, WHO Geneva | 1999 and 2000 (revised) | HbsAg 5-15% ~80% population have been infected |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of monovalent vaccine :

Not Applicable

- Planning for hepB vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 1042772 | 1126241 | 1185680 | 1247558 | 1326713 |
| Total vaccine doses required | 4887992 | 5279255 | 5557873 | 5847929 | 6218969 |
| Preferred vial size(s) | 10 dose | 10 dose | 10 dose | 10 dose | 10 dose |
| Estimated wastage rate | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |
| % of vaccines requested from the Fund | 100 | 100 | 100 | 100 | 100 |
| AD syringes | 4887992 | 5279255 | 5557873 | 5847929 | 6218969 |

- Planning for Hib vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

- Planning for yellow fever vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

| - Find attached the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) - Hepatitis B Vaccine Introduction in Routine Infant Immunization – Tanzania | Document number…10. |
| --- | --- |

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each line item and for each year are attached in Annex 1. | Document number .11. |
| --- | --- |

- Find below a list of financial sustainability strategies and of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative). The relevant documents are attached.

(USD ,000)

| Strategy title / Line item | Partner1 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Document number |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine Independence Initiative | UNICEF |  |  |  |  |  |  |  |  |  |
|  | GOT/MOH | 213 | 92 | 506 |  |  |  |  |  |  |
| Specify contributions in USD made by each partner sharing the strategy (Government, name of donor…) |  |  |  |  |  |  |  |  |  |  |

| - We summarize hereunder the support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached. | Document number…… |
| --- | --- |

The President of the United Republic of Tanzania has openly declared in public that immunization is one of the priority issues to be considered for support from the funds generated from poverty reduction strategy. High level Government Officials will work out the amount.

# Preferred channel of funds

(Only for countries seeking support from the immunization services sub-account)

- From the immunization services sub-account, funds will be transferred to the country through the following channel or system (tick only one) :

| Directly to the Government |  | Through a partner agency | X | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the following box we describe how the mechanism will operate and how it will address transparency, standards of accounting, long-term sustainability and empowerment of the government.

Partner agency will be WHO. Funds will be channeled to MOH/EPI via WHO country office according to standard procedures .

# Country concerns

The following are the ICC’s concerns and recommendations while submitting this proposal :

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Document number 11

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | ROTARY INTERNATIONAL | ###### JICA | DFID | DANIDA | ##### UNICEF | IRELAND AID | Total Expend-iture in 1999 |
| 1. | Vaccines, AD syringes… |  | NIL | - |  |  |  |  |  |  |
| 1.1 | - OPV | 177.5 |  |  | 497.76 |  |  |  | 49 | 724.26 |
| 1.2 | - BCG |  |  |  |  |  | 200.88 |  |  | 200.88 |
| 1.3 | - TT |  |  |  |  |  |  | 121.59 |  | 121.59 |
| 1.4 | - MEASLES |  |  |  |  |  |  | 1741.48 |  | 1741.48 |
| 1.5 | - DPT |  |  |  |  |  | 113.978 |  |  | 113.978 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain equipments |  |  |  |  | 81.375 |  |  |  | 81.375 |
| 2.2 | - Kit Bs and spare parts |  |  |  |  |  |  |  |  |  |
| 2.3 | - Kerosine | 295 |  |  |  |  |  |  |  | 295 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  |  | 559.253 | 3548.54 |  |  | 4107.79 |
| 3.2 | - Outreach activities |  |  |  |  | 168.75 |  |  |  | 168.75 |
| 3.3 | - Mass campaign (operational) |  |  | 9.555 |  | 1020.918 |  | 11.379 |  | 1041.852 |
| 3.4 | - Disease surveillance |  |  |  |  | 236.274 |  |  |  | 236.274 |
| Total expenditure in 1999 |  | 472.5 | - | 9.555 | 497.76 | 2066.57 | 3863.39 | 1874.44 | 49 | 8833.229 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 2                                                                                           Document number 11

| Budget for 1999 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | IRELAND AID | ROTARY INTERNATIONAL | JICA | DFID | DANIDA | UNICEF |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV | 177.5 | 49 |  | 497.76 |  |  |  | 724.26 |  |
| 1.2 | - BCG |  |  |  |  |  | 200.88 |  | 200.88 |  |
| 1.3 | - TT |  |  |  |  |  |  | 121.59 | 121.59 |  |
| 1.4 | - MEASLES |  |  |  |  |  |  | 1741.48 | 1741.48 |  |
| 1.5 | - DPT |  |  |  |  |  | 113.978 |  | 113.978 |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold chain equipments |  |  |  |  | 81.375 | 471.362 |  | 552.737 | 471.362 |
| 2.2 | - Kit Bs and spare parts |  |  |  |  |  |  | 287.81 | 287.81 | 287.81 |
| 2.3 | - Kerosine | 496.2 |  |  |  |  |  |  | 496.2 | 201.21 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  |  | 559.253 | 3548.54 |  | 4107.77 |  |
| 3.2 | - Outreach activities |  |  |  |  | 337.5 |  |  | 337.5 | 168.75 |
| 3.3 | - Mass campaign (operational) |  |  | 9.555 |  | 1020.918 |  | 11.379 | 1041.852 |  |
| 3.4 | - Disease surveillance |  |  |  |  | 236.274 |  |  | 236.274 |  |
| Total commitment |  | 673.7 | 49 | 9.555 | 497.76 | 2235.32 | 4334.76 | 2162.259 | 9962.331 | 1129.132 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number…2 |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies on private sector participation, as it relates to Immunization. | Document number 4 |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC | Document number 5 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number 6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document number 7 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number 8 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 9 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | Document number 10 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number 11 |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Document number 12 |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Document number 12 |
| - Hepatitis B Seroprevalence | Document number 13 |
| - Diagram of Interagency Coordinating Committee | Document number 14 |
| - Rapid Assessment of Injection safety | Document number 15 |
| - Media campaign | Document number 16 |
| - Review situation of EPI in Tanzania | Document number 17 |
| - Review of Implementation progress of Health Sector Plan of Action… | Document number 18 |
| - Financial information - EPI Tanzania | Document number 19 |

Please submit hard copy documents with an additional electronic copy wherever possible