31/07/26 19:48

Revision  4

August  2002

The Government of

REPUBLIC OF ANGOLA

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

The Government of the Republic of Angola places great importance on the provision of sound health care services to its population. The Expanded Program on Immunization is one of the Ministry of Health priority programs.

Angola experienced one of the worst periods in its recent history, which was characterized by two phases of armed conflicts that directly affected the entire population. The social sectors, particularly basic health services were most hit by the war. The massive destruction of infrastructures and the small scale investment in the health sector have all contributed to the state of poor health of the population.

Notwithstanding, EPI as a program has made significant progress in reducing morbidity and mortality attributable to vaccine-preventable diseases among children less than five years of age. The program has particularly made great progress in the polio eradication initiative. By the end of 2002, the program had achieved certification levels for AFP surveillance.

According to our administrative data, the Angolan EPI vaccinated 47% of children less than one year of age (target population) with DTP3 in 2002. This figure translates into 311,557.  The country aims to vaccinate at least 70% of the target population of under one year in the year 2004 with DPT3. This target translates into 460,946 infants. Using the coverage of 2002 as the baseline and the anticipated coverage of 2004 for the request for the Institutional Strengthening Support (ISS), the number of infants to be vaccinated above the baseline is 149,389.

In addition to the request for ISS, Angola is also requesting for support for injection safety materials. The table below shows the forecast for the materials.

Table 0: Total supplies for safety of vaccinations with BCG, DTP, Measles, YF and TT vaccines requested to GAVI and The Vaccines Fund

| ITEM |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- |
| Total AD syringes | for BCG | 888,773 | 748,127 | 795,594 | 863,306 | 887,479 |
|  | for Others | 4,996,524 | 4,438,066 | 4,787,747 | 5,153,528 | 5,536,043 |
| Total of reconstitution syringes |  | 172,676 | 208,530 | 221,588 | 236,749 | 242,792 |
| Total of safety boxes |  | 67,244 | 59,881 | 64,435 | 69,415 | 73,996 |
|  | Total cost | $ 711,193 | $ 630,481 | $ 492,597 | $ 527,193 | $ 557,132 |

The ICC has been very involved in the all aspects of the program including the preparation of this Application and fully endorses its content.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of Angola commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	Vice Minister of Health.

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health | Vice Minister |  |
| WHO | WHO Representative |  |
| UNICEF | UNICEF Representative |  |
| Rotary | Chairperson Rotary/Polioplus |  |
| ODEBRECHT | Country Director |  |
| USAID | Health Officer |  |
| CORE Group | Country Director |  |
| RED Cross Society | Health Delegate |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Dr. Fátima Valente, National Programme Director, Rua 1º Congresso nº67

Tel.No.: 00-2442-391226

Fax No.: 00- 2442- 391226

E-mail: pav. ang @. ebonet.net

Alternative address:

Dr. Nasir Yusuf	Team leader ai, EPI/WHO

Tel.No.: 244-2 392180

Fax No.: 244-2 332314

E-mail:nasiryusuf@yahoo.com

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 14,418,866 (Projected for 2003) | GNP per capita | 648$US |
| Surviving Infants* | 753,597 | Infant mortality rate | 150/ 1000 |
| Percentage of GDP allocated to Health | 16.9% (2001) | Percentage of Government expenditure for Health Care | 8% |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 56% | 74% | NA | NA | 73.7 | 12-23 mo | Tuberculosis | 1,381 | 1,969 |
| DTP | DTP1 |  |  |  | NA | NA | NA | NA | Diphtheria | 0 | 0 |
|  | DTP3 |  | 31 | 41% | NA | NA | 39.0 | 12-23 mo | Pertussis | 560 | 504 |
| OPV3 |  |  | 33 | 44% | NA | NA | 64.3 | 12-23 mo | Polio | 59 | 1 |
| Measles |  |  | 41% |  | NA | NA | 58.2 | 12-23 mo | Measles | 1,375 | 10,103 |
| TT2+ (Pregnant women) |  |  | 60 | 14 | NA | NA | NA | NA | NN Tetanus | 77 | 447 |
| Hib3 |  |  | NA | NA | NA | NA | NA | NA | Hib | NA | NA |
| Yellow Fever |  |  | 29% | 49% | NA | NA | NA | NA | Yellow fever | 0 | 0 |
| HepB3 |  |  | NA | NA | NA | NA | NA | NA | hepB seroprevalence (if available) | NA | NA |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) |  |  | NA | NA | NA | NA |  |  |  |
|  |  | Infants ( > 6 months) |  |  | NA | NA | NA | NA |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. The above coverage is the best estimate. The program relies on administrative data and the coverage survey, indicated in the table above, as it has problems with the population data (last population census conducted in 1970).

- Summary of health system development status relevant to immunization: The following section is a summary of the annexed 02 document.

The National health structure is based on a three-tier system:

- Primary health care level composed of health centers, health post and maternities

- Secondary health care level composed of general hospitals and more simple specialized hospitals; and

- Tertiary health care level composed of highly specialized hospitals (teaching hospital, provincial and national hospitals)

Table 1: Health facilities in the country

| Type of facility | Number of facilities |  | Total |
| --- | --- | --- | --- |
|  | Functioning | Non-functioning |  |
| Health posts | 888 | 447 | 1335 |
| Health centers | 248 | 44 | 292 |
| Municipal and provincial hospitals | 70 | 6 | 76 |
| National hospitals | 8 | 0 | 8 |

Vaccination services are provided in about 30% of functioning health facilities. In addition, vaccination services are provided by mobile teams that originate from the provincial level and by outreach team, which originate from health facilities to reach populations that cannot be reached through the regular health system.

Malaria constitutes the main cause of morbidity and mortality among children and pregnant women in Angola, being 80% of the reported out patient visits and 76% of deaths registered in the year 2000.

In accordance with the “Strategic Project for Alleviating Poverty” of the Ministry for Planning, only 35% of the population use the health services. Among the main factors causing low use of preventative and curative Service, are the lack of medicines (46%), long time of waiting for attendance (16%), long distances to the health facilities (6%) and high costs of attendance (2%). Other causes of morbidity include acute respiratory diseases, acute diarrhoeic diseases, measles, tuberculosis and sexually transmissible diseases, including HIV/AIDS.

According to the Multiple Indicators Cluster Survey (MICS) conducted in 2001, about 45% of women had assisted births by trained personnel, compared to 23% in 1996. Combined factors to maternal mortality are malaria and anaemia. Among the main causes of maternal mortality through direct obstetrics complications are haemorrhage, which represents 25% of the total deaths, followed by sepsis (15%), hypertension in during pregnancies (12%).

| - Attached are the relevant section(s) of strategies for health system development | Document number 02.. |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

- Name of the ICC: Inter-agency coordinating Committee (ICC)

- Date of constitution of the current ICC: November 1995

- Organisational structure (e.g., sub-committee, stand-alone):  The Chairperson for the ICC is the Honourable Vice-Minister of Health.

The committee has several sub-committees, which include:

- Technical sub-committee

- Social Mobilization sub-committee

- Logistics sub-committee

- Frequency of meetings: Weekly although the TOR stipulates a monthly meeting

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Vice Minister/Ministry of Health | Dr. José Vieira Dias Van-Dunem |
| Secretary | EPI Program Director/MOH | Dr. Fátima Valente |
| Members | - Representative/WHO - Representative/UNICEF - President/Rotary - USAID - CORE Group - ODEBRECHET - Red Cross society | - Dr. Pier Paolo Balladelli - Dr. Mario Ferrari - Engr. Sylvia Nagy - Dr. Cathy Bowles - Dr. António Dias - Dr. Otacilio de Carvalho - Dr. Martin Acosta |

- Major functions and responsibilities of the ICC:

- Coordination: The ICC will coordinate all partners with the view of fostering a strong partnership that will facilitate rational use of resources, technical input, avoid duplication of efforts and to maximize benefits of the limited resources.

- Advocacy: The committee will advocate for EPI at higher political level nationally and internationally to ensure that the programme objectives are achieved.

- Programme Implementation: The ICC will review and endorse EPI Plans and supports the EPI programme implementation.

- Resource mobilization: the ICC will mobilize resources both locally and internationally. It is also responsible for ensuring that it supports the operationalization of the technical issues through its various sub-committees

- Social mobilization: ICC will support the program with social mobilization to ensure wide publicity of the programs

- Transparency and accountability:  ICC in collaboration with the EPI Unit, will also review and monitor the use of funds and other resources together and provide continuous feedback to the donors and communities as need arises.

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Ensure that regular meetings are held as planned.

- Agenda of the ensuing meeting is circulated in advance of the meeting date and time.

- The minutes are circulated to members in time

- Ensure that the terms of reference for the ICC are clear and responsibilities explicitly outlined.

- Ensure that the ICC is periodically briefed about the level of implementation of planned immunization and surveillance activities in order to enlist their support at all levels.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- The drop-out rate: as a sign of improvement in the immunization services, the ICC looks at the reduction of drop-out rate in multi-dose antigens (DTP1-DTP3)

- Country distribution of the vaccination coverage: the ICC monitors immunization coverage by sub-municipality levels (comunas).

- Wastage rate: The committee emphases the need to reduce vaccine wastage rate which is at the moment estimated at 30%

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number 03. |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number 04 |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number 05 (A, B &C) |

# Immunization services assessment(s)

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Multiple Indicator cluster Survey | UNICEF, NIS | 2001 |
| Evaluation of AFP surveillance | MOH,WHO,USAID & CDC, UNICEF | 10/2002 |
| National EPI Program Review | UNICEF, WHO, CDC, USAID, AN University | 03/2003 |

- The three major strengths identified in the assessments:

- Reduction in polio cases and

- Improved AFP surveillance performance

- Bilateral support to Cold chain expansion

- The three major problems identified in the assessments:

- Vaccine Management

- Training

- Supervision

- The three major recommendations in the assessments:

- Adopt the district planning approach as the model for expansion of routine EPI and use this approach to develop district, provincial and national plans

- Re-enforce training of supervisors and frontline health workers

- Review and revise the existing checklist and other supervisory tools.

- Attached are complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number 06 &07 |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document numbe 06 &07 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Evaluation of the measles immunization campaign | 2003 |
| Evaluation of the polio immunization campaign | 2003 |
| Immunization Coverage Survey | 2003 |
| Rapid Assessment of yellow Fever disease burden | 2004 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has updated the multi-year immunization plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. |  | Document number 08. |
| --- | --- | --- |
| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| Type of technical support | Period for the support | Desired from which agency |
| Training | To be determined | WHO, UNICEF & CDC |
| Rapid Assessment of yellow Fever disease burden | 2004 | WHO, UNICEF & CDC |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | X |  |  |
| Polio | At birth, 2, 4 & 6 Months | X |  |  |
| DTP | At 2, 4 & 6 Months | X |  |  |
| Measles | At 9 Months | X |  |  |
| Yellow Fever | At 9 Months | X |  |  |
| TT | Pregnant and women at childbearing age (15-45 Years) | X |  |  |
| Vitamin A | 6-59 months | X |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

| Major Action Points | Responsible Office | Timeframe |
| --- | --- | --- |
| Expansion of vaccination services: 1) by opening more fixed vaccination post in areas of the country that are recently accessible. 2) re-establishing functional out reach and mobile services that will be regular | MOH, WHO, UNICEF | 2003- 2005 |
| Ensure vaccine availability at all times by: 1) decentralizing vaccine depot to minimize distribution problem 2) Procurement of vehicles for distribution of EPI materials | MOH, WHO, UNICEF, JICA | 2003-2007 |
| Training of staff and improved supportive supervision which will aim at reducing missed opportunities for vaccination and improve quality of services | MOH, WHO, UNICEF | 2003-2007 |
| iv) Strengthening advocacy and communication | MOH, WHO, UNICEF | 2003-2007 |

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births |  | 711,105 | 733,075 | 753,597 |  | 774,699 | 796,390 | 818,688 | 841,611 | 865,176 |
| Infants’ deaths |  | 106,666 | 109,961 | 113,040 |  | 116,205 | 119,459 | 122,803 | 126,242 | 129,776 |
| Surviving infants |  | 604,439 | 623,114 | 640,557 |  | 658,494 | 676,932 | 695,885 | 715,369 | 735,400 |
| Pregnant women |  | 777,254 | 801,268 | 823,699 |  | 846,764 | 870,473 | 894,845 | 919,900 | 945,657 |
| Infants vaccinated with BCG* |  | 526,218 | 586,460 | 640,557 |  | 673,988 | 716,751 | 777,754 | 799,530 | NA |
| Infants vaccinated with OPV3** |  | 265,953 | 311,557 | 384,334 |  | 460,946 | 507,699 | 556,708 | 608,064 | NA |
| Infants vaccinated with DTP3** |  | 247,820 | 311,557 | 384,334 |  | 460,946 | 507,699 | 556,708 | 608,064 | NA |
| Infants vaccinated with**: DTP-HepB + Hib |  | NA | NA | NA |  | NA | NA | NA | NA | NA |
| Infants vaccinated with Measles** |  |  | 448,642 | 480,418 |  | 526,795 | 575,392 | 626,296 | 679,601 |  |
| Pregnant women vaccinated with TT+ |  | 677,774 | 696,752 | 716,261 |  | 736,316 | 756,933 | 778,127 | 780,306 | 802,155 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) |  |  |  |  |  |  |  |  |  |
|  | Infants (> 6 months) | 423,105 | 486,029 | 512,446 |  | 513,625 | 541,546 | 591,502 | 643,832 | 661,860 |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

| Major Action Points | Responsible Office | Timeframe |
| --- | --- | --- |
| Careful planning with accurate estimates and distribution of vaccines to sub-national levels | MOH | 2003- 2005 |
| Improved vaccine management with correct and appropriate stock management and records | MOH | 2003-2005 |
| Training of staff on the multi-dose policy and improved supportive supervision | MOH, WHO, UNICEF | 2003-2007 |
| Improved cold chain management | MOH | 2003-2007 |

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate | 30% | 30% | 30% | 30% | 25% | 20% | 15% | 15% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 28% | 28% | 25% | 20% | 15% | 10% | 10% | 10% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

N/A

- Planning and constraints for the Polio Eradication Initiative:

As part of the efforts being made for the eradication of polio, Angola started conducting national immunization days (NIDs) in 1996. The rounds of NIDs were being synchronized with countries in the sub-region (Namibia, Zambia, DRC, Congo-Brazzaville, Gabon e Sao Tome).

The OPV vaccination coverage during the NIDs in 2002 were 113% ,108%and 120% for first, second & third rounds respectively.

Surveillance for acute flaccid paralysis (AFP) has being part of the national integrated disease surveillance system. Moreover, AFP was intensified in 2002 that lead to the attainment of certification standards.

Also, the National Certification Committee and the National Expert Committee on Poliomyelitis were created in 2002.

Constraints for polio eradication

- Low routine OPV coverage

- Limited and uncertainties of funds for PEI activities

- Inadequate availability of transport

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

- Use of Auto-disabled syringes and needles since 1997

- Training of health workers for the proper use of AD and appropriate disposal

- Plans to build at least one incinerator in each province  and for each major hospital

| - Attached is a copy of the Plan to achieve Safe Injections and Management of Sharps Waste or of the relevant pages of the health plan. | Document number 08 &09. |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG vaccine Wastage included |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
|  |  | Target coverage | 85% | 87% | 90% | 95% | 95% |
| A | Target of children for BCG vaccination | See targets in Table 4 | 640,557 | 673,988 | 716,751 | 777,754 | 799,530 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate | % | 50% | 40% | 40% | 30% | 25% |
| D | Équivalent wastage factor | 1 / (1 - C) | 2.00 | 1.67 | 1.67 | 1.43 | 1.33 |
| E | Number of BCG doses | A x B x D | 1,281,115 | 1,123,314 | 1,194,585 | 1,111,077 | 1,066,041 |
| F | AD syringes (+ 10% wastage) | A x B x 1,11 | 711,019 | 748,127 | 795,594 | 863,306 | 887,479 |
| G | AD syringes buffer stock 2 | F x 0,25 | 177,755 | 0 | 0 | 0 | 0 |
| H | Total AD syringes | F + G | 888,773 | 748,127 | 795,594 | 863,306 | 887,479 |
| I | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| J | Number of re-constitution 3 syringes (+ 10% wastage) | E x 1,11 / I | 71,102 | 62,344 | 66,299 | 61,665 | 59,165 |
| K | Number of safety boxes (+ 10% extra need) | (H + J) x 1,11 / 100 | 10,655 | 8,996 | 9,567 | 10,267 | 10,508 |
|  | Cost of AD syringes | $ 0.110 | $ 97,765 | $ 82,294 | $ 87,515 | $ 94,964 | $ 97,623 |
|  | Cost of reconstitution syringes | $ 0.058 | $ 4,124 | $ 3,616 | $ 3,845 | $ 3,577 | $ 3,432 |
|  | Cost of safety boxes | $ 0.800 | $ 8,524 | $ 7,197 | $ 7,654 | $ 8,214 | $ 8,406 |
|  | Total cost for injection material |  | $110,413 | $ 93,107 | $ 99,014 | $106,754 | $109,460 |

| Table 6.2: Estimated supplies for safety of vaccination with DPT vaccine Wastage included |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
|  |  | Target coverage | 55% | 60% | 70% | 95% | 95% |
| A | Target of children for DPT vaccination | See targets in Table 4 | 384,334 | 460,946 | 507,699 | 556,708 | 608,064 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate | % | 30% | 30% | 25% | 20% | 15% |
| D | Equivalent wastage factor | 1 / (1 - C) | 1.43 | 1.43 | 1.33 | 1.25 | 1.18 |
| E | Number of DPT doses | A x B x D | 1,647,148 | 1,975,482 | 2,030,795 | 2,087,654 | 2,146,108 |
| F | AD syringes (+ 10% wastage) | A x B x 1,11 | 1,279,834 | 1,534,950 | 1,690,636 | 1,853,837 | 2,024,853 |
| G | AD syringes buffer stock 2 | F x 0,25 | 319,958 | 0 | 0 | 0 | 0 |
| H | Total AD syringes | F + G | 1,599,792 | 1,534,950 | 1,690,636 | 1,853,837 | 2,024,853 |
| I | Number of doses per vial | # | 20 | 10 | 10 | 10 | 10 |
| J | Number of re-constitution 3 syringes (+ 10% wastage) | E x 1,11 / I | 0 | 0 | 0 | 0 | 0 |
| K | Number of safety boxes (+ 10% extra need) | (H + J) x 1,11 / 100 | 17,758 | 17,038 | 18,766 | 20,578 | 22,476 |
|  | Cost of AD syringes | $ 0.110 | $175,977 | $168,844 | $185,970 | $203,922 | $222,734 |
|  | Cost of reconstitution syringes | $ 0.058 | $ - | $ - | $ - | $ - | $ - |
|  | Cost of safety boxes | $ 0.800 | $ 14,206 | $ 13,630 | $ 15,013 | $ 16,462 | $ 17,981 |
|  | Total cost for injection material |  | $190,183 | $182,475 | $200,983 | $220,384 | $240,715 |

| Table 6.3: Estimated supplies for safety of vaccination with Measles vaccine Wastage included |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
|  |  | Target coverage | 75% | 80% | 85% | 90% | 95% |
| A | Target of children for Measles vaccination | See targets in Table 4 | 480,418 | 526,795 | 575,392 | 626,296 | 679,601 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate | % | 30% | 30% | 25% | 25% | 20% |
| D | Equivalent wastage factor | 1 / (1 - C) | 1.43 | 1.43 | 1.33 | 1.33 | 1.25 |
| E | Number of Measles doses | A x B x D | 686,312 | 752,565 | 767,189 | 835,062 | 849,501 |
| F | AD syringes (+ 10% wastage) | A x B x 1,11 | 533,264 | 584,743 | 638,685 | 695,189 | 754,357 |
| G | AD syringes buffer stock 2 | F x 0,25 | 133,316 | 0 | 0 | 0 | 0 |
| H | Total AD syringes | F + G | 666,580 | 584,743 | 638,685 | 695,189 | 754,357 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| J | Number of re-constitution 3 syringes (+ 10% wastage) | E x 1,11 / I | 76,181 | 83,535 | 85,158 | 92,692 | 94,295 |
| K | Number of safety boxes (+ 10% extra need) | (H + J) x 1,11 / 100 | 8,245 | 7,418 | 8,035 | 8,745 | 9,420 |
|  | Cost of AD syringes | $ 0.110 | $ 73,324 | $ 64,322 | $ 70,255 | $ 76,471 | $ 82,979 |
|  | Cost of reconstitution syringes | $ 0.058 | $ 4,418 | $ 4,845 | $ 4,939 | $ 5,376 | $ 5,469 |
|  | Cost of safety boxes | $ 0.800 | $ 6,596 | $ 5,934 | $ 6,428 | $ 6,996 | $ 7,536 |
|  | Total cost for injection material |  | $ 84,338 | $ 75,101 | $ 81,622 | $ 88,843 | $ 95,984 |

| Table 6.4: Estimated supplies for safety of vaccination with YF vaccine Wastage included |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
|  |  | Target coverage | 50% | 60% | 70% | 80% | 90% |
| A | Target of children for DT vaccination | See targets in Table 4 | 320,279 | 395,096 | 473,852 | 556,708 | 643,832 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate | % | 30% | 30% | 25% | 25% | 20% |
| D | Equivalent wastage factor | 1 / (1 - C) | 1.43 | 1.43 | 1.33 | 1.33 | 1.25 |
| E | Number of DT doses | A x B x D | 457,541 | 564,424 | 631,803 | 742,277 | 804,791 |
| F | AD syringes (+ 10% wastage) | A x B x 1,11 | 355,509 | 438,557 | 525,976 | 617,946 | 714,654 |
| G | AD syringes buffer stock 2 | F x 0,25 | 88,877 | 0 | 0 | 0 | 0 |
| H | Total AD syringes | F + G | 444,387 | 438,557 | 525,976 | 617,946 | 714,654 |
| I | Number of doses per vial | # | 20 | 10 | 10 | 10 | 10 |
| J | Number of re-constitution 3 syringes (+ 10% wastage) | E x 1,11 / I | 25,394 | 62,651 | 70,130 | 82,393 | 89,332 |
| K | Number of safety boxes (+ 10% extra need) | (H + J) x 1,11 / 100 | 5,215 | 5,563 | 6,617 | 7,774 | 8,924 |
|  | Cost of AD syringes | $ 0.110 | $ 48,883 | $ 48,241 | $ 57,857 | $ 67,974 | $ 78,612 |
|  | Cost of reconstitution syringes | $ 0.058 | $ 1,473 | $ 3,634 | $ 4,068 | $ 4,779 | $ 5,181 |
|  | Cost of safety boxes | $ 0.800 | $ 4,172 | $ 4,451 | $ 5,293 | $ 6,219 | $ 7,139 |
|  | Total cost for injection material |  | $ 54,527 | $ 56,326 | $ 67,218 | $ 78,972 | $ 90,933 |

| Table 6.5: Estimated supplies for safety of vaccination with TT vaccine Wastage included |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
|  |  | Target coverage | 70% | 75% | 80% | 85% | 90% |
| A | Target of pregnant women for TT vaccination | See targets in Table 4 | 823,699 | 846,764 | 870,473 | 894,845 | 919,900 |
| B | Number of doses per pregnant woman | # | 2 | 2 | 2 | 2 | 2 |
| C | Estimated wastage rate | % | 30% | 30% | 25% | 25% | 20% |
| D | Equivalent wastage factor | 1 / (1 - C) | 1.43 | 1.43 | 1.33 | 1.33 | 1.25 |
| E | Number of TT doses | A x B x D | 2,353,426 | 2,419,326 | 2,321,261 | 2,386,253 | 2,299,751 |
| F | AD syringes (+ 10% wastage) | A x B x 1,11 | 1,828,612 | 1,879,816 | 1,932,450 | 1,986,556 | 2,042,179 |
| G | AD syringes buffer stock 2 | F x 0,25 | 457,153 | 0 | 0 | 0 | 0 |
| H | Total AD syringes | F + G | 2,285,765 | 1,879,816 | 1,932,450 | 1,986,556 | 2,042,179 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| J | Number of re-constitution 3 syringes (+ 10% wastage) | E x 1,11 / I | 0 | 0 | 0 | 0 | 0 |
| K | Number of safety boxes (+ 10% extra need) | (H + J) x 1,11 / 100 | 25,372 | 20,866 | 21,450 | 22,051 | 22,668 |
|  | Cost of AD syringes | $ 0.110 | $251,434 | $206,780 | $212,569 | $218,521 | $224,640 |
|  | Cost of reconstitution syringes | $ 0.058 | $ - | $ - | $ - | $ - | $ - |
|  | Cost of safety boxes | $ 0.800 | $ 20,298 | $ 16,693 | $ 17,160 | $ 17,641 | $ 18,135 |
|  | Total cost for injection material |  | $271,732 | $223,473 | $229,730 | $236,162 | $242,774 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
|  | AD syringes and waste disposal boxes |  |
|  | UNICEF | 1997 |
|  | JICA | 2001 |
|  | Government of Angola | 2007 |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes | 2004 |
| GAVI/Vaccine Fund | Assistance with funds for the construction of incinerators | 2003 |

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Angola will submit an application for new vaccines when the program achieves the require DPT3 vaccination coverage.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
|  | NA |  |  |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

Although Angola has not introduced new vaccines, the country has vast experience with logistics and vaccine management. There is continuous training of staff in the management of vaccines to ensure that vaccines are stored in the appropriate temperature. The draft five-year plan proposes decentralization of vaccine depots and distribution.

Vaccine wastage is not currently monitored, but this is now being emphasized in all training sessions and will be one of the key indicators during the next five years.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

Angola has just re-enforced its cold chain system by the procurement and distribution of new freezers and refrigerators.  The program also has developed maintenance and replacement plans (see draft 5-year plan).

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Not requesting for new vaccine at this point in time

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

N/A

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) |  |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

The Government of Angola started contributing to the purchase of vaccine and vaccination materials in 2001 and has increased the contribution progressively. The government has also assumed the responsibility of funding supervision, training and fuel for EPI activities and plans to continue.

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number 01 |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

  - Decentralization of vaccine depot which will reduce the cost of air freighting vaccine from Luanda to all provinces

  - More careful forecasting of vaccines and vaccination materials to avoid over/under forecasting

  - Training of health workers on the use of the MVP and proper interpretation of the VVM

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Angola considering that its DTP3 coverage for 2002 was 47% corresponding to 311,557 number of children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                            YES          NO

- Support for Injection Safety                                                    YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 149,389 children. Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

The Government of the Republic of Angola will take full responsibility for in-country transfer of funds.

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

Although the government of Angola will manage funds, the ICC members shall endorse all the transactions for the utilization of funds. All activities shall be discussed and endorsed by the ICC before funds are released for the activities. Several signatories will be identified in order to ensure transparency and accountability and periodic monitoring will be done and reports submitted.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :  N/A

By UNICEF                                 By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund..

SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Total supplies for safety of vaccinations with BCG, DTP, Measles, YF and TT vaccines requested to GAVI and The Vaccines Fund |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ITEM |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| Total AD syringes | for BCG | 888,773 | 748,127 | 795,594 | 863,306 | 887,479 |
|  | for Others * | 4,996,524 | 4,438,066 | 4,787,747 | 5,153,528 | 5,536,043 |
| Total of reconstitution syringes |  | 172,676 | 208,530 | 221,588 | 236,749 | 242,792 |
| Total of safety boxes |  | 67,244 | 59,881 | 64,435 | 69,415 | 73,996 |
| * with DPT for 2003 and 2004 only | Total cost | $ 711,193 | $ 630,481 | $ 492,597 | $ 527,193 | $ 557,132 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

- The ICC fully supports the proposal and is looking forward to it being   approved by the independent review committee of the GAVI secretariat

- The ICC reiterates total government commitment to ensuring improving and strengthening  EPI services in the country.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 UNICEF | Donor 2 WHO | Donor 3 Rotary | Donor 4 JICA | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV |  |  |  | 1,830,066 |  |  |  |  |  |
| 1.2 | - Other Vaccines & Vitamin A |  |  |  | 535,425 |  |  |  |  |  |
| 1.3 | - AD, S5ml, N19G & safety boxes |  |  |  | 235,248 |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold rooms & refrigerators |  |  |  | 237,875 |  |  |  |  |  |
| 2.2 | - Vaccine carriers |  |  |  | 175,728 |  |  |  |  |  |
| 2.3 | - Spare parts |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  | 177,634 |  |  |  |  |  |
| 3.2 | - Supervision, monitoring & evaluation |  |  |  | 200,807 |  |  |  |  |  |
| 3.3 | - Social mobilization |  |  |  | 416,031 |  |  |  |  |  |
| 3.4 | - Surveillance |  |  |  |  | 907,639 |  |  |  |  |
| 3.5 | - NIDs |  |  |  |  | 3,660,764 |  |  |  |  |
| Total expenditure |  |  |  |  | 3,808,817 | 4,568,403 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2001 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 UNICEF | Donor 2 WHO | Donor 3 Rotary | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV |  |  |  | 2,000,000 |  |  |  |  |  |
| 1.2 | - Other Vaccines & Vitamin A |  |  |  | 780,000 |  |  |  |  |  |
| 1.3 | - AD, S5ml, N19G & safety boxes |  |  |  | 550,000 |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold rooms & refrigerators |  |  |  | 600,000 |  |  |  |  |  |
| 2.2 | - Vaccine carriers |  |  |  | 225,000 |  |  |  |  |  |
| 2.3 | - Spare parts |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  | 150,000 |  |  |  |  |  |
| 3.2 | - Supervision, monitoring & evaluation |  |  |  | 185,000 |  |  |  |  |  |
| 3.3 | - Social mobilization |  |  |  | 450,000 |  |  |  |  |  |
| 3.4 | - Surveillance |  |  |  |  | 1,509,806 |  |  |  |  |
| 3.5 | - NIDs |  |  |  |  | 3,871,964 |  |  |  |  |
| Total commitment |  |  |  |  | 4,940,000 | 5,390,770 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 3

| Expenditure in 2002 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 UNICEF | Donor 2 WHO | Donor 3 Rotary | Donor 4 JICA | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV |  |  |  | 2,198,340 |  |  |  |  |  |
| 1.2 | - Other Vaccines & Vitamin A |  |  |  | 1,653,987 |  |  |  |  |  |
| 1.3 | - AD, S5ml, N19G & safety boxes |  |  |  | 638,562 |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold rooms & refrigerators |  |  |  | 657,471 |  |  |  |  |  |
| 2.2 | - Vaccine carriers |  |  |  | 210,925 |  |  |  |  |  |
| 2.3 | - Spare parts |  |  |  | 118,769 |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  | 373,202 |  |  |  |  |  |
| 3.2 | - Supervision, monitoring & evaluation |  |  |  | 273,145 |  |  |  |  |  |
| 3.3 | - Social mobilization |  |  |  | 739,644 |  |  |  |  |  |
| 3.4 | - Surveillance |  |  |  |  | 1,130,568 |  |  |  |  |
| 3.5 | - NIDs |  |  |  |  | 3,724,650 |  |  |  |  |
| Total expenditure |  |  |  |  | 6,864,045 | 4,855,218 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 4

| Budget for 2002 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 1 UNICEF | Donor 2 WHO | Donor 3 Rotary | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV |  |  |  | 2,500,000 |  |  |  |  |  |
| 1.2 | - Other Vaccines & Vitamin A | 573,215 |  |  | 1,500,000 |  |  |  |  |  |
| 1.3 | - AD, S5ml, N19G & safety boxes |  |  |  | 650,000 |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold rooms & refrigerators | 9,720 |  |  | 750,000 |  |  |  |  |  |
| 2.2 | - Vaccine carriers |  |  |  | 50,000 |  |  |  |  |  |
| 2.3 | - Spare parts |  |  |  | 150,000 |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  | 350,000 |  |  |  |  |  |
| 3.2 | - Supervision, monitoring & evaluation |  |  |  | 285,000 |  |  |  |  |  |
| 3.3 | - Social mobilization |  |  |  | 800,000 |  |  |  |  |  |
| 3.4 | - Surveillance |  |  |  |  | 1,687,562 |  |  |  |  |
| 3.5 | - NIDs |  |  |  |  | 3,628,071 |  |  |  |  |
| Total commitment |  |  |  |  | 7,035,000 | 5,315,633 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 5

| Budget for 2003 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 UNICEF | Donor 2 WHO | Donor 3 Rotary | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV |  |  |  | 2,500,000 |  |  |  |  |  |
| 1.2 | - Other Vaccines & Vitamin A |  |  |  | 1,500,000 |  |  |  |  |  |
| 1.3 | - AD, S5ml, N19G & safety boxes |  |  |  | 650,000 |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold rooms & refrigerators |  |  |  | 750,000 |  |  |  |  |  |
| 2.2 | - Vaccine carriers |  |  |  | 50,000 |  |  |  |  |  |
| 2.3 | - Spare parts |  |  |  | 150,000 |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training |  |  |  | 350,000 |  |  |  |  |  |
| 3.2 | - Supervision, monitoring & evaluation |  |  |  | 285,000 |  |  |  |  |  |
| 3.3 | - Social mobilization |  |  |  | 800,000 |  |  |  |  |  |
| 3.4 | - Surveillance |  |  |  |  | 1,713,606 |  |  |  |  |
| 3.5 | - NIDs |  |  |  |  | 2,960,308 |  |  |  |  |
| Total commitment |  |  |  |  | 7,035,000 | 4,673,914 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number 02. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number 03 |
| - Terms of reference of the ICC | Document number 04 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 05 (A, B & C) |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 06 & 07 & 14( MICS) |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 06 & 07 & 14( MICS) |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 11 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number N/A Document number 12 13 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number 01 |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated 20/04/03. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of .Angola . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  | Programa Alargado da Vacinação (PAV) |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
|  |  | Rua 1º Congresso, Nº 67 |  |  |  |  |  |  |  |  |
| #### City – Country: |  | Luanda – Angola |  |  |  |  |  |  |  |  |
| Telephone No.: |  | 244-2-391226 |  | Fax No.: |  |  |  | 244-2-391226 |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  | USD |
| For credit to: Bank account’s title |  | Deposit account |  |  |  |  |  |  |  |  |
| Bank account No.: |  | 728769.31.001 |  |  |  |  |  |  |  |  |
| At: Bank’s name |  | Banco de Fomento e Exterior |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES (X ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  | Ministry of Finance |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: | Dr. José Vieira Dias Van-Dúnem |  |  |  |  |  |  |  | Seal: |  |
| #### Title: | Vice Minister of Health |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Multiple Indicator Cluster Survey (MICS) 2001. National Institute of Statistics & UNICEF Angola.

Annual  Epidemiological bulletin/2002

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

Please submit hard copy documents with an identical electronic copy whenever possible