The Government of COTE D’IVOIRE

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.ch or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Signatures of the Government

The Government of ……COTE D’IVOIRE……………………………………….. commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:	……………………………………… Prof. Janine Saracino-Tagliante

Title:	Minister of Health, Cote d’Ivoire

Date:	30/6/2000

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |
| European Union |  |  |
| Worldbank |  |  |
| KFW/GTZ |  |  |
| Canadian Development Cooperation |  |  |
| French Development Cooperation |  |  |
| WHO |  |  |
| UNICEF |  |  |
| AMP |  |  |

Signed this day of : _____________/2000

In case the GAVI Secretariat have queries on this submission, please contact :

Name :  Dr SANGARE Sekou Victor	Title/Address : Directeur Executif du PEV

INSP,  BPV 47, Abidjan 01

Tel.No. :  (225) 20 22 05 33			Cell : (225) 05 04 75 14

Fax No. :  (225) 20 22 05 40

E-mail : 	depevci@africaonline.co.ci

- Immunization-related fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 16 302 025 | GNP per capita | 700 $US |
| Infants 0-11 months | 643 930 | Infant mortality rate | 112/1000 |
| Percentage of GDP allocated to Health | 1,3 % | Percentage of Government expenditure for Health Care | 8.7 % |

| Health system development status |  |
| --- | --- |
| Please find attached background documentation in French on: |  |
| - Overall government health policies and strategies Plan National de Developpement Sanitaire Tome 1 et 2 (with summary) | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services summary with original ministerial bylaw including organizational chart | Document number 2 |
| - Status of the ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies and practices on private sector participation, as it relates to immunization | Document number 4 |

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 71 | 77 | 87 |  | Diphtheria | 0 | NA | NA | NA |
| DTP3 | 64 | 60 | 70 | 61 | Pertussis | NA | NA | NA | NA |
| OPV3 | 64 | 60 | 70 | 61 | Polio | 13 | 9 | NA | NA |
| Measles | 66 | 59 | 63 | 66 | Measles | 12 289 | 4 824 | NA | NA |
| TT2+ Pregnant Women | 49 | 69 | 70 |  | NN Tetanus | 95 | 83 | NA | NA |
| Hib | SO | S0 | SO |  | Hib | NA | NA | NA | NA |
| Yellow Fever | 57 | 50 | 65 |  | Yellow fever | 0 | 1* | NA | NA |
| HepB | S0 | ~ | SO |  | HepB seroprevalence (if available) | 9%** | 9% | NA | NA |

# *   A tourist was the only case of Yellow fever

# ** seroprevalence of Hepatitis B in blooddonors

# Profile of the Inter Agency Coordinating Committee (ICC)

(Various agencies and partners supporting immunization services in the country are coordinated and organized through an inter-agency coordinating mechanism, which is referred to in this document as ICC)

- Name of the ICC :  ‘Groupe Thematique PEV’,

- Date of constitution of the current ICC :   June 2000. The predecessor of the current ICC was the Interagency Coordination Committee for the Polio-eradication, which was functional since October 1996 (see Document 5). In June 2000, the Minister of Health has decided to extend its mandate from solely Polio-eradication to the comprehensive field of EPI and place it directly in her cabinet.

- Organizational structure: subcommittee of the ‘Comite de Suivi de PNDS’, which is located in the Ministry of Health, in the ‘Secretariat Technique Permanent du PNDS’. (see Document 6)

- Frequency of meetings : 4 times per year

- Composition: Since the committee has recently changed its mandate, the composition and the terms of references are not yet fully defined, or adopted. However, the committee is already functional on an unofficial basis, with approval of the Minister of Health.

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Ministry of Health |  |
| Secretary | DE-PEV (National EPI-Services) | Dr S.V. Sangare |
| Members | - INHP - INSP - PSP - IPCI - DIEM - DEPS - DAF - DIPE - DSC - Directeur Regional de la Sante ( 1) - Directeur Departemental de la Sante (1) - Ministere de l’Economie et des Finances - Ministere de l’Interieur et de la Decentralisation - Representatives of the Development Agencies (bi- & multilateral) | Institut National d’Hygiene Publique Institut National de la Sante Publique Pharmacie de la Sante Publique Institut Pasteur de Cote d’Ivoire Direction des Infrastructures, de l’Equipement et de la Maintenance Direction des Etablissement et de Personnel de Sante Direction Administrative et Financiere Direction de l’Information, de la Planification et des Etudes Direction de Sante Communautaire |

- Major functions and responsibilities :

- Defining the Immunization policies and strategies - Assuring sustainability of the EPI services through efficient resource mobilization (internal & external) - Review and endorse the national plans of action with the budgets, and monitoring the EPI-implementation countrywide, advising on corrective actions. - Advising on operational research, other studies and evaluations of the EPI services

- The following diagram shows the ICC functional relationships with other institutions in health sector :

Ministere de la Sante Directeur de Cabinet Secretariat Technique Permanent de PNDS Groupe Thematique PEV Autres groupes

Find attached the following documents:

| - Proposed terms of reference of the ICC ‘Groupe Thematique PEV’ | Document number 7 |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings in which partners participated that concerned improving and expanding the national immunization program | Not available |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Enquete Demographique et de Sante 1994, Document 8 | DHS, Institut Nationale de la Statistique (INS) | Dec. 1995 |
| Enquete National d’Evaluation de la Couverture Vaccinale 1998, Document 9 | Ministere de la Sante Publique, DE-PEV | Oct. 1998 |
| Enquete Demographique et de Sante, Cote d’Ivoire1998/99, Document 10 | DHS, MACRO Int., Ministere de la Planification et de la Programmation du Developpement, INS | May 1999 |
| Case Study on the Costs and Financing of the Immunization Services in Cote d’Ivoire, Document 11 | PHR, USAID, WHO, Gouv. de Cote d’Ivoire | May 2000 |

- The following are the three major problems identified in the assessments :

- In the EDS 1998/99, an significant improvement of the EPI-coverage is noted: - DPT 3 1998/99 61 % compared to DPT 3 1994 51 %) - Fully vaccinated children in 1998/99 51 % compared to 41 % in 1994 However, both surveys state a significant difference between the immunization coverage in urban areas compared to those in rural areas. - Findings from the National Immunization Coverage survey 1998: 9 % of the children are not reached by the routine EPI services, high dropout rate national average 18 % (range 5% - 54%). Concerning services delivery: missed vaccinations-opportunities, in 13 % the Yellow fever is not administered simultaneously with Measles. In Abidjan, 12 % of the children received invalid dosages for DTP 3 and 11 % received invalid dosages of the measles vaccine. - Findings of the Case Study on Costs & Financing: - Financing strategy is heavily dependent on the EU & other donors and is not sustainable over the long term. This dependency might have relaxed the pressure on the efficient use of the resources. - Need for information exists concerning: the disease burden (regular disease surveillance and reporting), an inventory on cold chain equipment and its condition to determine maintenance and replacement needs, cost-effectiveness data on different strategies to improve immunization coverage.

- The following are the three major recommendations in the assessments :

- To address the inequity of the EPI-services between the urban and the rural areas by strengthening the outreach services and mobile strategies - To develop an IEC strategy adapted to the target groups (ex. illiterate women) - To strengthen supervision and in-service training on EPI technical issues and managerial topics - To create sustainable long-term financing for the immunization program, especially for the operational costs, by both increasing central government budget allocations through the operating budget and tapping into other local sources, such as insurance, local government and community contributions. - To develop a national immunization strategic multi-year plan including program objectives maintaining & improving the current coverage rates and introducing new vaccines and other innovative strategies (ex. auto-destruct syringes). The plan should include also: capacity building in critical areas, addressing financing and maintenance issues, planning for operational research on national and district level - To develop a detailed annual EPI-planning on the district levels facilitating monitoring. - To assess the vaccine-procurement process and to improve the vaccine-stock management.

- Find attached a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number 8,9,10 & 11 |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in workplan, implemented, not implemented, in progress…. | Document number 12 |

- The following components or areas of immunization services are yet to be reviewed (or studied). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |
| Burden of Disease assessment Hepatitis B | 2001 | Funded by AMP |
| Entomological & Serologic Surveys for all vaccine-preventable diseases | 2001-2005 | 850,000 over 5 years |
| Burden of Disease assessment Haemophilus influenza | 2002 | 30,000 |
| Detailed cost-assessment on district level | 2003 | n.a. |
| National EPI assessment (WHO) | 2003 | 85.000 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 13 |
| --- | --- |

- As per 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 361,942 |
| Used doses of DTP | 460,000 |

- Estimated annual targets

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Children planned to be vaccinated with DTP3 | 647,686 | 669,060 | 691,139 | 713,947 | 737,507 | 761,845 |
| Doses of DTP planned to be used | 1,833,300 | 1,497,800 | 552,500 | - | - | - |

Note: the phasing-out of the DPT-doses is due to the gradual introduction of the combo-DTP-Hb.

# New and under-used vaccines

Find below a summary of those aspects of the plan, mentioned in section five that refer to introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Pneumopathy | Prise en charge de Pleurisie de l’enfant en reanimation, Abidjan (42 cas) These medicale de S. Konate | 1994 | Haemophilus 10 % |
| Meningitis | Meningite a Haemophilus Influenzae chez l’ enfant a Abidjan, (886 cas de 1990-1994) Bissagnegne et coll. Med. D’ Afrique Noire 1996, 43 (10) | 1996 | Haemophilus 36 % (89% serotype b) Pneumococ 38 % |
| Meningitis | Profile actuelle de meningite purulente de l’enfant au CHU de Yopougon de 1993-1995, (101 cas) These medicale de P.D. N’zue 1998 | 1998 | Haemophilus 24 % |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of monovalent vaccine :

Not Applicable

- Planning for hepB vaccinations : Note: DPT-Hb requested

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 345,602 | 483,797 | 713,947 | 737,507 | 761,845 |
| Total vaccine doses required | 946,400 | 1,905,500 | 2,535,600 | 2,752,900 | 2,864,300 |
| Preferred vial size(s) | 10 D | 10 D | 10 D | 10 D | 10 D |
| Estimated wastage rate | 25 % | 25 % | 25 % | 25 % | 25 % |
| % of vaccines requested from the Fund | 41 % | 71 % | 78 % | 80 % | 81 % |
| AD syringes * | 5,762,100 | 7,201,100 | 6,189,400 | 6,764,600 | 7,008,500 |

* The AD-syringes are requested not only for the DTP-Hb, but for all vaccines except for BCG.

- Planning for Hib vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | - | - | 713,947 | 737,507 | 761,845 |
| Total vaccine doses required | - | - | 2,535,600 | 2,752,900 | 2,864,300 |
| Preferred vial size(s) |  |  | 10 D | 10 D | 10 D |
| Estimated wastage rate |  |  | 25 % | 25 % | 25 % |
| % of vaccines requested from the Fund |  |  | 78 % | 80 % | 81 % |
| AD syringes |  |  | 6,189,400 | 6,764,600 | 7,008,500 |

- Planning for yellow fever vaccinations: not applic., Yellow Fever incorporated in the routine EPI 1983

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

| - Find attached the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number 13 Included in the multi-years plan of action |
| --- | --- |

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each line item and for each year are attached in Annex 1. | Document not available |
| --- | --- |

- Find below a list of financial sustainability strategies and of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative). The information is obtained from the Director of the National EPI services, for detailed information contact him.

(USD ,000)

| Strategy title / Line item | Partner1 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel | Gov. | 5,130,535 |  |  |  |  |  |  |  |
| Vaccines & Supplies | EU budget-aid | 1,869,000 | 1,953,183 | 1,953,183 |  |  |  |  |  |
| Transport | Gov. | 130,800 |  |  |  |  |  |  |  |
| Maintenance/Overhead | Gov. | 100,000 |  |  |  |  |  |  |  |
| Measles control | UNICEF |  | 200,000 |  |  |  |  |  |  |
| Support to GAVI-initiative | UNICEF |  |  | 150,000 |  |  |  |  |  |
| Elimination of Neonatal Tetanus | UNICEF |  |  | 250,000 | 250,000 |  |  |  |  |
| Yellow control | WHO |  |  | 152,050 | 173,370 |  |  |  |  |
| Surveillance, with focus on Polio | WHO | 90,000 | 86,000 | ? |  |  |  |  |  |
| Polio NIDs | WHO /Rotary | 300,000 | 350,000 | ? |  |  |  |  |  |
|  | Japanese Gov. /UNICEF | 1,167,000 | 950,000 |  |  |  |  |  |  |
|  | Rotary Nat |  | 50,000 |  |  |  |  |  |  |
| Cold chain and logistics investments | UNICEF | 37,000 | 11,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 |
|  | JICA | 265,020 |  |  |  |  |  |  |  |
|  | KFW |  | 5,000,000 |  |  |  |  |  |  |

| - We summarize hereunder the support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached. | Document not available |
| --- | --- |

The PNDS is an integrated part of the plan of action in the Fight against Poverty, which was adopted by the Government in 1998. Unfortunately, the implementation of the PNDS is confronted with serious delays, and in the current election year, the focus of the government is more oriented toward the political arena rather to social policies. Due to the political circumstances, the negotiations concerning the debt relief are not pursued as before, but will be resume as soon as the results of the General Elections are known. In these discussions, investments in the EPI-services will be taken into account, since the EPI is a priority program in the plan of action against Poverty as an important preventive program executed by the Ministry of Health, one of the basic social services of Cote d’Ivoire.

# Preferred channel of funds

(Only for countries seeking support from the immunization services sub-account)

- From the immunization services sub-account, funds will be transferred to the country through the following channel or system (tick only one) :

| Directly to the Government |  | Through a partner agency |  | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the following box we describe how the mechanism will operate and how it will address transparency, standards of accounting, long-term sustainability and empowerment of the government.

The details of the fund disbursement mechanisms are not yet finalized. The Government would like to create a separate budget-line for the GAVI-funds on the account of the INHP to integrate the increased expenditures for the EPI-services in the national budget straight from the beginning. It would like to handle the GAVI- funds in a similar way as the financing of the routine vaccines with the budget-assistance of the European Union. However, it would simultaneously welcome an involvement of UNICEF to enhance financial transparency. This issue requires further consultation between the Government, ICC partners, UNICEF Abidjan and UNICEF Headquarters-New York.

# Country concerns

The following are the ICC’s concerns and recommendations while submitting this proposal :

Cote d’Ivoire is currently undergoing a critical period of Government transition, which puts the basic social services in a difficult position to mobilize internal resources. The EPI services, which request substantial financing, are especially in a vulnerable position. In the recent past the EPI-services of Cote d’Ivoire have shown remarkable achievements in improving their performance, increasing the DTP 3 coverage from 41 % in 1995 to 70 % in 1997. This achievement was mainly obtained through an improved supervision and management by the central level, even before the major investments in the cold chain and logistics had taken place. At this point in time it is imperative to sustain the good performance of the EPI-services and to avoid putting the children in Cote d’Ivoire at risk for preventable diseases. Thus, the Government of Cote d’Ivoire takes the opportunity to request the GAVI-funding on the sub-account Immunization services to reinforce capacity of the EPI-service to face the challenge of improving immunization coverage under difficult circumstances. Since the first step in introducing new vaccines in the routine EPI has already been undertaken (introduction of Hepatitis B vaccination in the capital, 20% of total target-group), the Ministry of Health has decided to continue this effort. Therefore, it appeals to GAVI for funding the gradual extension of the Hepatitis immunization nation-wide over the 3 years period. Secondly, the multi-years plan projects an introduction of the Hib-immunization in 2004. The political commitment to universal immunization exists on all levels of the Government, and with the debt-relief foreseen in the near future, it is important to assist the Ministry of Health now to reinforce the EPI-services’ capacity with a financial and technical assistance. The partners in development are strongly supportive to this renewed EPI-initiative and are willing to take part in the planning and implementation, as the active participation in the planning-workshop (June 2000) and the various contributions to this proposal have shown.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Government | Local Government | Private sector AXA | JICA & UNICEF | KFW | USAID/WHO | Total Expenditure in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |
| 1.1 | - Line item Routine Vaccines | 2,222,222 |  |  |  |  |  | 2,222,222 |
| 1.2 | - Line item OPV |  |  |  | 750,376 |  |  | 750,376 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |
| 2.1 | - Line item Cold Chain & logistics |  |  |  |  | 5,500,000 |  | 5,500,000 |
| 2.2 | - Line item n… |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |
| 3.1 | - Line item Polio operational cost | 281,749 |  | 32,593 | 78,518 |  | 311,112 | 703,972 |
| 3.2 | - Line item n… |  |  |  |  |  |  |  |
| Total expenditure in 1999 |  |  |  |  |  |  |  |  |

Table 2

| Budget for 1999 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USD | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | UNICEF | WHO | Others | Donor n.. 2 |  |  |
| 0. | Operational Costs (Salaries EPI central level, maintenance of duty-vehicles etc.) | 50,4000 |  |  |  |  |  |  | 50,400 |  |
| 1. | Vaccines, AD syringes… (EU) |  |  |  |  |  |  |  |  |  |
| 1.1 | Line item Routine Vaccines | 2,222,222 |  |  |  |  |  |  |  |  |
| 1.2 | Line item OPV |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item n… |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Social Mobilization/IEC | 99,260 |  |  | 18,000 |  | 12,000 |  | 129,000 |  |
| 3.2 | - Training | 26,000 |  |  | 7,400 | 18,000 |  |  | 50,400 |  |
| 3.3 | - Studies & Evaluation | 59,000 |  |  |  |  |  |  | 59,000 |  |
| 3.4 | - Monitoring & Surveillance | 296,300 |  |  | 29,600 | 220,000 |  |  | 561,000 |  |
| 3.4 | - Logistics | 49,500 |  |  |  |  |  |  | 49,500 |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number 2 |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies on private sector participation, as it relates to Immunization. | Document number 4 |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC for Polio eradication - Terms of reference of the Secretariat Technique Permanent du PNDS - Terms of reference of the ICC –Groupe Thematique sur le PEV- | Document number 5 Document number 6 Document number 7 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Not available |
| Immunization Services Assessment |  |
| - Enquete Demographique et de Sante, Cote d’Ivoire 1994 - Enquete National d’Evaluation de la Couverture Vaccinale 1998 - Enquete Demographique et de Sante, Cote d’Ivoire1998/99 - Case Study on the Costs and Financing of the Immunization Services in Cote d’Ivoire | Document number 8 Document number 9 Document number 10 Document number 11 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number 12 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 13 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | Document number 13 Included in Multi-year plan |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number…… |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Not available |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Not available |

Please submit hard copy documents with an additional electronic copy wherever possible