The Government of

Lesotho

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Government of the Kingdom of Lesotho places great importance in the provision of sound health care services to its population. The high immunization coverage registered in the early 90s was a result of government’s commitment in financial and technical resources towards improving the welfare of the children of Lesotho. The AIDs scourge, rising poverty and unemployment have however  over-stretched the limited resources meant for the health care delivery system.

The reduction of vaccine-preventable diseases such as measles and neonatal tetanus since the inception of EPI in the country is a clear testimony of the importance to strengthen the immunization activities. It is on this background that the government  with its collaborating partners are asking for support in three areas namely, new vaccines, safe injection and strengthening of immunization services. The  DPT coverage of 56% for 2000, which represented 36,062 children, reflected a decline. Efforts have been made to improve on management, capacity building, advocacy at all levels, communication, education  and information for immunization and logistics support inorder to reverse the decline in the immunization coverage.

The country has aimed to vaccinate at least 65% of the target  population of under one year in the year 2002  with new vaccines that translates into 43,549 children. The first preference for the country is use of a combination pentavalent  DPT-HepB+Hib (2 dose vial) vaccine. Initially a total of 171,474 doses will be required and followed with 150,932 doses in the second year. In addition to introduction of new vaccines, the country has planned to introduce autodisable syringes in its routine immunization services. Assistance with A-D syringes and safety boxes will, therefore, improve safe injection practices.

The ICC has been very instrumental in the preparation of this GAVI Application. This is a clear demonstration of their full support for the introduction of new vaccines, improvements in injection safety and in the global immunization coverage in the country.

# Signatures of the Government

The Government of Lesotho commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Health Services Area (Health Districts) performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : ……………………………	Title/Address : ……………………………….

Tel.No. : ………………………….   		            ………………………………..

Fax No. :………………………….. 		            ………………………………..

E-mail :……………………………                         ……………………………….

Alternative address :

Name : ……………………………	Title/Address : ……………………………….

Tel.No. : ………………………….   		            ………………………………..

Fax No. :………………………….. 		            ………………………………..

E-mail :……………………………                         ……………………………….

- Immunization-related fact sheet

| Table 1 : Basic facts (For the year 2000 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 2,144,146** | GNP per capita | US$680 |
| Surviving Infants* | 64,324 | Infant mortality rate | 74/ 1000LB |
| Percentage of GDP allocated to Health | 3.2 | Percentage of Government expenditure for Health Care | 7% (2001-2002) |

* Surviving infants = Infants surviving the first 12 months of life

** Source : National Bureau of Statistics, Lesotho

| Table 2: Trends of immunization coverage and disease burden by 12 months of age as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage ( in percentage ) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 1999 | 2000 | 1999 | Age group | 2000 | Age group |  | 1999 | 2000 |
| BCG |  |  | 68 | 53 | NA | NA | NA | NA | Tuberculosis | 63 | 128 |
| DTP | DTP1 |  | 55 | 58 | NA | NA | NA | NA | Diphtheria | 0 | 0 |
|  | DTP3 |  | 62 | 56 | NA | NA | NA | NA | Pertussis | 0 | 0 |
| OPV3 |  |  | 60 | 56 | NA | NA | NA | NA | Polio | 0 | 0 |
| Measles |  |  | 63 | 48 | NA | NA | NA | NA | Measles | 248 | 660 |
| Hib3 |  |  | NA | NA | NA | NA | NA | NA | Hib | NA | NA |
| Yellow Fever |  |  | NA | NA | NA | NA | NA | NA | Yellow fever | NA | NA |
| HepB3 |  |  | NA | NA | NA | NA | NA | NA | hepB seroprevalence (if available) | NA | NA |
| Vit A supplementation |  | Mothers ( < 6 weeks from delivery ) | NA | NA | NA | NA | NA | NA |  |  |  |
|  |  | Infants ( > 6 months) | NA | 34 | NA | NA | NA | NA |  |  |  |

The best official estimate: Indicate the best official estimates of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are best estimate: Immunization data from all the Health Services Areas (HSAs) are aggregated at national level and coverage is calculated against the target population of under one year projected by the National Bureau of Statistics of Lesotho. The decline in immunization as observed during the review meeting was mainly due to inadequate managerial capability, advocacy and logistics support. Communication services were also poor

Summary of health system development status relevant to immunization

The Government  of Lesotho is in the process of restructuring  its health sector in order to meet the multiple challenges faced by the country. The vision of the reform is to achieve the following:

- Universal coverage so that every citizen has access to essential health services

- Social justice so that those in greatest need will receive particular attention and

- Equity so that every person, no matter the social standing, will receive the same treatment, with the only determining factor being their need for services

The emphasis will be on prevention and eradication of priority diseases especially those that are amenable to cost effective approaches such as immunization of  women and children . The short-to-medium term priorities include:

- Reducing infant morbidity and mortality rates

- Reducing  maternal mortality  through the promotion of safe motherhood, within a comprehensive reproductive health context

- Eradicating and eliminating EPI priority diseases namely poliomyelitis, Neonatal Tetanus and Measles by the year 2005

The Ministry of Health and Social Welfare is committed to addressing  the challenges observed in the EPI review. Through its collaborating partners and donors, most of the health facilities have been provided with  working refrigerators in order to keep vaccines safe and potent. The government  has for the first time procured BCG vaccine for the year 2001 as an indication of  supporting the vaccine independence initiative. Although there is critical shortage of health personnel,  each health centre is staffed by at least a registered nurse and/or  a nursing assistant  who are supposed to conduct outreach services in order to increase immunization coverage.  Capacity building will be strengthened at all levels in order to improve the knowledge and skills of health workers in order to cope  with the present challenges, policies and innovations.

Non-Governmental Organizations (NGOs) in Lesotho collaborate with the Ministry of Health and Social Welfare in the provision of health services. The Christian Health Association of Lesotho (CHAL), Lesotho Highlands Development  Authority (LHDA), Red Cross, Maseru City Council etc  have actively been involved in immunization  including information, education and communication. Some NGOs are members of the ICC.

| - Attached are the relevant section(s) of strategies for health system development | Document number: 01 |
| --- | --- |

Attached sections of the health sector reform document reflect some of the strategies on the development of the health sector in the country. Key issues are:

- Decentralization policy

- Introduction of multi-sectoral approach to the provision of health services

- Introduction of the Health Service Area strategy (HSA)

- Introduction of the Nurse Clinician cadre

- Introduction of the Community Health Worker programme

- District Management  Improvement  Project

- Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services, are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC : 			Lesotho

- Date of constitution of the current ICC: 1996

- Organisational structure (e.g., sub-committee, stand alone)  The chairperson for the ICC is the honourable Minister of Health and Social Welfare. The committee has several sub-committees such as:

- Technical Committee

- Social Mobilization Committee

These committees are mandated to conduct certain activities that are planned by the main committee.

- Frequency of meetings  : The ICC is mandated to meet every three months. However, extra-ordinary meetings are called for by the chairperson whenever there is an urgent issue to be discussed by all members

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister of Health and Social Welfare | Dr P. Sekatle |
| Secretary | National EPI Programme Manager | Mrs A. Petlane |
| Members | - Director General of Health Services - WHO Representative - UNICEF Representative - Chairperson, Rotary International - Health Programme Advisor, Ireland AID - Epidemiologist, MOH and SW - Head, PHC Services ,CHAL - Director, Maseru City Council - Head, Laboratory Services - Paediatrician, Parastatal | Dr T. Ramatlapeng Dr T.R. Tshabalala Mrs K. Gamble-Payne Dr A.D. Lebona Dr K.L.M. Lerotholi Dr Oo Mrs Fegurson Mr Thamae Mr Tlali Dr Metsing |

- Major functions and responsibilities of the ICC:

- Coordination: The ICC coordinates all partners with a view to fostering a strong partnership which will facilitate sharing of resources and technical input and which will ultimately lead to maximum utilization of available resources.

- Advocacy: The committee advocates for EPI at higher political level in the country and internationally to maintain the status quo the programme  used to have when it was established

- Programme Implementation: The ICC  reviews and endorses EPI Plans and supports the EPI programme by mobilizing resources both locally and internationally. It is also responsible for ensuring that it supports the operationalization of the current technical issues

- Social mobilization: One of the critical tasks of the ICC is to support programmes with social mobilization to ensure wide publicity of the programmes

- Transparency and accountability: Since the ICC will mobilize resources for EPI, the committee will be obliged to review and monitor the use of funds and other resources together with the EPI Unit and give continuous feedback to the donors and communities as need arises.

- Information, Education and Communication: The ICC will ensure support  for IEC  activities.

- Three major strategies to enhance ICC’s role and functions in the next 12 months

- Ensuring that quarterly meetings with all ICC members are conducted as planned. The minutes and agenda are circulated to members in time

- Ensuring that the terms of reference for the  ICC are clear and responsibilities explicitly outlined.

- Ensuring that the  ICC is periodically briefed about immunization and disease surveillance activities in order  to enlist their support  at all levels.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- The drop-out rate: as a sign of improvement in the immunization services, the ICC will also look at the reduction of drop- out rate in multidose antigens

- The ICC will monitor immunization coverage by Health Service Areas (HSAs)

- Wastage Rate: The committee will emphasize the need to reduce  vaccine wastage rate which is at the moment above 30%

Attached are the supporting documents :

| - ICC’s workplan of the next 12 months | Document number: 02 |
| --- | --- |
| - Terms of reference of the ICC | Document number: 03 |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number: 04 |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Review of the Expanded Programme on Immunization in the Kingdom of Lesotho | - Ministry of Health and Social Welfare - WHO (Afro) - WHO (Lesotho) - UNICEF (Lesotho) - Department of Health (South Africa) | July, 2001 |

- The three major strengths identified in the assessments :

- Cold Chain: Most of the health facilities visited had  working EPI refrigerators with thermometers in good condition. The review also did not  find any frozen DPT.The VVM on all OPV vials did not reach a discard point

- Clinical Practices: Screening of children through the ‘road to health card’ was done in most facilities by health workers. Health talks were given by health workers before vaccinations were administered to clients

- Vaccination Coverage and Disease Surveillance: Health workers in most health facilities collected and compiled vaccination statistics which were normally sent to Health Services Area (HSAs) and the central EPI Office.  AFP and Measles case-based surveillance was instituted. In the year 2000, Lesotho reported 9 cases of AFP instead of the targeted 10 although only 4 had specimens collected within the recommended first 14 days of onset of paralysis

- The three major problems identified in the assessments :

- Transport  for distribution of vaccines, other EPI logistics and supervision was highly cited. The National EPI Office does not  distribute vaccines to health facilities. Health Services Areas collect vaccines from the national vaccine storeroom using their own transport which sometimes is not available. This results in vaccine stock outs in health facilities.

- Inadequate knowledge and skills of health workers in the management of EPI. Calculation of  vaccine wastage was not being done by most health workers. The majority of health workers did not know the EPI  policies on multidose vial, the use and interpretation of VVM, AEFI , safe injection etc.

- Inadequate advocacy and communication on immunization activities. Social mobilization is inadequate and most health facilities have shortage of publicity materials or have outdated materials. Other communication channels apart from leaflets and posters are not utilized.

- The three major recommendations in the assessments :

- Improvement on the availability and use of transport at national  and HSA levels. This will improve distribution of vaccines, supportive supervisory visits to HSAs and other health facilities.

- Improvement of health workers knowledge and skills in the management of EPI. The training should cover such areas as current policies and guidelines on the use of  multidose vial vaccine, the use and interpretation of the VVM and Cold Chain Monitor, management of vaccines and the calculation of immunization coverage, vaccine wastage and drop-out rate. The  present disease surveillance procedures will also be better understood.

- Information, Education and Communication should be intensified by addressing pertinent areas which are negatively affecting the immunization activities. Promotional materials both visual and audiovisual should be developed according to the needs of the target groups of the community

- Attached are  complete copies (with an executive summary) of :

| - the most recent assessment reports on the status of immunization services | Document number: 05 |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number: 06 |

| Recommendations | Implemented | Not implemented | In Progress | Remarks |
| --- | --- | --- | --- | --- |
| 1. Revision of EPI Policy |  |  |  | To be circulated nationally for peer review |
| 2. Conducting supportive supervisory visits |  |  |  | This will be enhanced by procurement of transport for all 18 HSAs by 2001 |
| 3. Use of refrigerated vehicle for distribution of vaccines and other supplies to HSAs |  |  |  | The system of national EPI Office to deliver vaccine to HSAs will be strengthened |
| 4.Training of Health Workers in EPI Management |  |  |  | Some of the training sessions will start in October ,2001. The trainings will continue up to 2005 |
| 5.Use of village registers to trace defaulters and thereby increase coverage |  |  |  | This practice be strengthened in villages over a period of time |
| 6. Advocacy and Communication for immunization |  |  |  | The health education section is in the process of revising some of the promotion materials. When the proposal will be approved, it is going to revise all the materials so that the new vaccines are incorporated. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Title of the assessment | Month/Year |
| --- | --- |
| The WHO 30 Cluster EPI Survey | March, 2002 |

# 6.	Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

The EPI Multi Year Plan of Action was developed in August, 2001 and was discussed and accepted by all members of the ICC

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number: 07 |
| --- | --- |

The Five Year Plan of Action for the Kingdom of Lesotho is attached to this proposal.

| - Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which Agency |
| - Implementation of the 5 year plan of action and yearly plan of actions | 5 years | MOH &SW, LHDA, Ireland AID, Rotary International, CHAL, WHO, UNICEF |
| - Procurement of vaccines and other EPI supplies | 5 years | GAVI Government of Lesotho(GOL), Ireland AID, Rotary International, JICA, UNICEF ICC |
| - Procurement of transport | 2 years | Collaborating partners and donors such as WHO,UNICEF, Rotary, JICA, Ireland AID ICC Government of Lesotho |
| - Training of health workers | 3 years in phases | Collaborating partners and donors such as GOL, WHO, UNICEF, Ireland AID ICC |
| - Development of promotional materials | 5 | Collaborating partners and donors ICC GOL |
| - EPI Evaluation | 1 year in 2002 | External consultants -Internal staff -Collaborating partners and donors such as: WHO, UNICEF, Ireland AID, Rotary, GOL ICC |

| Table 3 : Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth or first contact until the age of 1 year | x |  |  |
| DPT | 6, 10, 14 weeks | x |  |  |
| DT | 18 months | x |  | Booster dose |
| OPV | Birth, 6, 10, 14 weeks | x |  |  |
| Measles | 9 , 18 months | x |  | second dose given at 18 months |
| TT (pregnant Women) | First contact, 4 weeks, 6 months, 1 year, 1 year | x |  | A policy of vaccinating all women of child bearing age with TT is not in place |
| Vitamin A | -Every 6 months from 6-59 months for children | x |  | It is not the policy of GOL to supplement postnatal mothers with Vit A . Vitamin A supplementation to children started in the year 2000 |

- Summary of major action points and timeframe for improving immunization coverage

| Major Action Points | Responsible Office | Timeframe |
| --- | --- | --- |
| i) Training of health workers and supervisors in midlevel management that shall include among others immunization coverage and disease surveillance, data analysis, calculation of vaccine wastage and drop-out rates, vaccine management etc. | -MOH&SW -ICC | From 2002 to 2005 |
| ii) Procurement of vehicles for EPI programme for supervision, collection and distribution of logistics and, disease surveillance activities | -ICC -Donors | 2002 |
| iii) Implementation of the new EPI policies such as the MDVP, use and interpretation of VVM and Cold Chain Monitors, AEFIs, Safe injection and waste management. | -MOH&SW -ICC | By 2002 |
| iv) Strengthening advocacy and communication | -MOH&SW | by 2002 |

| Table 4 : Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of |  | Baseline | Targets |  |  |  |  |  |  |  |
|  |  | 2000 | 2001 (60%) | 2002 (65%) |  | 2003 (70%) | 2004 (75%) | 2005 (80%) | 2006 (85%) | 2007 (90%) |
| Births |  | 69083 | 70525 | 71956 |  | 73515 | 75196 | 76700 | 78234 | 79799 |
| Infants’ deaths |  | 5112 | 5219 | 5328 |  | 5440 | 5565 | 5676 | 5789 | 5905 |
| Surviving infants |  | 64324 | 65666 | 66998 |  | 68450 | 70015 | 71416 | 72844 | 74301 |
| Children vaccinated with BCG* |  | 34174 | 42315 | 46771 |  | 51461 | 56397 | 61360 | 66499 | 71819 |
| Children vaccinated with OPV3** |  | 36293 | 39400 | 43549 |  | 47915 | 52511 | 57133 | 61917 | 66871 |
| Children vaccinated with DTP3** |  | 36062 | 39400 | 43549 |  | 47915 | 52511 | 57133 | 61917 | 66871 |
| Children vaccinated with**: (use one row for any new vaccine) |  | NA | NA | 43549 |  | 47915 | 52511 | 57133 | 61917 | 66871 |
| Children vaccinated with Measles** |  | 30970 | 39400 | 43549 |  | 47915 | 52511 | 57133 | 61917 | 66871 |
| Pregnant women vaccinated with TT+ |  | 27956 | 39400 | 43549 |  | 47915 | 52511 | 57133 | 61917 | 66871 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | NA | NA | NA |  | NA | NA | NA | NA | NA |
|  | Infants (> 6 months) | 43930 | 39400 | 43549 |  | 47915 | 52511 | 57133 | 61917 | 66871 |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

- Summary of the major action points and timeframe for reduction of vaccines wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate.

- Careful planning of the estimates and distribution of the new and routine vaccines

- Improved management of the cold chain

- Implementation of the revised WHO policy on the use of opened multi-dose vials of vaccine in subsequent sessions

- Training on the use and interpretation of the vaccine vial monitor (VVM) as a management tool for OPV and other vaccines that may have VVMs

- Introduction of the new combination DTP-HepB + Hib vaccine in a two-dose presentation.

- Improving vaccine stock management at all levels

- Reducing missed opportunities for vaccination of eligible children and pregnant mothers

| Table 5 : Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual | Targets |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate | 35 | 30 | 25 | 20 | 15 | 15 | 15 | 15 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |

- Planning and constraints for Polio Eradication Initiative:

- Successful NIDs held in 1997 for polio eradication

- Target of detecting at least 1 AFP case in 100,000 population of <15 years was met in 2000

- As at 31st  August, 2001,  8 out of 10 expected AFP cases had been detected

- Two members have been elected to serve on the National Certification Committee formed in the Republic of South Africa and which includes Swaziland, Lesotho and South Africa.

- Collection of two stool specimens within the first 14 days is currently the biggest challenge faced.  However, efforts to improve on quality of surveillance have been put in place in order to reach the 80% target.

# 7.   Injection safety

7.1 Summary of the injection safety strategy for immunization (for all countries)

- Introduction of auto-disable syringes into the routine immunization services

- Introduction of approved, standardised safety boxes into the EPI programme, with the government of Lesotho purchasing additional supplies to cover injection administration throughout the health services

- Assessment of storage space needed for new, unused and filled sharps boxes.

- Collaboration with Environmental Health Section to ensure correct waste management policies are implemented.

- Introduce a needle-stick policy for the management and/or treatment of accidental needle prick injuries

- Improve injection practices through careful handling of syringes and needles at each stage of injection administration.

- Ensure that vaccines that contain no preservatives are destroyed at the end of a session, and not stored for reuse.

- Use the Best Practical Environment Option (BPEO) for the destruction of all safety boxes and other clinic waste.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. Copy Annexed and also the multi year plan of Action on page 17 outlines the introduction of A-D syringes. | Document number: 08 |
| --- | --- |

  - Injection Safety equipment (for countries submitting a request for injection safety support)

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for BCG vaccination | Match with targets in table 4 | 46771 | 51461 | 56397 | 61360 |
| B | Number of doses per child | 1 | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 46771 | 51461 | 56397 | 61360 |
| D | AD syringes (+10% wastage) | C x 1.11 | 51916 | 57122 | 62601 | 68110 |
| E | AD syringes buffer stock | D x 0.25 | 12979 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 64895 | 57122 | 62601 | 68110 |
| G | Number of doses per vial | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 2596 | 2856 | 3130 | 3405 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 749 | 668 | 730 | 794 |

| Table 6.2: Estimated supplies for safety of vaccination with DT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for DT vaccination | Match with targets in table 4 | 43549 | 47915 | 52511 | 57133 |
| B | Number of doses per child | 1 | 1 | 1 | 1 | 1 |
| C | Number o DT doses | A x B | 43549 | 47915 | 52511 | 57133 |
| D | AD syringes (+10% wastage) | C x 1.11 | 48340 | 53186 | 58287 | 63418 |
| E | AD syringes buffer stock | D x 0.25 | 1209 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 49549 | 53186 | 58287 | 63418 |
| G | Number of doses per vial | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 0 | 0 | 0 | 0 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 550 | 590 | 647 | 704 |

| Table 6.3: Estimated supplies for safety of vaccination with TT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for TT vaccination | Match with targets in table 4 | 43549 | 47915 | 52511 | 57133 |
| B | Number of doses per child | 3 | 3 | 3 | 3 | 3 |
| C | Number o f TT doses | A x B | 130647 | 143745 | 157533 | 171399 |
| D | AD syringes (+10% wastage) | C x 1.11 | 145018 | 159557 | 174862 | 190253 |
| E | AD syringes buffer stock | D x 0.25 | 36255 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 181273 | 159557 | 174862 | 190253 |
| G | Number of doses per vial | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 0 | 0 | 0 | 0 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 2012 | 1771 | 1941 | 2112 |

| Table 6.4: Estimated supplies for safety of vaccination with Measles |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for Measles vaccination | Match with targets in table 4 | 43549 | 47915 | 52511 | 57133 |
| B | Number of doses per child | 2 | 2 | 2 | 2 | 2 |
| C | Number of Measles doses | A x B | 87098 | 95830 | 105022 | 114266 |
| D | AD syringes (+10% wastage) | C x 1.11 | 96679 | 106371 | 116574 | 126835 |
| E | AD syringes buffer stock | D x 0.25 | 24170 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 120849 | 106371 | 116574 | 126835 |
| G | Number of doses per vial | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 9668 | 10637 | 11657 | 12684 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 1449 | 1299 | 1423 | 1549 |

  - Areas for injection safety funds (for countries requesting funds equivalent to the supplies calculated above)

List of areas of injection safety funded by different sources: (for the GAVI/Vaccine Fund support, fill in “areas of support”. For Ad syringes and waste disposal, fill in “ source of funds”.)

| Source of fund | Area of support | Start of fund utilization |
| --- | --- | --- |
| *NA | NA | NA |

The government of Lesotho is requesting GAVI to provide the items requested in tables 6.1-6.4

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Section 6.0 of the multi year plan of action talks about introduction of innovations in the EPI programme

Sub-Section 6.1 outlines the desire and commitment of the government of Lesotho to introduce pentavalent DPT-HepB+Hib in the routine immunization activities by 2002. The plan further proposes necessary areas that need to be addressed before the introduction of new vaccines such as adequate storage facilities, production of training guides, training of health workers, modification of recording and reporting forms, adequate publicity to communities and other stake holders.

Sub-Section 6.2 refers to the introduction of auto-disable (A-D) syringes in routine immunization services and how they can be disposed off in order to ensure safe injection practices. It is hoped that the EPI programme will shift from using re-usable  and or disposable syringes to A-D syringes in  routine immunization services  by 2002

- Assessment of burden of relevant diseases (if available) :

Currently an assessment of burden of relevant diseases has not yet been done. However, it is proposed that a Hib surveillance sentinel site will be identified with a view to establishing the magnitude of the disease.

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
|  | Possibly to be done in future when the sentinel site for Hib will be established as required by WHO | 2002 onwards | Proportion of meningitis caused by Hib |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc…in relation to the current experience with new and under-used vaccines:

The Government of Lesotho has not yet introduced the new vaccines

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines

- Additional cold chain equipment will be purchased for the Health Service Areas (HSAs) and health facilities.

- Additional and durable shelves will be bought for the national cold room.

- The refrigerated vehicle will make regular deliveries to health facilities

- The temperature in all fridges and freezers will be monitored twice daily, and thermometers will be used in cold boxes during outreach  sessions or during transportation of vaccines.

- Training will be given at all levels of health service provision ( for trainers, supervisors, health workers).

- Appropriate training materials will be developed, funds provided, and training on all formulations and presentations of the new vaccines will be given

- Posters and leaflets will be produced for information, education and communications for both the health workers and the public.

- Training materials will be made available to all HSAs at least six weeks prior to start-up date.

- The policy of Multidose vials will be implemented in all health facilities by 2002

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulas)

| Table 7.1: Estimated number of doses of Pentavalent DPT-HepB+Hib (2 dose vial) vaccine |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to receive new vaccine | match with targets in table 4 | 43549 | 47915 | 52511 | 57133 | 61917 | 66871 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate in percentage | % | 5 | 5 | 5 | 5 | 5 | 5 |
| D | Equivalent wastage factor | See list in table  | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| E | Number of doses | A x B x D | 137179 | 150932 | 165410 | 179969 | 195039 | 210644 |
| F | Number of vaccines buffer stock | E x 0.25 | 34295 | 0 | 0 | 0 | 0 | 0 |
| G | Total of vaccine doses needed | E + F | 171474 | 150932 | 165410 | 179969 | 195039 | 210644 |
| H | Percentage of vaccines requested from the Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 | 171474 | 150932 | 165410 | 179969 | 195039 | 210644 |
| J | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x 1.11 x H / 100 | 183086 | 159557 | 174862 | 190253 | 206184 | 222680 |
| L | Number of AD syringes buffer stock | K x 0.25 | 45772 | 0 | 0 | 0 | 0 | 0 |
| M | Total of AD syringes | K + L | 228858 | 159557 | 174862 | 190253 | 206184 | 222680 |
| N | Number of Reconstitution syringes (+10% wastage) | I x 1.11 / J | 95168 | 83767 | 91803 | 99883 | 108247 | 116907 |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 | 3597 | 2701 | 2960 | 3221 | 3490 | 3769 |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference : Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulas as per table 7.1)

| Table 7.2: Estimated number of doses of Pentavalent DPT-HepB+Hib (10 dose vial) vaccine |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to receive new vaccine | match with targets in table 4 | 43549 | 47915 | 52511 | 57133 | 61917 | 66871 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate in percentage | % | 25 | 20 | 15 | 15 | 15 | 15 |
| D | Equivalent wastage factor | See list in table  | 1.33 | 1.25 | 1.18 | 1.18 | 1.18 | 1.18 |
| E | Number of doses | A x B x D | 173761 | 179681 | 185889 | 202251 | 219186 | 236723 |
| F | Number of vaccines buffer stock | E x 0.25 | 43440 | 0 | 0 | 0 | 0 | 0 |
| G | Total of vaccine doses needed | E + F | 217201 | 179681 | 185889 | 202251 | 219186 | 236723 |
| H | Percentage of vaccines requested from the Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 | 217201 | 179681 | 185889 | 202251 | 219186 | 236723 |
| J | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x 1.11 x H / 100 | 193237 | 159557 | 174862 | 190253 | 206184 | 222680 |
| L | Number of AD syringes buffer stock | K x 0.25 | 48309 | 0 | 0 | 0 | 0 | 0 |
| M | Total of AD syringes | K + L | 241546 | 159557 | 174862 | 190253 | 206184 | 222680 |
| N | Number of Reconstitution syringes (+10% wastage) | I x 1.11 / J | 24109 | 19945 | 20634 | 22450 | 24330 | 26276 |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 | 2949 | 1992 | 2170 | 2361 | 2559 | 2763 |

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) Page 16 of the five year plan of Action | Document number: 07 |
| --- | --- |

# 9.  Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive «Resource Mobilisation Plan» by the time of the mid-term Review. Highlights of the agreements made with donor-agencies (i.e.: Vaccine Independence Initiative) and the use of funds freed by debt relief :

The Government  of Lesotho is committed to ensuring the provision of sound health care to the children of Lesotho. It is on this light that it has for the first time taken the initiative to contribute to the procurement of BCG vaccine for the 2001-2002 financial year. The government has in the past been supporting EPI by procuring such logistics as refrigerators, vaccine carriers, cold boxes, syringes in order to complement external support for the programme.

The government will continue with its efforts to mobilize adequate resources for immunization from its own allocation and  from its collaborating partners and donors. The 15% committed by the government for the procurement of vaccines will be increased over the next five years. The ICC on the other hand,  will ensure  mobilization of adequate resources in order to improve and sustain the immunization services.

Periodic review of the immunization activities will be conducted in order to assess the performance of the programme. Findings will be discussed and disseminated to all stakeholders. Health Service Areas (health administrative areas) with low immunization coverage will be identified through a monitoring system that will be put in place and appropriate actions will be instituted in order to improve coverage in those areas.

| - Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number: 09 |
| --- | --- |

For more details on expenditure towards immunization activities see tables 1 and 2 on Annex 1.

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- Careful planning of the estimates and distribution of the new and routine vaccines

- Improved management of the cold chain

- Implementation of the revised WHO policy on the use of opened multi-dose vials of vaccine in subsequent sessions

- Training on the use and interpretation of the vaccine vial monitor (VVM) as a management tool for OPV and other vaccine that may have VVMs

- Introduction of the new combination DTP-HepB + Hib vaccine in a two-dose presentation.

- Improving vaccine stock management at all levels

- Reducing missed opportunities for vaccination of eligible children and pregnant mothers

# 10.        Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Lesotho

considering that its DTP3 coverage for 2000 was  56%  corresponding to 36,062 number of children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government does hereby apply to receive the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for strengthening Immunization Services                        (YES)           NO

- Support for Injection Safety                                                             (YES)           NO

- Support for New  Vaccines                          		                    (YES)           NO

10.1  SUPPORT FOR STRENGTHENING IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 43, 549  (number of children). Funds will also be requested for following years as estimated in table 4.

- The in-country transfer of funds will be by (tick only one):

| Government |  | A Partner agency (specify name) |  | An independent third party |  |
| --- | --- | --- | --- | --- | --- |

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

Although funds will be managed by the government, the ICC members shall endorse all the transactions for the utilization of funds. All activities shall be discussed and endorsed by the ICC before funds are released for the activities. Several signatories will be identified in order to ensure transparency and accountability and periodic monitoring will be done and reports submitted.

- Countries requesting immunization services support should submit the  “Banking Details” form (Annex 3) with the proposal

10.2  SUPPORT FOR INTRODUCTION OF NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the plan for introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8 : New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| DPT-HepB+Hib (combination | 2 dose | June, 2002 | 171,474 | 150,932 |
| DPT-HepB+Hib (Combination) | 10 dose | June, 2002 | 217,201 | 179,681 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                             By GOVERNMENT

- (If vaccines are procured by the Government) Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

As stated above, the vaccines will be procured by UNICEF on behalf of the Government of Lesotho.

- (In case you are entitled to receive US$ 100,000 to facilitate introduction of new vaccines) If you submit the attached “Banking Details” form (Annex 3) with the proposal, it will speed up the process for funds disbursement to the country, as soon as the support for New and Under-used Vaccines is approved.

10.3  SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the Injection Safety plan by providing:

(Tick one choice only):	   	The amount of supplies listed in table 9

The equivalent amount of funds

| Table99: Total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES requested to GAVI and the Vaccines Fund (fill in the total sums of rows “F”, “H” and “I” of tables 6.1,6.2, 6.3, 6.4. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | For BCG | 53214 | 57122 | 62601 | 68110 |
|  |  | for others | 351671 | 319114 | 349723 | 380506 |
| H | Total of Reconstitution syringes |  | 12264 | 13493 | 14787 | 16089 |
| I | Total of safety boxes |  | 4760 | 4328 | 4741 | 5159 |

- (In case you have chosen to receive funds) If you submit the attached “Banking Details” form (Annex 3) with the proposal, it will speed up the process for funds disbursement to the country, as soon as the support for Injection safety is approved.

# 11.    Additional comments and recommendations from the ICC

- The ICC fully supports the proposal and is looking forward to its approval by the independent review committee of the GAVI secretariat

- The ICC reiterates the total government commitment to ensuring improving and strengthening  EPI services in the country.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2000 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Private sector | Donor 1 (WHO) | Donor 21 (UNICEF) | Donor 3 (Irish AID) | Donor 4 (EU) | Donor 5 (LHDA) | Donor n.. 2 | Total Expend-iture in 2000 |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |  |
| 1.1 | - BCG,DPT,OPV, Measles,TTV |  |  |  | 84884 |  |  |  |  | 84884 |
| 1.2 | - Vit A |  |  |  | 9790 |  |  |  |  | 9790 |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  |  | 45300 |  |  | 45300 |
| 2.2 | - Personnel and operation | 81160 |  |  |  | 17755 | 5940 | 5940 |  | 110795 |
| 2.2 | - Transport |  |  | 40,000 |  |  |  |  |  | 40000 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Measles and A-D syringes |  |  |  | 48000 | 58651 |  |  |  | 106651 |
| 3.2 | - Line item |  |  |  |  |  |  |  |  |  |
| 4 | - NIDs and Surveillance |  |  | 89,278 |  |  |  |  |  | 89,278 |
| Total expenditure in 2000 |  | 81160 |  | 129278 | 142674 | 76406 | 51240 | 5940 |  | 486698 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2000 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Private sector | Donor 11 ((WHO) | Donor 2 (UNICEF) | Donor 3 (Irish AID) | Donor 4 (EU) | Donor 5 (LHDA) |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - BCG,DPT,OPV,Measles,TTV |  |  |  | 84884 |  |  |  | 113178 | 28295 |
| 1.2 |  |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Personnel | 81160 |  |  |  | 17755 | 5940 | 5940 | 199913 | 89118 |
| 2.2 | - Cold Chain Equipment |  |  |  |  |  | 45300 |  | 45637 | 337 |
| 2.3 | - Transport |  |  | 40,000 |  |  |  |  | 40,000 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Measles and A-D syringes |  |  |  | 48000 | 58651 |  |  | 201863 | 95212 |
| 3.2 | - Vit A |  |  |  | 9790 |  |  |  | 9790 | - |
| 4 | - NIDs and Surveillance |  |  | 89,278 |  |  |  |  | 89,278 | - |
| Total commitment |  | 81160 |  | 129278 | 142674 | 76406 | 51240 | 5940 | 699659 | 212962 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation10

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number: 01 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number: 02 |
| - Terms of reference of the ICC | Document number: 03 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number: 04 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number: 05 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number: 06 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number: 07 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) Page 17 - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number: 07 Document number: 08 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2000 and resource needs (Annex 1) | Document number: 09 |

10Please submit hard copy documents with an identical electronic copy whenever possible

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below : |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution : (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address : |  |  |  |  |  |  |  |  |  |  |
| #### City – Country : |  |  |  |  |  |  |  |  |  |  |
| Telephone No. : |  |  |  | Fax No. : |  |  |  |  |  |  |
| #### Amount in USD : |  | ( To be filled in by GAVI Secretariat ) |  |  | Currency of the bank account : |  |  |  |  |  |
| For credit to : Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No. : |  |  |  |  |  |  |  |  |  |  |
| At : Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited ? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official : |  |  |  |  |  |  |  |  |  |  |
| #### Name : |  |  |  |  |  |  |  |  | Seal : |  |
| #### Title : |  |  |  |  |  |  |  |  |  |  |
| #### Signature : |  |  |  |  |  |  |  |  |  |  |
| Date : |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 ( To be completed by the Bank ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name : |  |  |  |  |  |
| Branch Name : |  |  |  |  |  |
| Address : |  |  |  |  |  |
| City – Country : |  |  |  |  |  |
| Swift code : |  |  |  |  |  |
| Sort code : |  |  |  |  |  |
| ABA No. : |  |  |  |  |  |
| Telephone No : |  |  |  |  |  |
| Fax No : |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories : |  |  | Name of bank’s authorizing official : |  |  |
| 1 Name : Title : |  |  | Signature : |  |  |
|  |  |  | Date: |  |  |
| 2 Name : Title : |  |  | Seal: |  |  |
| 3 Name : Title : |  |  |  |  |  |
| 4 Name : Title : |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative : |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine Wastage Rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records; B =  the number of DTP vaccinations. If you request for yellow fever vaccines, include a row for measles vaccine wastage rate.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vacc

ines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided.

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided.

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

The preferred mechanism is payment directly to a Government account (Guidelines on Country Proposal # 5.1)