The Government of

The Republic of MALI

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette along with the signed hard-copy original of the document to: The GAVI Secretariat, c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland. Please address any enquiries to: Dr Tore Godal,

tgodal@unicef.ch or to representatives of a GAVI partner agency. All documents and attachments must be submitted in English or French.

# Government signatures

LIST OF ACRONYMS

ARIVAS 	:	Project to Support Immunization and Vaccination Self-Reliance 				in Sahelian Africa (Projet d'Appui Régional pour l'Indépendance 				Vaccinale en Afrique Sahélienne)

BCG 		:	Bacille Calmette Guerin

CATR	 	:     	Regional Support Centre (Cellule d'Appui Technique Régionale)

CNI 		: 	National Immunization Centre (Centre National d'Immunisation)

CROCEP 	: 	Regional Steering, Coordination and Evaluation Committee of 				PRODESS (Comité Régional d'Orientation, de Coordination et 				d'Evaluation du PRODESS

CSA 		: 	District Health Centre (Centre de Santé d'Arrondissement)

CSAR 	: 	Revitalized District Health Centre (Centre de Santé 						d'Arrondissement  Révitalisé)

CSCOM 	: 	Community Health Centre (Centre de Santé Communautaire)

DAF 		: 	Finance and Administration Department

DHS II 	: 	Demographic and Health Survey (Enquête Démographique et 				Sanitaire)

DNB/MF 	: 	National Budget Department/Ministry of Finance (Direction 					Nationale du Budget/Ministère des Finances)

DNCF/MF 	: 	National Financial Control Department/Ministry of Finance 					(Direction Nationale du Contrôle Financier/Ministère des 					Finances)

DNSI 		: 	National Statistics and Information Department (Direction 					Nationale de la Statistique et de l'Information)

DNSP 	: 	National Public Health Department (Direction Nationale de la 				Santé Publique)

DTP 		: 	Diphtheria-Tetanus-Pertussis

ED 		:	Epidemiology Division (Division Epidémiologie)

EDF 		: 	European Development Fund

EPI 		: 	Expanded Programme on Immunization

EU  		: 	European Union

GDP 		: 	Gross Domestic Product

GNP 		: 	Gross National Product

HepB 		: 	Hepatitis B

Hib 		: 	Haemophilis Influenzae B

ICC 		: 	Inter-Agency Coordinating Committee (Comité de Coordination 				Inter-agences)

JNV 		: 	National Immunization Days

MS		: 	Ministry of Health

n.a.  		: 	not available

NGO  		: 	Non-Governmental Organization

NN Tetanus  :	Neonatal Tetanus

OP 		: 	Operational Plan

OPV 		: 	Oral Polio Vaccine

PMA 		: 	Minimum Package of Activities (Paquet Minimum d'Activités)

PRODESS 	: 	Health and Social Development Programme (Programme de 				Développement Sanitaire et Social)

PSPHR 	: 	Health Project/Population and Rural Domestic Water Supply 					(Projet Santé/Population et Hydraulique Rurale)

SSP Ségou 	: 	Ségou Primary Health Care (Soins de Santé Primaires Ségou)

TT 		: 	Tetanus (vaccine)

UNDP		: 	United Nations Development Programme

UNICEF 	: 	United Nations Children's Fund

USAID 	: 	United States Agency for International Development

WHO 		: 	World Health Organization

The Government of the Republic of MALI undertakes to develop the national immunization services on a sustainable basis in accordance with the multi-year plan attached hereto. It further undertakes to conduct an annual review of district immunization performances by means of a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet financial, material and technical needs arising from the plan.

Signature:	…………………………………………...

Title:	Minister of Health

Date:	23 June 2000

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries. The GAVI Secretariat may share the documents with the Alliance's partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee, approve this proposal on the basis of the supporting documents attached thereto:

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |
| 1. Finance and Administration Department/Ministry of Health (DAF/MS) | Mr. Ibrahim TANDIA Director |  |
| 2. National Immunization Centre (CNI) | Dr. Youssouf KONATE Director |  |
| - National Financial Control Department/Ministry of Finance (DNCF/MF) | Mr. Yaya DIALLO Financial Controller |  |
| 4. National Budget Department/Ministry of Finance (DNB/MF) | Mr. Abdoulaye BATHILY Head, Accounting and Materials Division |  |
| 5. UNICEF | Mr. Bréhima Siaka DIALLO Deputy Administrator, Health Programme |  |
| 6. WHO | Dr. Tiécoura COULIBALY Administrator, Disease Control Programme |  |
| 7. USAID | Mrs. Aïssatou LÔ Health Advisor |  |
| 8. UNDP | Mrs. Awa Paul DIAWARA Programme Administrator |  |
| 9. European Union (EU) | Dr. Laurent LOB Health Advisor |  |

The Chairman						 Signed on: _______________ 2000

Mr. Ibrahim TANDIA

Should the GAVI Secretariat have queries concerning this submission, the contact person is:

Name: Dr. Youssouf KONATE	Title/Address: Director CNI - BP 51

Tel: (223) 22 39 20 (switchboard) or (223) 22 77 99 (straight line)

Fax c/o DNSP: (223) 23 24 74 or Ministry of Health: (223) 22 03 02

E-mail:  c/o OMS: coulibalyt@oms.org.ml

or UNICEF: bdiallo@unicef.org

- Immunization fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 9,790,492* inhabitants | per capita GNP | USD 280*** |
| Infants 0-11 months | 391 620* | Infant mortality rate | 123/ 1000** |
| Percentage of GDP allocated to Health | n.a. | Share of health care in Government expenditure | 11,07%**** |

* 1998 census findings. The figure of 10,240,000 inhabitants given in the Letter of Intent is our population projection for the year 2000, based on this figure and on a 2.2% population growth rate per annum (the DNSI has not yet made this projection)

** DHS II (1995-1996)

*** National Strategy to Combat Poverty

**** MSSPA budget trends (see Annex 3).

| Situation of the Health System |  |
| --- | --- |
| Please find attached the following background documents: |  |
| - Overall government health policies and strategies: Sectoral health and population policy statement | Document number: 1 |
| - Structure of central, provincial and peripheral government health services and how they relate to immunization services (include organization chart) | Document number: 2 |
| - Status of ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in funding methods) and their implications for the immunization services | Document number: 3 |
| - Government policies and practices pertaining to private sector participation in the immunization programme.* | Document number: 0 |

* For the time being there are no government policies and practices pertaining to private sector participation in the immunization programme. Nevertheless, most NGOs do participate in the immunization programme by virtue of a framework agreement with the Government.

| ### Immunization coverage trends Data from the annual report to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden Data from the annual report to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 78% | 64% | 84% |  | Diphtheria | n.a. | 0 | n.a. | 0 |
| DTP3 | 56% | 47% | 52% |  | Pertussis (whooping cough) | n.a. | 19 | n.a. | 0 |
| OPV3 | 56% | 47% | 52% |  | Poliomyelitis | 2 | 4 | 0 | 0 |
| Measles | 60% | 46% | 57% |  | Measles | 10240 | 2 506 | 35 | 17 |
| TT2+ Pregnant Women | 20% | 19% | 33% |  | NN Tetanus | 31 | 29 | n.a. | n.a. |
| Hib | - | - | - |  | Hib | n.a. | n.a. | n.a. | n.a. |
| Yellow Fever* | 10% | 13% |  |  | Yellow fever | 0 | 0 | 0 | 0 |
| HepB | - | - | - |  | HepB seroprevalence (if available) | n.a. | n.a. | n.a. | n.a. |

No immunization coverage survey was conducted in 1999.

* Selective activities confined to some localities.

Hib and HepB not yet introduced.

The rate of coverage reported for 1999 is lower than that for 1998 (DTPP3 contracted from 56% in 1998 to 47% in 1999). This trend results from:

- reporting for 1998 that was 91% complete as against only 88% for 1999 (source: ED);

- a real contraction in the PMA for 1999, including vaccination, owing to funding problems stemming from the changeover from a project-based approach (PSPHR, PSSP Ségou…) to a  programme-based  approach (PRODESS).

# Profile of the Inter-Agency Coordinating Committee (ICC)

(Various agencies and partners supporting immunization services in the country are coordinated and organized through an inter-agency mechanism referred to in this document as ICC)

- Name of the ICC: Technical Immunization Follow-up Committee

- Date of constitution of the current ICC: May 1996.  Operational but not formalized

- Organizational structure (e.g., sub-committee, independent entity): Single committee

- Frequency of meetings: quarterly

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chairperson | Director/DAF/MS | Mr. Ibrahim TANDIA |
| Secretary | Director/CNI/MS | Dr. Youssouf KONATE |
| Members | - Financial Controller/DNCF/MF - Head, Accounting and Materials Division/DNB/MF - Dep. Adm. Health Prog./UNICEF - Admin., Disease Control Prog./WHO - Health Advisor/USAID - Prog. Adm./UNDP - Health Advisor/EU | Mr. Yaya DIALLO Mr. Abdoulaye BATHILY Mr. Bréhima S. DIALLO Dr. Tiécoura COULIBALY Mrs. Aïssatou LÔ Mrs. Awa Paul DIAWARA Dr. Laurent LOB |

As emerges from the report of the CATR mission to Mali from 25 to 30 October 1999, this structure has not yet been formalized. The DAF chairs the Committee, whilst CNI provides secretariat services. As presently made up, this Committee is unable to discharge the functions and responsibilities outlined below.  The department is now taking steps to formally set up a new committee, the terms of reference of which are attached hereto.

ICC terms of reference 					Document number: 4

- Main functions and responsibilities:

- Follow up of the programme's implementation - Resource mobilization - Strengthening inter-agency coordination and partnership

- The following diagram shows the ICC's operational relationships with other health sector institutions:

The ICC member agencies are members of the PRODESS technical follow-up committee. The same is true of the JNV steering committee and the JNV national organizing committee. The ICC members participate in the meetings of PRODESS at the decentralized level (CROCEP*).

* PRODESS Regional Steering, Coordination and Evaluation Committee

The following documents are attached:

| - Terms of reference of the ICC: informal committee | Document number: 4 |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings attended by partners and pertaining to the improvement and enlargement of the national immunization programme | Document number: 5 |

# Immunization Services Assessment

Reference is made to the most recent assessments of the immunization system conducted during the three years preceding the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Joint external assessment of the Expanded Programme on Immunization - national survey on immunization coverage - operational survey Study on vaccine wastage rate in Mali | Ministry of Health- UNICEF-USAID-WHO-UNDP-EU Ministry of Health-CATR*-UNICEF-WHO | December 1998 April 1999 June 1999 |

* Regional Support Centre of the ARIVAS/EDF Project

- The following are the three major problems identified in the assessments :

- Limited immunization coverage and high wastage rate - Inadequate programme management at all levels - Inadequate supervision

- The following are the three core recommendations of the assessments:

- Enhance the supply, accessibility and sustainability of immunization services - Improve programme management at all levels - Promote quality-based supervision.

- Attached is a complete copy (including executive summary) of:

| - the most recent assessment report on the status of immunization services - survey on immunization coverage .......................... - operational survey .................................................... - study on wastage rates............................................. | Document number 6 7 8 |
| --- | --- |
| - the recommendations of the assessment report, indicating the status of their implementation (whether included in work programme, implemented, not implemented, in progress…. | Document number: 9 |

- The following immunization service components or areas are still pending review (or study). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |
| Study on injection safety Study on cold chain maintenance | July 2000 June-July 2000 | 15 000 9 666 |

# Multi-Year Immunization Plan

Based on the recommendations of the immunization services assessment, the Government has drawn up (or updated) the multi-year immunization plan or adapted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. - Operational Plan 2000 | Document number: 10 Document number: 11 |
| --- | --- |

The multi-year plan needs to be reviewed following the dissemination of the findings of the joint external assessment in the regions. OP 2000 activities do, however, reflect some of the recommendations of the assessment.

- According to  the 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 186 795 |
| Used doses of DTP* | 648 548 |

- Estimated annual targets

|  | 2000 | 2001 | 2002 |  | 2003 |  | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of children scheduled for DTP3 vaccination | 245 880 | 272 584 | 300 440 | 329 550 |  | 359 968 |  | 391 782 |
| Projected doses of DTP to be used | 981 062 | 1 087 611 | 1 198 756 |  | 1 314 905 |  | 1 436 273 | 1 563 211 |

The factors used as the basis of computation are:

- Projected annual population based on the 1998 census and a 2.2% growth rate;

- Annual coverage targets: 60% in 2000, 65% in 2001, 70% in 2002, 75% in 2003, 80% in 2004 and 85% in 2005;

- Proportion of infants of 0-11 months = 4% of the population;

- 25% wastage rate, with a multiplication factor of 1.33;

- Three (3) doses per child.

# New and under-used vaccines

Following is a summary of those aspects of the plan, mentioned in section five, addressing the introduction of new and under-used vaccines.

- Assessment of the burden of the diseases concerned (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Yellow fever | n.a. | - | - |
| HepB | n.a. | - | - |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of a monovalent vaccine:

None

- Planning for hepB vaccinations:

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 272 584 | 300 440 | 329 550 | 359 968 | 391 782 |
| Total vaccine doses required | 1 087 611 | 1 198 756 | 1 314 905 | 1 436 273 | 1 563 211 |
| Preferred vial size(s) (no. of doses) | 10-dose | 10-dose | 10-dose | 10-dose | 10-dose |
| Estimated wastage rate | 25% | 25% | 25% | 25% | 25% |
| % of vaccines requested from the Fund | 90% | 90% | 90% | 90% | 80% |
| AD syringes | 899 528 | 991 452 | 1 087 515 | 1 187 894 | 1 292 882 |
| Syringe wastage rate | 10% | 10% | 10% | 10% | 10% |

Factors used for computation:

- Projected annual population based on the 1998 census and a 2.2% growth rate;

- Identical annual coverage targets as for DTPP, since it is the same timetable and we wish to have the combined DTP-HepB vaccine.

- Proportion of infants of 0-11 months (target)  = 4% of the population;

- 25% wastage rate (multiplication factor of 1.33)

- 3 doses.

Number of AD syringes lower than that of vaccine doses required, as we estimated a wastage rate of 10% (even trained staff waste many syringes in the initial years) and a 25% rate for vaccines.

- Planning for Hib vaccinations:

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) (no. of doses) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

Mali does not envisage introducing Hib vaccines before 2005.

- Planning for yellow fever vaccinations:

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 209 680 | 236 060 | 263 640 | 292 474 | 322 644 |
| Total vaccine doses required | 278 874 | 313 960 | 350 641 | 388 990 | 429 117 |
| Preferred vial size(s) | 10-dose | 10-dose | 10-dose | 10-dose | 10-dose |
| Estimated wastage rate | 25% | 25% | 25% | 25% | 25% |
| % of vaccines requested from the Fund | 90% | 90% | 90% | 90% | 80% |
| AD syringes | 230 648 | 259 666 | 290 004 | 321 722 | 354 909 |
| Syringe wastage rate | 10% | 10% | 10% | 10% | 10% |

Factors used for computation:

- Projected annual population based on the 1998 census and a 2.2% annual growth rate

- Annual Coverage targets: 50% in 2001, 55% in 2002, 60% in 2003, 65% in 2004 and 70% in 2005

- Proportion of infants of 0-11 months (target)  = 4% of the population

- 25% wastage rate (multiplication factor of 1.33)

- 1 dose only

- 10% estimated AD syringe wastage rate

| - Attached hereto is the action plan for vaccinations with new or under-used vaccines (if already included in the national multi-year plan, indicate page and paragraphs) | Document number: 10 pp. 9, 10, 11, 12, 13, 14 |
| --- | --- |

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each budget item and for each year are shown in Annex 1. | Document number: 12 |
| --- | --- |

- Below is a list of financial sustainability strategies and of current/projected immunization financing mechanisms, including agreements concluded with other agencies (namely, Vaccine Independence Initiative). The relevant documents are attached.

| CONTRIBUTIONS FROM EACH PARTNER ASSOCIATED WITH STRATEGY (in USD) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Partner | Strategy title/Budget item | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | TOTAL |
| 1. UNICEF | 1. Ext. cov./Routine EPI | 416,258 | 615,183 | 949,908 | 680,000 | 615,500 | - | - | - | 3,276,849 |
|  | 2. Vacc. Indep. Initiative | - | - | - |  |  |  |  |  | - |
|  | 3. Additional immunization | 633,216 | 771,974 | 600,000 | - | - | - | - | - | 2,005,190 |
| 2. WHO | 1. Ext. cov./Routine EPI | 85,514 | 200,868 | 595,500 | 133,000 | 130,000 | 130,000 | 130,000 | 130,000 | 1,534,882 |
|  | 2. Vacc. Indep. Initiative | - | - | - |  |  |  |  |  | - |
|  | 3. Additional immunization | 201,503 | 268,969 | 669,500 | 669,500 |  |  |  |  | 1,809,472 |
| 3. USAID | 1. Ext. cov./Routine EPI |  |  | 400,000 |  |  |  |  |  | 400,000 |
|  | 2. Vacc. Indep. Initiative |  |  |  |  |  |  |  |  | - |
|  | 3. Additional immunization |  |  |  |  |  |  |  |  | - |
| 4. Eur. Comm. | 1. Ext. cov./Routine EPI |  |  | 8,279 | 1,000,000 | 1,000,000 |  |  |  | 2,008,279 |
|  | 2. Vacc. Indep. Initiative |  |  |  |  |  |  |  |  | - |
|  | 3. Additional immunization |  |  |  |  |  |  |  |  | - |
| 5. Swiss Coop. | 1. Ext. cov./Routine EPI | 311,663 | 318,634 | 285,863 |  |  |  |  |  | 916,160 |
|  | 2. Vacc. Indep. Initiative | - | - | - |  |  |  |  |  | - |
|  | 3. Additional immunization | 4,637 | 4,891 | 4,282 |  |  |  |  |  | 13,810 |
| 6. Dutch Coop. | 1. Ext. cov./Routine EPI | 875,297 | 1,070,581 | 1,324,072 |  |  |  |  |  | 3,269,950 |
|  | 2. Vacc. Indep. Initiative | - | - | - |  |  |  |  |  | - |
|  | 3. Additional immunization | 25,666 | 15,033 | - |  |  |  |  |  | 40,699 |
| 7. Intern. Plan | 1. Ext. cov./Routine EPI |  |  | 40,856 | 283,528 | 12,507 | 12,507 | 12,507 |  | 361,905 |
|  | 2. Vacc. Indep. Initiative |  |  |  |  |  |  |  |  | - |
|  | 3. Additional immunization |  | 23,588 |  |  |  |  |  |  | 23,588 |
| 8. Government | 1. Ext. cov./Routine EPI | 175,171 | 191,496 | 537,467 |  |  |  |  |  | 904,134 |
|  | 2. Vacc. Indep. Initiative | 914,509 | 1,226,960 | 1,226,960 |  |  |  |  |  | 3,368,429 |
|  | 3. Additional immunization | 225,714 | 225,714 | 225,714 |  |  |  |  |  | 677,142 |
| 9. CATR | 1. Ext. cov./Routine EPI |  |  |  |  |  |  |  |  | - |
|  | 2. Vacc. Indep. Initiative |  | 12,753 | 24,698 |  |  |  |  |  | 37,451 |
|  | 3. Additional immunization |  |  |  |  |  |  |  |  | - |
|  | TOTAL | 3,869,148 | 4,946,644 | 6,893,099 | 2,766,028 | 1,758,007 | 142,507 | 142,507 | 130,000 | 20,647,940 |
| The main partners are UNICEF, WHO, USAID, Swiss Cooperation and Dutch Cooperation. Data is available to us for some partners beyond the year 2000, though not for others, as their pledges cannot surpass programming cycles. |  |  |  |  |  |  |  |  |  |  |
| In Mali there are two strategies for the sustainability of the Expanded Programme on Immunization: |  |  |  |  |  |  |  |  |  |  |
| - extending coverage (creating CSCOMs, revitalizing the CSAs), network of health centres in outlying areas run by the communities and providing a minimum package of activities, including the immunization of children and women of reproductive age. |  |  |  |  |  |  |  |  |  |  |
| - Thanks to the Vaccine Independence Initiative being implemented through CATR since 1996 with the support of the EDF, the Government of Mali is now able to purchase form its own funds all the antigens in the routine EPI. |  |  |  |  |  |  |  |  |  |  |
| Although done on a selective basis, additional immunization has been absorbing considerable funding for some years now, mobilizing many partners and helping to shore up the routine EIP. |  |  |  |  |  |  |  |  |  |  |

| - Hereunder is a brief description of the immunization support derived from poverty reduction strategies (including the use of funds freed up by debt relief). The relevant document is attached. | Document number: 14 |
| --- | --- |

The national strategy to combat poverty drawn up in July 1998 is helping to improve access to immunization services, in particular for people in outlying areas, by creating community health centres.

# Preferred funding channel

(Only for countries seeking support from the immunization services sub-account)

- Funds will be transferred to the country from the immunization services sub-account in the following manner (tick one box only) :

| Directly to the Government | X | Through a partner agency |  | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the box that follows we describe how the mechanism will operate to ensure transparency, the observance of accounting standards, long-term sustainability and government autonomy.

PRODESS management procedures - Replenishment of Account A at the central level by the partner - Replenishment of Account B at the regional level from Account A - Replenishment of Account C at the circle level from Account B Disbursements are made through the government financial services based on the OP and the balance sheets adopted for each level.

# Country concerns

The following are the ICC’s concerns and recommendations pertaining to this proposal:

Despite the endeavours of the various EPI partners, the persisting concerns are: - The limited immunization coverage; - The risk of a yellow fever epidemic; - Tardiness in introducing HepB vaccination into the routine EPI. It is therefore necessary to: - Boost the EPI by means of sustainability strategies such as speedier extension of health coverage, people empowerment by means of the community health centres (CSCOM). - Introduce new antigens such as hepatitis B and yellow fever into the routine EPI, gradually and over the medium term.

| ANNEX 1 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial statements and unmet immunization needs (in USD) |  |  |  |  |  |  |  |  |  |  |
| Table 1: 1999 Expenditure |  |  |  |  |  |  |  |  |  |  |
| 1999 Expenditure and respective funding sources |  |  |  |  |  |  |  |  |  |  |
| Ref. | Category/Budget Item | Central Government | ASACO | UNICEF | WHO | UNDP | USAID | Rotary | CATR | Total 1999 expenditure |
| 1 | Vaccines, AD syringes |  |  |  |  |  |  |  |  |  |
| 1.1. | Item 1: Vaccines | 1,188,978 | - | 618,530 |  |  |  |  |  | 1,807,508 |
| 1.2. | . Item 2: AD syringes | - |  | 30,983 |  |  |  |  |  | 30,983 |
| 2 | Equipment (cold chain, spare parts, sterilization...) |  |  |  |  |  |  |  |  |  |
| 2.1. | Item 1: Cold chain | 46,953 |  | 160,000 | 57,070 |  | 32,606 |  |  | 296,629 |
| 2.2 | Item 2: Sterilization + injection | 211,941 |  | 6,971 |  |  |  |  |  | 218,912 |
| 3 | Other immunization-related items |  |  |  |  |  |  |  |  |  |
| 3.1 | Item 1: Logistics | 76,233 |  | 240,000 |  |  | 100,507 |  |  | 416,740 |
| 3.2 | Item 2: Construction | 7,711 |  | - |  |  |  |  |  | 7,711 |
| 3.3 | Item 3: Fuel for cold chain |  | 71,000 | 63,473 |  |  |  |  |  | 134,473 |
| 3.4 | Item 4: Operations, |  |  |  |  |  |  |  |  |  |
|  | Office supplies | 237,400 |  | - | 165,066 |  | 19,008 |  |  | 421,474 |
| 3.5 | Item 5: Training |  |  | 152,823 | 37,108 | 35,145 | 200,000 |  | 4,626 | 429,702 |
| 3.6 | Item 6: Supervision/Follow-up | 53,800 |  | 11,710 | 12,409 |  |  |  | 8,127 | 86,046 |
| 3.7 | Item 7: Social mobilization |  |  | 102,667 | 92,211 |  |  | 39,943 |  | 234,821 |
| 3.8 | Micro-planning | - | - | - | 42,796 |  |  |  |  | 42,796 |
| 3.9 | Epidemiological Surveillance | - | - |  | 63,177 |  |  |  |  | 63,177 |
|  | Total 1999 expenditure | 1,823,016 | 71,000 | 1,387,157 | 469,837 | 35,145 | 352,121 | 39,943 | 12,753 | 4,190,972 |
| 1. If basket funding or a similar aggregated funding approach is used, please give the most accurate possible description of total funding and/or partner contributions. |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |
| 2. Please use the electronic version of the document and insert as many columns as needed for partner contributions. |  |  |  |  |  |  |  |  |  |  |
| 3. Please use the electronic version of the document in order to insert as many items as necessary |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | * JNV + extension of coverage |  |  |
| For the purposes of expanding coverage and implementing the PMA, Swiss Cooperation has contributed USD 226,467 in the Yorosso, Koutiala and Sikasso circles, whilst Dutch Cooperation has made USD 749,074 available in the Ségou region. |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |
| Table 2: Routine EPI + JNV |  |  |  |  |  |  |  |  |  |  |
| 1999 Budget (in USD) |  |  |  |  |  |  |  |  |  |  |
|  | Category/Budget Item | Central Government | ASACO | UNICEF | WHO | UNDP | USAID | Rotary | CATR | Total 1999 expenditure |
| 1 | Vaccines, AD syringes |  |  |  |  |  |  |  |  |  |
| 1.1. | Item 1: Vaccines | 1,204,709 |  | 634,892 |  |  |  |  |  | 1,839,601 |
| 1.2. | . Item 2: AD syringes | - |  | 30,000 |  |  |  |  |  | 30,000 |
| 2 | Equipment (cold chain, spare parts, sterilization...) |  |  |  |  |  |  |  |  |  |
| 2.1. | Item 1: Cold chain | 48,909 |  | 260,000 | 650,000 |  |  |  |  | 958,909 |
| 2.2 | Item 2: Sterilization + injection | 211,941 |  | 8,000 |  |  |  |  |  | 219,941 |
| 3 | Other immunization-related items |  |  |  |  | 135,145 | 352,121 |  |  | 487,266 |
| 3.1 | Item 1: Logistics | 37,497 |  | 230,000 |  |  |  |  |  | 267,497 |
| 3.2 | Item 2: Construction | 15,620 | 1,562 | - |  |  |  |  |  | 17,182 |
| 3.3 | Item 3: Fuel for cold chain | - | 71,000 | 70,000 |  |  |  |  |  | 141,000 |
| 3.4 | Item 4: Operations, |  |  |  |  |  |  |  |  |  |
|  | Office supplies | 91,912 | - | - | 61,400 |  |  |  |  | 153,312 |
| 3.5 | Item 5: Training | - | - | 150,000 | 12,500 |  |  |  | 4,626 | 167,126 |
| 3.6 | Item 6: Supervision/Follow-up | 18,749 | - | 20,000 | 31,787 |  |  |  | 8,127 | 78,663 |
| 3.7 | Item 7: Social mobilization | 2,664 | - | 371.081 | 73,600 |  |  |  |  | 266,264 |
| 3.8. | Micro-planning |  |  |  | 18,000 |  |  | 39,000 |  | 57,000 |
| 3.9. | Epidemiological Surveillance (PFA) |  |  |  | 81,802 |  |  |  |  | 81,802 |
| Total 1999 commitment |  | 1,632,001 | 72,562 | 1,773.973 | 929,089 | 135,145 | 352,121 | 39,000 | 12,753 | 4,946.644 |
| 1. If basket funding or a similar aggregated funding approach is used, please give the most accurate possible description of total funding and/or partner contributions. |  |  |  |  |  |  |  |  |  |  |
| 2. Please use the electronic version of the document and insert as many columns as needed for partner contributions. |  |  |  |  |  |  |  |  |  |  |
| 3. Please use the electronic version of the document in order to insert as many items as necessary |  |  |  |  |  |  |  |  |  |  |

###### ANNEX 2

Summary of documentation requested

| Background information on the development of the health system |  |
| --- | --- |
| - Overall government health policies and strategies | Document number: 1 and 1bis |
| - Structure of the government health services at central, provincial and peripheral levels and linkage with the immunization services (include an organization chart) | Document number: 2 |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in funding methods) and the implications for the immunization services | Document number: 3 |
| - Government policies on private sector participation in the immunization programme. | Document number: 0 |
| Profile of the Inter-Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC | Document number: 4 |
| - Minutes of the three most recent ICC meetings or any meetings pertaining to the introduction of new or under-used vaccines | Document number: 5 |
| Immunization services assessment |  |
| - Most recent national assessment report on immunization services | Document number: 6, 7, 8 |
| - Summary of the recommendations of the assessment report, describing the status of implementation of each recommendation. | Document number: 9 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number : 10,11 |
| - Action plan for introducing new or under-used vaccines into immunization services (if already included in the national multi-year plan, please indicate page and paragraphs) | Document number: 10 ANNEX 1 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number: 12 |
| - Agreement concluded with other agencies on sustainability strategy (namely VII) | Document number: 13 |
| - The priority given to immunization in poverty reduction strategies financed with funds freed up by debt relief (for countries targeted under the HIPC initiative) | Document number: 14 |

If possible, please submit hard copies and electronic versions of documents.