Revision  4

August  2002

The Government of

The Islamic Republic of Mauritania

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Islamic Republic of Mauritania is situated in West Africa between the 15th. and 27th. northern parallels, and has a surface area of 1 030 700 km2 with a population of 2 548 157 inhabitants, which gives a density of 2.5 inhabitants per km2. The annual population growth rate stands at 2.6%, and life expectancy at birth stands at 51.3 years of age.

- The main health indicators are the:

- Infantile death rate			74/1000

- The infantile/juvenile death rate 		116/1000

- The maternal death rate 			747/100,000 living births

- Gross death rate 				15,98/1000

- Inter-genetic interval			35 months

In our country, the Expanded Programme on Immunization started in 1977 at Keur Macène and Rosso, two experimental areas in Trarza, and was then gradually extended and became generalised in 1984.

It applied two strategies:

A fixed strategy via the maternal and infantile health services in urban areas.

A mobile strategy via mobile teams in rural areas.

A third strategy, also called the accelerated strategy, was introduced in 1985 during national and municipal immunisation days. This strategy was subsequently extended to the mograbin immunisation days from 1987 until 1994.

From 1995 onwards, Mauritania committed itself to eradicating poliomyelitis and controlling measles through the organisation of National Immunisation Days.

In 1996, the RIM opted for the Vaccination Independence Initiative (VII) by taking over costs of vaccines and consumables. The general objective of the EPI is to protect children aged 0-11months against tuberculosis, diphtheria, whooping cough, tetanus, poliomyelitis, mumps, and to protect women of procreation age (14-44) against tetanus. According to the routine health district report, the coverage rate for DTP-3 stoodat 61% in 2001, which accounts for 64,907 immunised infants.

For the period 2002-2006, the objectives of the EPI for each anti-gene are the following:

|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| BCG | 70 | 80 | 85 | 90 | 95 | 95 |
| DTP3/ Polio 3 | 61 | 70 | 75 | 80 | 85 | 90 |
| VAR | 58 | 65 | 75 | 85 | 90 | 95 |
| TT-2 + | 31 | 40 | 50 | 60 | 65 | 70 |
| Hepatitis B | - | - | 0 | 20 | 30 | 40 |
| Hæmophilus influenzae b | - | - | 0 | 20 | 30 | 40 |

The strategies adopted to reach these objectives are based on the following considerations:

- Enhancement of the fixed strategy

- A more dynamic advanced strategy.

- Reactivation of the mobile strategy.

- Gradual introduction of the innovative mobile strategy.

- Implementation of a national injection safety strategy.

- Enhancement of capabilities / new abilities through training, supervision, and continued strengthening of the EPI with human resources, at the central, regional, and peripheral levels.

- Improvement of social mobilisation.

- Improvement of planning standards, coordination, and management (enhancement of monitoring to make quality EPI data, including vaccine data, available right down to the decentralised level).

- Improvement of additional immunisation coverage through the organisation of mass campaigns or locating non-immunised populations.

- Improvement of performance of integrated epidemiological monitoring.

This supportive proposal to be submitted to GAVI was elaborated by a technical committee set up by the CNC/EPI, and has subsequently been amended and endorsed by all members of the committee.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of The Islamic Republic of Mauritania commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	Mr. Diop Abdoul Hamet……………………………….

Title:	Minister of Health and Social Affairs

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health and Social Affairs | Mr. Diop Abdoul Hamet: Minister of Health and Social Affairs |  |
|  | Dr. Dah Ould Cheikh: Secretary- General of the Ministry of Health and Social Affairs |  |
|  | Dr. Idoumou Ould Mohamed Vall: Director of Health Protection. |  |
|  | Dr. Mariem Takhla Mint Mohamed Hamed: Director of pharmacies and laboratories |  |
|  | Dr. Isagh Ould Khalef: National EPI Coordinator |  |
| Ministry of National Education | Mr. Aderrahmane Ould Mohamed Sidina |  |
| Ministry of Culture and Islamic Guidance | Mr. Mohamed Ali Ould Septy |  |
| Ministry of the interior, postal and telecommunications | Mr. Mohamed Hady Macina, technical counsellor of the Minister |  |
| Ministry of Defence | Dr. Barro Souleymane |  |
| Ministry of Communication and Relations with Parliament | Mr. Mohamed Addallahi Ould Boussery, technical counsellor of the Minister |  |
| Secretariat for the condition of Women | Mrs. Oumoulvadly Kamara |  |
| Ministry of Finance | Mr. Mohamed Cherif, technical counsellor of the Minister |  |
| French Cooperation | Mrs. Gaelle LEPAPE |  |
| WHO | Dr. Diallo M. Pathé: representative |  |
| UNICEF | Dr. Diallo Souleymane: representative |  |
| World Bank | Mr. Yves Dudivier: representative |  |
| Rotary International | Mr. Habibou Fall: representative |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Dr. Ishagh Ould Kalef			Title/Address: National EPI Coordinator

Tel.No.: (00222) 525 17 51  		            Head office for the protection of Health

Fax No.: (00222) 525 17 51			P.O.Box 1433 Nouakchott

E-mail: pevmas@yahoo.fr

Alternative address:

Name: Dr. Idoumou Ould Mohamed Vall	Title/Address: Director of Health Protection

Tel.No.: (00222) 525 12 27  		             P.O.Box 483 Nuakchott

Fax No.: (00222) 525 69 43

E-mail: dps@mauritania.mr

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 2 548 157 | GNP per capita | 480 $US |
| Surviving Infants* | 106 768 | Infant mortality rate | 74/ 1000 |
| Percentage of GDP allocated to Health | 2,32 | Percentage of Government expenditure for Health Care | 8.0 |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 48 | 70 | 75 | 12-23 months | - | - | Tuberculosis | 3 788 | 3 617 |
| DTP | DTP1 |  | 45 | 82 | 61 | 12-23 months | - | - | Diphtheria | 0* | 0 |
|  | DTP3 |  | 31 | 61 | 40 | 12-23 months | - | - | Pertussis | 445* | 1331 |
| OPV3 |  |  | 31 | 58 | 44 | 12-23 months | - | - | Polio | 0* | 0 |
| Measles |  |  | 28 | 58 | 62 | 12-23 months | - | - | Measles | 907* | 2 234 |
| TT2+ (Pregnant women) |  |  | 19 | 31 | 25 | 14-45 years | - | - | NN Tetanus | 1** | 11* |
| Hib3 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Hib | N/A | N/A*** |
| Yellow Fever |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Yellow fever | N/A | N/A |
| HepB3 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | hepB seroprevalence (if available) | 24*** | - |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |
|  |  | Infants ( > 6 months) | 81 | 94,9 | 58 |  |  |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: Recent efforts achieved the reactivation of the EPI (since May 2001) through the organisation of local multi-anti-gene immunisation campaigns, reactivation of the mobile strategy and consistent supervision, linked to improved gathering, analysis, and forwarding of routine data with a satisfactory completeness standard from the Moughataa’s (health districts) have helped routine immunisation coverage. All these aspects were not taken into account in 2000-2001 EDSM data.

- Summary of health system development status relevant to immunization:

The main objectives of the fourth health action plan (1981-1985) were to increase health protection, to prioritise preventative health care, and to generalise primary health care.

The main recommendations of the 1992-1996 national master plan suggested that the struggle against diseases and handicaps must be enhanced and integrated. The efforts made have indeed brought about a marked reduction in the incidence of certain key diseases such as poliomyelitis, measles, and maternal / post - natal tetanus, but the infantile and infant/juvenile death rates remain very high. Transmittable diseases and malnutrition are the main causes of morbidity and mortality affecting all age groups, and the use of preventative services still remains low.

Immunisation coverage has come a long way between 1991 and 2000, with continuous progress during its first phase, before stagnating and even falling since 1996. The National Immunisation Days organised since 1995 have been an extraordinary success, with immunisation coverage rates above 90%, but the polio virus is still around – as confirmed by a case with the domestic wild polio virus in March 2001.

Furthermore, the RIM has committed itself to the vaccination independence initiative since 1996 by taking over costs for the purchase of vaccines and consumables. This budget has been increased from 36 to 50 million.

The current health master plan (1998-2002) reconfirms the will to continue efforts to help the greatest number, in accordance with the commitments made by the government: poliomyelitis will be eradicated by 2005, post-natal tetanus will be eliminated to achieve an incidence of less than 1 case in 1000 living births, measles will be controlled to achieve an incidence reduction of 90% and to reduce its share in the cause of death by 95%. Immunisation against hepatitis B and haemophilus influenzae b will be introduced gradually to the EPI as of 2004.

In March 1999, the RIM was declared eligible for the debt reduction initiative for poor countries with very high debts (PPTE), where one of the conditions relative to health is the improvement of routine immunisation coverage, particularly with regard to DTP-3 which has to be increased to 70%.

Four main key issues have been outlined in the strategic context of efforts to alleviate poverty. The third key issue aims to develop human resources and access to essential infrastructures, and is the one that will have the most significant impact on poverty in the long run in the way it influences productivity and improves living conditions of the poor. Access to education and particularly health services considerably reduce vulnerability of the poor.

Medium term budget planning for the implementation of health strategies within the context of efforts to alleviate poverty has outlined three main categories of objectives to beat poverty:

- Improving the health indicators of the Mauritanian population with special emphasis on improving health indicators from the poorest groups, and a reduction of infantile, infant-juvenile, and maternal mortality (e.g. reducing infantile mortality in urban areas from 75/1000 in 2001 to 60/1000 by 2004.

- Limiting the impact of costs on the income of the poor.

- Improving the participation of the poor.

The bottom line is to increase health expenditure per inhabitant from 8 US Dollars in 1999,  14 US Dollars in 2002, to reach 16 US Dollars per inhabitant in the coming years.

| - Attached are the relevant section(s) of strategies for health system development |  |
| --- | --- |
| - National health master plan 1998-2002 (pages 36-59) | Documents number 1 and 2 |
| - Medium term budget planning 2002-2004 (pages 3-8, 20 and 29) |  |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC: Inter-Agency Coordinating Committee (ICC/EPI)

- Date of constitution of the current ICC: 05 February 2002

- Organisational structure (e.g., sub-committee, stand-alone): Logistical sub-committee, sub-committee for social mobilisation, epidemiological monitoring committee, and National Immunisation days sub-committee.

- Frequency of meetings: Once per month during the 1st. quarter of 2002, and one quarterly meeting during the second quarter.

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister of Health and Social Affairs | Mr. Diop Abdoul Hamet |
| Secretary | National EPI Coordinator | Dr. Ishagh Ould Kalef |
| Members | Secretary-General of the MSAS | Dr. Dah Ould Cheikh |
|  | Director of Health Protection | Dr. Idoumou Ould Mohamed Vall |
|  | Director of Pharmacies and Laboratories | Dr. Mariem Takhla Mint Ahmedou |
|  | Ministry of Education representative | Mr. Aderrahmane Ould Mohamed Sidina |
|  | Ministry of Culture and Islamic Guidance | Mr. Mohamed Ali Ould Septy |
|  | Technical counsellor from the Ministry of the Interior, Post Office, and Telecommunications | Mr. Mohamed Hady Macina |
|  | Ministry of Defense, representative & Head of the paediatric unit (military hospital) | Dr. Barro Souleymane |
|  | Technical counsellor from the Ministry of Communication and Relations with Parliament | Mr. Mohamed Abdallahi Ould Boussery |
|  | Representative from State Secretariat for the condition of women. | Mrs. Oumoulvadly Kamara |
|  | French Coperation representative | Mrs. Gaelle LEPAPE |
|  | Permanent WHO representative | Dr. El Hadi Benzerroug |
|  | Permanent UNICEF representative | Mrs. Ute Deseniss Gros |
|  | World Bank representative | Mr. Souleymane Sow |
|  | Rotary International representative | Mr. Habibou Fall |

- Major functions and responsibilities of the ICC:

- Elaboration of a national immunisation policy against infectious and potentially epidemic diseases that can be eradicated.

- Specifying the diseases targeted by the programme.

- Follow-up of the implementation of the immunisation programme.

- Defining objectives, strategies, and appropriate measures of the programme.

- Ensuring that activities of the programme take place as planned.

- Endorsing action plans and the implementation of multi-year sector plans for both immunisation and activity reports.

- Increasing awareness of all national and international partners ready to provide support to the expanded programme on immunisation.

- Supporting and encouraging the exchange of information and feed-back at the national level, and at the operational level with external partners.

- Coordinating activities  and commitments of partners.

- Ensuring that the partnership created by the national committee reveals itself as a positive driving force for both the routine EPI and the national immunisation days.

- Four major strategies to enhance the ICC’s role and functions in the next 12 months:

- Strengthening of cold chain logistics.

- Implementation of the strategic communications plan for development and social mobilisation.

- Enhancement of integrated epidemiological monitoring.

- Improvement of quality of the synchronised door-to-door national immunisation days.

- Four main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Drop-out rate between DTP-1 and DTP-3

- Vaccine wastage rate

- Integrated epidemiological monitoring (AFP)

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number 4 |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number 3 |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program (available) | Document number 5 |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Document based analysis of the routine EPI and disease monitoring. | MSAS/WHO/UNICEF | January 2000 |
| External review of the Expanded Programme on Immunisation in Mauritania, September 2001 to April 2002. | WHO/UNICEF/EPI Abidjan | April 2002 version |
| Demographic and health survey in Mauritania | MSAS/UNFPA/USAID / Central Statistics Office, National Statistics Office / WHO/UNICEF/UNDP/BM/ MACRO International | 2000-2001 |
| Strategic communications plan for development and social mobilisation. | MSAS/WHO/UNICEF | 2001 |

- The three major strengths identified in the assessments:

- Membership of the vaccine independence initiative

- Good storage capacity at the central level.

- Implementation of an integrated epidemiological monitoring system

- Creation a coordination committee for national communication, pleading, and social mobilisation programmes.

- The three major problems identified in the assessments:

- Low immunisation coverage

- Lack of communication means (radio, fax, e-mail, vehicles…)

- Insufficient social mobilisation

- The three major recommendations in the assessments:

Improvement of the quality of routine immunisation and integrated monitoring of diseases.

Enhancement of community participation and of social mobilisation.

Strengthening of additional immunisations.

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services (available) | Document number 6,7,8 |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress….(available) | Document number 9 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| EPI financing |  |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 10 |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Consultants | 2002-2004 | WHO/UNICEF/IDA |
| Training programmes | 2002-2003 | WHO/UNICEF/IDA |
| Management tools | 2002-2003 | WHO/UNICEF/IDA |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG & Polio 0 | At birth | x |  |  |
| DTP-1/ polio 1 | 6 weeks | x |  |  |
| DTP-2 / polio 2 | 10 weeks | x |  |  |
| DTP-3 / Polio 3 | 14 weeks | x |  |  |
| Measles | 9 months | x |  |  |
| TT-1 | Age 14+ / during pregnancy | x |  |  |
| TT-2 | 4 weeks after TT-1 | x |  |  |
| TT-3 | 1 year after TT-2 | x |  |  |
| TT-4 | 1 year after TT-3 | x |  |  |
| TT-5 | 1 year after TT-4 | x |  |  |
| Hepatitis B1 / Hib 1 | 6 weeks |  | X | The vaccines against hepatitis B and heamophilus influenzae 1b will be introduced in 2004-2005 in the cities of Nouakchott and Nouadhibou, and extended to the whole country from 2006 onwards |
| Hepatitis B2 / Hib 2 | 10 weeks |  | x |  |
| Hepatitis B3 / Hib 3 | 14 weeks |  | X |  |
| Vitamin A | 1st. doses after 6 months, 2nd. doses 6 months later | x |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

Improvement of immunisation quality through:

- The enhancement of the fixed strategy.

- The enhancement of the advanced strategy.

- The reactivation of the mobile strategy.

- The introduction of the new mobile strategy.

- The implementation of the national injection safety strategy.

- The enhancement of capabilities / re-training.

- Improvement of social mobilisation.

- Better planning and management quality.

- Strengthening of additional immunisations by the organisation of mass campaigns or identifying groups not yet immunised.

- Improvement of integrated epidemiological monitoring performance.

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births |  | 121037 | 124184 | 127413 |  | 10726 | 134125 | 137612 |  |  |
| Infants’ deaths |  | 74/1000 | 74/1000 | 72/1000 |  | 72/1000 | 70/1000 | 70/1000 |  |  |
| Surviving infants |  | 106768 | 109544 | 122392 |  | 115314 | 118318 | 121388 |  |  |
| Infants vaccinated with BCG* |  | 74943 | 87635 | 95533 |  | 103783 | 122397 | 115319 |  |  |
| Infants vaccinated with OPV3** |  | 64907 | 76681 | 84294 |  | 92251 | 100570 | 109249 |  |  |
| Infants vaccinated with 3 doses of DTP** |  | 64907 | 76681 | 84294 |  | 92251 | 100570 | 109249 |  |  |
| Infants vaccinated with the vaccine against hepatitis B** |  | N/A | N/A | N/A |  | 6226 | 9581 | 48555 |  |  |
| Infants vaccinated with the vaccine against haemophilus infuenzae b |  | N/A | N/A | N/A |  | 6226 | 9581 | 48555 |  |  |
| Infants vaccinated with Measles** |  | 62160 | 71204 | 84294 |  | 98017 | 106486 | 115319 |  |  |
| Pregnant women vaccinated with TT+ |  | 37751 | 49674 | 63707 |  | 78436 | 87181 | 96328 |  |  |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |
|  | Infants (> 6 months) | 384901 | 415691 | 426499 |  | 437588 | 448965 | 460638 |  |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

***The number of immunised infants was calculated for the cities of Nouakchott and Nouadhibou

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

- 1998: A study carried out to assess wastage rates in six wilayas highlighted the importance of wastage monitoring.

- 1998: Institutionalisation of vial supplies with 10 doses each.

- 1999: Elaboration of national guidelines for opened vials, and training of health agents on the policy of opened vials.

- 2000: Implementation of information technology based anti-gene management.

- 2001: Implementation EPI data management, including cold chain follow-up.

- 2002: Updating of guidelines on the use of opened vials in the context of guideline dissemination for EPI reactivation (ministerial circular).

- 2002: Setting up of systematic feed-back to the wilayas regarding vaccine monitoring.

- 2002: Training of regional key staff on the management of the programme, including vaccine management.

- 2002: Review of the vaccine supply plan at the central level (supplies twice annually instead of 1).

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate | 33.7% | 25 | 25 | 20 | 20 | 15 |  |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 24 | 20 | 15 | 10 | 7 | 5 |  |  |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

N/A

- Planning and constraints for the Polio Eradication Initiative:

Mauritania is a very large country with a very scattered population, a little developed communication network, and health coverage that still remains insufficient.

Performance data on the routine immunisation programme and monitoring of targeted diseases is often incomplete and late arriving. Data on immunisation coverage shows low rates for all anti-genes, including OPV, with high wastage rates that gain in potential with the low rates of use of health facilities. Synergies still need to be created between the monitoring units and management teams of the routine immunisation programme.

Since 1995, Mauritania has organised eradication campaigns against polio and the control of measles. Coverage rates of 90% have not made it possible to stop the wild polio virus from circulating (a case with the domestic wild polio virus was isolated in 2001). Hence the importance of carrying out synchronised door-to-door NID’s with the objective of reaching the final potential pockets of the wild virus responsible for a few exceptional cases of AFP.

The quality of NID’s will be improved in the short run, the active monitoring system strengthened, and campaigns to locate non-immunised groups will be organised if required. All in all, special emphasis will be placed on reactivating the routine EPI.

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

In order to contribute to the improvement of the state of health of the population, the government the Islamic Republic of Mauritania has committed itself to ensuring a safe and rational use of injections to avoid any risk to the person receiving these, and to those administering them, and to the community. The I.R.M has elaborated a multi-year plan for the implementation of the national injection safety strategy based on the following aspects:

2000: Generalisation of the use of auto-destruct syringes as EPI injection material.

2000: Survey of injection safety to identify weak spots.

2001:

Elaboration of the national policy project for injection safety.

Elaboration of the multi-year plan for the implementation of the injection safety policy based on the following aspects:

Training/re-training/ supervision of health staff (public and private sectors) in stock management, injection safety, rationalisation of prescriptions, and waste management.

A long-term approach to the budget policy for the purchase of vaccines and consumables.

A regular supply of injection and sample-taking material and single use consumables.

Information and education of, and communication with the community regarding injection safety.

Construction / refurbishing of incinerators.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 11 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 87635 | 95533 | 103783 | 112397 | 115319 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 87636 | 95533 | 103783 | 112397 | 115319 |
| D | AD syringes (+10% wastage) | C x 1.11 | 97275 | 106042 | 115199 | 124761 | 128004 |
| E | AD syringes buffer stock | D x 0.25 | 24319 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 121594 | 106042 | 115199 | 124761 | 128004 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 4864 | 5302 | 5760 | 6238 | 6400 |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1404 | 1236 | 1343 | 1454 | 1492 |

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.2: Estimated supplies for safety of vaccination with DTP ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 76681 | 84294 | 92251 | 100570 | 327747 |
| B | Number of doses per child (or per woman in case of TT) | # | 3 | 3 | 3 | 3 | 3 |
| C | Number of DTP doses | A x B | 230043 | 252882 | 276753 | 301710 | 327747 |
| D | AD syringes (+10% wastage) | C x 1.11 | 255348 | 280699 | 307196 | 334898 | 363799 |
| E | AD syringes buffer stock | D x 0.25 | 63837 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 319185 | 280699 | 307196 | 334898 | 363799 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |  |  |  |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 3543 | 3116 | 3410 | 3717 | 4038 |

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.3: Estimated supplies for safety of vaccination with VAR ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 71204 | 84294 | 98017 | 106486 | 115319 |
| B | Number of doses per child (or per woman in case of TT) | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of VAR doses | A x B | 71204 | 84294 | 98017 | 106486 | 115319 |
| D | AD syringes (+10% wastage) | C x 1.11 | 79036 | 93566 | 108799 | 118199 | 128004 |
| E | AD syringes buffer stock | D x 0.25 | 19759 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 98795 | 93566 | 108799 | 118199 | 128004 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 7904 | 9357 | 10880 | 11820 | 12800 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1184 | 1142 | 1328 | 1443 | 1563 |

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.4: Estimated supplies for safety of vaccination with TT ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 49674 | 63707 | 78436 | 87181 | 96328 |
| B | Number of doses per child (or per woman in case of TT) | # | 5 | 5 | 5 | 5 | 5 |
| C | Number of TT doses | A x B | 248370 | 318535 | 392180 | 435905 | 481640 |
| D | AD syringes (+10% wastage) | C x 1.11 | 275691 | 353574 | 435320 | 483855 | 534620 |
| E | AD syringes buffer stock | D x 0.25 | 0 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 275691 | 353574 | 435320 | 483855 | 534620 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |  |  |  |
| I | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 3060 | 3925 | 4832 | 5371 | 5934 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes | 2002 |
| GAVI/Vaccine Fund | Construction of incinerators | 2003 |
| GAVI/Vaccine Fund |  |  |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

The vaccine against hepatitis B will be introduced gradually to the routine  EPI as of 2004, initially in the two most populated cities of Nouakchott and Nouadhibou that represent 27% of the total population of the country. It will then be provided throughout the entire country as of 2006. A study of the haemophilus influenzae vaccine is to take place in 2003 to gather missing data on this subject prior to the planned introduction of this vaccine in the immunisation programme as of 2004. It is with this in mind that a regular and constant supply of vaccines and consumables has been taken into account in the multi-year plan that will be preceded by an enhancement of technical and logistical means. The introduction of the new vaccines will be accompanied by a monitoring and assessment process.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | Study of the prevalence of the HBS agent in blood donors at the national hospital centre. | 1996 | 24% |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines: N/A

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

The introduction of new vaccines will take into account:

The storage capacity of the central EPI that currently has two cold chambers: a positive one with 18m³, a negative one with 9m³. This is largely adequate for the annual routine EPI supplies, including the introduction of new vaccines (hepatitis B and haemophilus influenzae b).

The enhancement of technical know-how of agents in the field through the implementation of a training programme between 2002-2004.

Stricter supervision by the central level of the intermediary level, and by the intermediary level of the operational level (health districts) as part of the implementation of the EPI reactivation plan started in 2001.

The introduction of the freezing test at the intermediary and operational levels, application of guidelines regarding the policy on opened vials,  and implementation of cold chain follow-up standards.

Introduction of the monitoring system at the intermediary and operational levels in order to reduce high drop-out and wastage rates.

Improved road transport capacity with at least two already purchased (?) four wheel drive vehicles to help routine EPI activities at every Wilaya.

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses  of   ………...   vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  | Percentage of vaccines requested from The Vaccine Fund | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  |  |  |  |  |
| B | Number of doses per child | # |  |  |  |  |  |  |
| C | Estimated wastage rate in % | % |  |  |  |  |  |  |
| D | Estimated wastage factor | see list in table  |  |  |  |  |  |  |
| E | Number of doses | A x B x D |  |  |  |  |  |  |
| F | Vaccine buffer stock | E x 0.25 |  |  |  |  |  |  |
| G | Total vaccine doses requested | E + F |  |  |  |  |  |  |
| H | % of vaccines requested from the vaccine fund | % |  |  |  |  |  |  |
| I | Number of doses requested from the vaccine fund | G x H / 100 |  |  |  |  |  |  |
| J | Number of doses per vial | # |  |  |  |  |  |  |
| K | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  |  |  |  |  |
| L | Buffer stock of AD syringes | K x 0.25 |  |  |  |  |  |  |
| M | Total number of AD syringes | K + L |  |  |  |  |  |  |
| N | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  |  |  |  |
| O | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  |  |  |  |  |

Table 7.1: Estimated number of doses  of   hepatitis B  vaccine in 10 dose vials (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  | Percentage of vaccines requested from The Vaccine Fund | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | Match up with targets in table 4 |  |  | 6226* | 9581* | 48555* |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in % | % |  |  | 25 | 20 | 15 |  |
| D | Estimated wastage factor | see list in table  |  |  | 1,33 | 1,25 | 1,18 |  |
| E | Number of doses | A x B x D |  |  | 24842 | 35929 | 171885 |  |
| F | Vaccine buffer stock | E x 0.25 |  |  | 6211 | 0 | 0 |  |
| G | Total vaccine doses requested | E + F |  |  | 31053 | 35929 | 171885 |  |
| H | % of vaccines requested from the vaccine fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the vaccine fund | G x H / 100 |  |  | 31053 | 35929 | 171885 |  |
| J | Number of doses per vial | # |  |  | 10 | 10 | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  | 25572 | 31905 | 161688 |  |
| L | Buffer stock of AD syringes | K x 0.25 |  |  | 6393 | 7976 | 40422 |  |
| M | Total number of AD syringes | K + L |  |  | 31965 | 39881 | 202110 |  |
| N | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  | - | - | - |  |
| O | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  | 426 | 531 | 2243 |  |

* In 2004 & 2005: Immunisation will only take place in two cities (Nouakchott and Dahklet Nouadhibou).

** In 2006: Immunisation to take place in the rest of the country.

Table 7.2: Estimated number of doses  of   Haemophilus influenzae vaccine in 10 dose vials (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  | Percentage of vaccines requested from The Vaccine Fund | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  | 6226* | 9581* | 48555 |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in % | % |  |  | 25 | 20 | 15 |  |
| D | Estimated wastage factor | see list in table  |  |  | 1,33 | 1,25 | 1,18 |  |
| E | Number of doses | A x B x D |  |  | 24842 | 35929 | 171855 |  |
| F | Vaccine buffer stock | E x 0.25 |  |  | 6211 | 0 | 0 |  |
| G | Total vaccine doses requested | E + F |  |  | 31053 | 35929 | 171855 |  |
| H | % of vaccines requested from the vaccine fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the vaccine fund | G x H / 100 |  |  | 31053 | 35929 | 171855 |  |
| J | Number of doses per vial | # |  |  | 10 | 10 | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  | 25572 | 31905 | 161688 |  |
| L | Buffer stock of AD syringes | K x 0.25 |  |  | 6393 | 7976 | 40422 |  |
| M | Total number of AD syringes | K + L |  |  | 31965 | 39881 | 202110 |  |
| N | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  | 3447 | 3988 | 19079 |  |
| O | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  | 393 | 487 | 2455 |  |

* In 2004 & 2005: Immunisation will only take place in two cities (Nouakchott and Dahklet Nouadhibou).

** In 2006: Immunisation to take place in the rest of the country.

Table 7.3: Estimated number of doses  of  hepatitis B vaccine in one dose vials (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  | Percentage of vaccines requested from The Vaccine Fund | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  | 6226* | 9581* | 48555* |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in % | % |  |  | 5 | 5 | 5 |  |
| D | Estimated wastage factor | see list in table  |  |  | 1,05 | 1,05 | 1,05 |  |
| E | Number of doses | A x B x D |  |  | 19612 | 31031 | 152948 |  |
| F | Vaccine buffer stock | E x 0.25 |  |  | 4903 | 0 | 0 |  |
| G | Total vaccine doses requested | E + F |  |  | 24515 | 31031 | 152948 |  |
| H | % of vaccines requested from the vaccine fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the vaccine fund | G x H / 100 |  |  | 24515 | 31031 | 152948 |  |
| J | Number of doses per vial | # |  |  | 1 | 1 | 1 |  |
| K | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  | 26175 | 31905 | 161688 |  |
| L | Buffer stock of AD syringes | K x 0.25 |  |  | 6544 | 7976 | 40422 |  |
| M | Total number of AD syringes | K + L |  |  | 32719 | 39881 | 202110 |  |
| N | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  |  |  |  |
| O | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  | 363 | 443 | 2243 |  |

* In 2004 & 2005: Immunisation will only take place in two cities (Nouakchott and Dahklet Nouadhibou).

** In 2006: Immunisation to take place in the rest of the country.

Table 7.4: Estimated number of doses  of   haemophilus influenza vaccine in one dose vials (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  | Percentage of vaccines requested from The Vaccine Fund | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  | 6226* | 9581 | 48555** |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in % | % |  |  | 5 | 5 | 5 |  |
| D | Estimated wastage factor | see list in table  |  |  | 1,05 | 1,05 | 1,05 |  |
| E | Number of doses | A x B x D |  |  | 19612 | 31031 | 152948 |  |
| F | Vaccine buffer stock | E x 0.25 |  |  | 4903 | 0 | 0 |  |
| G | Total vaccine doses requested | E + F |  |  | 24515 | 31031 | 152948 |  |
| H | % of vaccines requested from the vaccine fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the vaccine fund | G x H / 100 |  |  | 24515 | 31031 | 152948 |  |
| J | Number of doses per vial | # |  |  | 1 | 1 | 1 |  |
| K | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  | 26175 | 31905 | 161688 |  |
| L | Buffer stock of AD syringes | K x 0.25 |  |  | 6544 | 7976 | 40422 |  |
| M | Total number of AD syringes | K + L |  |  | 32719 | 39881 | 202110 |  |
| N | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  | 27212 | 34444 | 169772 |  |
| O | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  | 665 | 825 | 4128 |  |

* In 2004 & 2005: Immunisation will only take place in two cities (Nouakchott and Dahklet Nouadhibou).

** In 2006: Immunisation to take place in the rest of the country.

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) (Available in the multi-year plan). | Document number 10, pages 6,16,20,21 |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

In order to increase the mobilisation of resources for the immunisation of infants, the government plans to:

- To rely more heavily on the national coordination committee for the EPI (ICC/EPI).

- Gradually increase state funding by benefiting from the HIPC initiative.

- Increasing community involvement in the financing of peripheral activities.

- Using the safety funds at the central level to finance the operating of the cold chain (purchase of gas, etc.).

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number 12 |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- Vaccines with costs that do not change with shipment size (new and other vaccines such as DTP and the polio vaccine whose cost varies slightly between 10 to 20%). A reduction of costs for these vaccines will mainly be achieved by reducing the wastage rate, where one of the main causes is the use of opened vials in small quantities.

- Vaccines with costs that change significantly with shipment size (e.g. TT: 49% higher cost of 20 doses compared to 10 doses). A reduction of costs for the latter does not only depend on reducing the wastage rate, and could be achieved by providing 20 dose shipments instead of 10 doses, even with high wastage rates.

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the ISLAMIC REPUBLIC OF MAURITANIA,

considering that its DTP3 coverage for 2001 was 61%,  corresponding to 64907 children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES

- Support for New and Under-used vaccines                                  YES

- Support for Injection Safety                                                          YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 11774 (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Hepatitis B (multi-dose) | 10 | 2004 | 31053 | 35929 |
| Haemophilus influenza | 10 | 2004 | 24842 | 35929 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

x

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 | 2006 |
| F | Total AD syringes | for BCG | 121595 | 106042 | 115119 | 142761 | 128004 |
|  |  | for other vaccines | 693671 | 727839 | 851315 | 936952 | 1026423 |
| I | Total of reconstitution syringes |  | 12768 | 14659 | 16640 | 18058 | 19200 |
| J | Total of safety boxes |  | 8891 | 9419 | 10913 | 11985 | 13027 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2001 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number……. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number……. |
| - Terms of reference of the ICC | Document number…… |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number…… |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number…… |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number…… |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…… |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…… Document number…… |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number…… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

General population and habitat survey of 2000

Demographic and health survey of 2000-2001

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible