The Government of

REPUBLIC OF TAJIKISTAN

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience.

Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.ch or representatives of a GAVI partner agency.

All documents and attachments must be submitted in English or French.

- Executive Summary

Sinopsis of the proposal including the specific requests for support from one or both sub-accounts – immunization services and/or new and underused vaccines. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DPT3 coverage and targets for increased coverage, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

A.

  - Strengthening and improvement of immunization services

  - Introduction of the new vaccine - hepatitis B

  - Assessment of burden of Hepatitis B

  - Training on safe immunization practices

B. Children under 1 (one) year received BCG/OPV/DPT/Measles vaccines in 1999

|  |  | GBAO* | Dushanbe | RSR** | Kurgan- Tube zone | Kulob zone | Sogdiyon Oblast | Total Republic |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Children |  | 4705 | 12451 | 37643 | 37495 | 21356 | 41633 | 155283 |
| BCG | # vaccinated | 4396 | 12449 | 36890 | 36445 | 20908 | 40967 | 152055 |
|  | % of coverage | 95,0 % | 100 % | 98,0 % | 97,2 % | 97,9 % | 98,4 % | 97,9 % |
| OPV | # vaccinated | 4450 | 12077 | 35008 | 36524 | 20309 | 40717 | 149085 |
|  | % of coverage | 95,0 % | 97,0 % | 93,0 % | 97,4 % | 95,1 % | 97,8 % | 96,0 % |
| DPT | # vaccinated | 4491 | 12102 | 34331 | 36183 | 20245 | 40709 | 148061 |
|  | % of coverage | 95,0 % | 97,2 % | 91,2 % | 96,5 % | 94,8 % | 97,8 % | 95,3 % |
| Measles | # vaccinated | 4643 | 11554 | 34895 | 28721 | 19199 | 40634 | 139646 |
|  | % of coverage | 99,0 % | 92,8 % | 92,7 % | 76,6 % | 89,9 % | 97,6 % | 89,9 % |
| Received Full vaccination | # vaccinated | 4438 | 11343 | 34481 | 28684 | 19187 | 40551 | 138684 |
|  | % of coverage | 94,4% | 91,1% | 91,6% | 76,5% | 89,9 | 97,4 | 89,3% |

* GBAO – Gorno Badakhshan Autonomy Oblast

** RSR  – Republican Subordinate Rayons

C. Baseline Data

|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # of birth | 158.097 | 159.150 | 160.500 | 161.110 | 162.700 | 163.330 | 163.800 |
| # of infants deaths | 2814 | 2737 | 2696 | 2626 | 2554 | 2483 | 2440 |
| Surviving infants | 155.283 | 156.413 | 157.804 | 158.484 | 160.146 | 160.847 | 161.360 |
| Drop out rate DPT1-DPT3 (%) | 4.7 % | 4.7% | 4.6% | 4.5% | 4.2% | 4.0% | 3.8% |
| # of children vaccinated with DPT 3 | 148.061 | 149.062 | 150.545 | 151.352 | 153.420 | 154.413 | 155.229 |

D. Tajikistan needs of vaccines and syringes in 2001

| Vaccine¦Syringes | BCG | OPV | DPT | Measles Primary | Measles Revaccin. | DT | BCG Revaccin. | Syringes 0.5 ml | Syringes BCG |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Targeted population | 160.000 | 158.000 | 158.000 | 158.000 | 150.000 | 150.000 | 150.000 | 310.000 | 310.000 |
| Vial size | 20 | 10 | 10 | 10 | 10 | 10 | 20 |  |  |
| No. of doses | 1 | 5 | 4 | 1 | 1 | 1 | 1 |  | 2 |
| Wastage rate | 2 | 1.3 | 1.2 | 1.2 | 1.2 | 1.2 | 1.3 | 1.05 | 1.05 |
| Total No. of doses Required | 320.000 | 1.027.000 | 758.400 | 189.600 | 180.000 | 180.000 | 195.000 | 1.974.950 | 325.500 |

- In May 2000 with the purpose of coordination of activities and efforts on strengthening immunization system in Tajikistan, as well as development of the proposal for support from the Global Alliance for Vaccine and Immunization, the Inter-agency Coordinating Coomittee was established. The activity and its membership was supported and approved by the Ministry of Health of Tajikistan on July

19, 2000, the Order # 225. The membership of the ICC included the leading specialist of health care system of the country and the representatives of all International agencies, involved in EPI in Tajikistan.

All questions of the proposal for support from GAVI have been discussed in details during the ICC monthly meetings and the drafts of the proposal have been also distributed among the ICC members several times for their comments and recommendations.

During the ICC meetings key questions on improvement and strengthening immunization sesrvices in Tajikistan have been also discussed. Ammendments, changes and recommendations have been done in :

- 2001-2010 National Program for Immunoprophylaxis ;

- 2000-2007 National Program for Hepatitis B Control and Prophylaxis ;

- Policy on Safe Immunization Practices ;

- New Immunization Schedule etc.

Thanks to joint collaboration of different agencies, involved in immunization services the first manual on «Safe Immunization Services» for primary vaccination level was developed, printed and distributed in October 2000.

The Inter-agency Coordinating Committee thanks the Global Alliance for Vaccines and Immunization for its initiative for support, as it was one of the main reasons and motivations for establishing the ICC in Tajikistan.

# 2.  Signatures of the Government

The Government of 	          THE REPUBLIC OF TAJIKISTAN____

commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:	                                     /N.M. Sharopova/__

Title:	        Deputy Prime-Minister of Tajikistan    ___

Date:	         December 18 2000    ____________

The GAVI Secretariat is unable to return submitted documents and attachments to

individual countries. Unless otherwise specified, documents may be shared with the

GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | ### Date Signature |
| --- | --- | --- |
| Ministry of Health | Rofiev H.K. – Deputy Minister |  |
| Ministry of Health | Olimova K.S. – Deputy Minister |  |
| Republican Centre for Immunoprophylaxis | Jabirov Sh.S. – General Director |  |
| Ministry of Health | Sharipova B.B. – Head of Finance Department |  |
| Ministry of Health | Vohidov A.B.- Head of Mother & Child Care Department |  |
| Ministry of Health | Shahobova S.A. – Chief Pediatrician |  |
| Ministry of Health | Odinaev H.O. – Head of San-Epid. Dep. |  |
| Health Care Reform Project | Mirzoeva Z.A. – Project Manager |  |
| Project Implementation Unit Health/World Bank | Sheralieva M.M.- Executive Director |  |
| Republican SES | Shoismatulloev B.Sh. – Chief Doctor |  |
| National Red Cross Society | Inomov D.I. – Chairman |  |
| World Bank | Bazarova S. – Project Officer for Social Sector |  |
| WHO | Artykova N.P. - Coordinator |  |
| UNICEF | Kurbanov S.K. – Project Officer Assistant |  |
| USAID | Muhidov R. – Program Coordinator |  |
| Suppoprted by UNICEF | Ibod Sharifi – EPI National Consultant |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : Shamsiddin Jobirov		Title/Address : 	General Director__

Tel.No. : (992372) 27-62-94 _   		              	8 Chapaev Street,__

Fax No. : (992372) 21-10-34 		             	Dushanbe,______

E-mail : immun@rci.tajik.net                         	 	Tajikistan, 734025_

Alternative address:

#### Name:    	Ibod Sharifi___	Title/Address:        EPI National Consultant

Tel.No.:    (992372) 27-71-92_			 ___8 Chapaev Street______

Fax.No.:    (992372) 21-10-73_			 ___Dushanbe,              ____

E-male:      demos@tajik.net__			 ___Tajikistan, 734025     __

3.  Immunization-related fact sheet

Table 1 : Basic facts in 1999

| Population (1999) | 6.100.000 | GNP per capita | 1999 – 297 2000 – 350 $US |
| --- | --- | --- | --- |
| Infants 0-11 months | 155,283 | Infant mortality rate | 1998 – 23,4 1999 – 17,8 / 1000 |
| Percentage of GDP allocated to Health | 1999 – 1,6 % 2000 – 1,1 % | Percentage of Government expenditure for Health Care | 1999 – 5,6 % 2000 - 6,4 % |

* Surviving infants = Infants surviving the first 12 months of life

Table 2 : Immunization coverage and disease burden trends

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases cases/deaths |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 98,0% | 97,9% | - | 89% | Tuberculosis | 1209/31 | 1358/42 | 4460/155 | 9500/210 |
| DTP1 DPT DTP3 Wastage rate (%) | 97,8% | 98,0% | - | 84% | Diphtheria | 166 | 35 | 235/0 | 70/0 |
|  | 93,0% | 95,3% | - | 73% | Pertussis | 66 | 80 | 110/0 | 90/0 |
|  | 23% | 20% | - | 21 % |  |  |  |  |  |
| OPV3 | 94,0% | 96,0% | - | 78% | Polio | 0 | 0 | 0 | 0 |
| Measles | 94,0% | 89,9% | - | 61% | Measles | 3070 | 177 | 920/0 | 1.500/0 |
| Wastage rate | 25% | 20% | - | 20,2% |  |  |  |  |  |
| TT2+ Pregnant Women | - | - | - | - | NN Tetanus | 0 | 0 | 0 | 0 |
| Hib (specify presentation) | - | - | - | - | Hib | 0 | 0 | 0 | 0 |
| Yellow Fever | - | - | - | - | Yellow fever | 0 | 0 | 0 | 0 |
| HepB (specify presentation | - | - | - | - | HepB seroprevalence (if available) | 270 | 311 | 375/0 | 520/0 |

- The sources of these reports are:

- Republican Centre for Immunoprophylaxis___________________________________________________

- Information Center of the Ministry of Health__________________________________________________

(2)   These data are collected from the following survey:

- Multi Indicator Cluster Survey (MICS), conducted by UNICEF and State Statistics Agency in July 2000__

- Summary of health system development status :

Health care system in Tajikistan remains in critical state due to lack of repairs of health facilities, medical equipment, and the lack of motivation of health workers because of low salary ($3,61 per month). A growing number of vulnerable people were deeply affected by the dramatic economic recession and lack of access to essential primary health care. Although epidemics of communicable diseases, including diphtheria, typhoid and malaria, were controlled during 1998, they remain a burden on existing health services. The Ministry of Health and International agencies working in Tajikistan agreed to limit the scope of the following years health component to life-saving and essential health interventions. In particular, it was decided to focus on reducing mortality and morbidity from communicable diseases with potentially high mortality, rehabilitating hospitals and clinics.

Nevertheless, in spite of limited resources there is some progress in improving case management, promoting health sector reform and updating medical equipment.

The incidence of most EPI target diseases in Tajikistan is similar to that in neighboring countries, however cases of diphtheria are still registered (35 cases in 1999). Measles is also target disease, which requires special attention (177 cases in 1999 and 192 cases in 2000 for 10 months), as well as hepatitis B, rubella and mumps.

The Ministry of Health, with the support of WHO and UNICEF, developed a 1994-2000 National Programme on EPI, and managed to maintain a high level of vaccination coverage: BCG (against TB) 98 percent; DPT 95 percent; polio 96 percent; measles (1dose) 95 percent. In the 2001-2010 National Programme for Immunoprophylaxis hepatitis B vaccination has been also included in the routine immunization schedule. It is planned to introduce this vaccine starting from July 2001 if the donors, in particular the Global Alliance for Vaccines and Immunization (GAVI) provides the hepatitis B vaccine and AD syringes.

With the assistance of WHO/EURO in 1999 the Government initiated the Somoni Health Project to develop a “master plan” for health care reform action. Through this work Tajikistan has developed the first draft of its strategic vision and action plan for the country’s future health care system. Phase II of the project plans to build a national capacity for implementation of health care reforms and improve health status of the population of Tajikistan by ensuring a sustainable health care system which promotes health gain, equity and efficiency.

Supporting documents: (only copies of relevant pages are attached)

- Overall government health policies and strategies					Document number       1_

- Structure of the government health services and how it relates to immunization

services (with an organizational chart)						Document number       2__

- The Presidential Programme of the Republic of Tajikistan on Health Care Reform (a draft)	Document number       3__

- Government policies and practices on private sector participation, as it relates to

Immunization services 								Document number       4__

# 4.   Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services in the country, are co-ordinated and organized through an inter-agency coordinating mechanism which is referred to in this document as ICC.

- Name of the ICC     Inter-Agencies  Co-ordinating Committee on Immunoprophylaxis_

- Date of constitution of the current ICC  –              May 25, 2000____________________

- Organizational structure (e.g., sub-committee, stand alone) -      Stand alone____________

- Frequency of meetings –            Monthly____________________________________

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Deputy Minister/Ministry of Health | Kh. Rafiev |
| Secretary | Epidemiologist/Republican Center for Immunoprophylaxis | S. Turkov |
| Members | Deputy Minister/Ministry of Health General Director/Republican Centre for Immunoprophylaxis Head of Finance Department/Ministry of Health Head of Mother & Child Care Department/Ministry of Health Chief Pediatrician/Ministry of Health Head of San-Epidemiological Department/Ministry of Health Project Director/Health Care Reform Project Executive Director/Project Implementation Unit Health Chief Doctor/Republican SES Chairman/National Red Cross Society Project Officer for Social Sector/World Bank Coordinator/WHO Program Officer/USAID Project Officer Assistant/UNICEF EPI National Consultant/Supported by UNICEF | Olimova K.S. Jabirov Sh.S. Sharipova B.B. Vohidov A.B. Shahobova S.A. Odinaev H.O. Mirzoeva Z.A. Sheralieva M.M. Shoismatulloev B.Sh. Inomov D.I. Bazarova S. Artykova N.P. Muhidov R. Kurbanov S.K. Ibod Sharifi |

- Major functions and responsibilities :

- Coordination of activities and efforts on strengthening immunization system ; - Revising Programs and National documents on improving and strengthening immunization system and different diseases control ; - Ensuring and facilitating support from the Government to immunization services; - Assistance in solving the issues of health facilities supply with cold chain equipment, vaccine, etc; - Promoting the EPI priority issues and ensuring that these issues get feedback by the Central government and local officials (Hukumats) ; - Facilitating information sharing and feedback among different implementing units and partners, involved in immunization services in and outside the country.

- Functional relationship of the ICC with other institutions in health sector : (diagram)

Ministry of Health International Agencies WHO, UNICEF, USAID, World Bank, ADB, MERLIN, MSF (Holland), AKF Academic Corps Inter-Agencies Coordinating Committee on Immunoprophylaxis Republican Center for Immunoprophylaxis - Health Reform Project - Project Implementation Unit Health/World Bank - National Red Cross NGOs Civic Society National Institutions

- Three major strategies to enhance ICC’s role and functions in the next 12 months :

- Ensure the support from the Ministry of Health in advocating health care services issues before the

Government ;

- Ensuer technical support from UNICEF to have a program officer on EPI in the country ;

- Ensure that WHO regularly shares with the information materials related to the efforts and achievements on immunization services in other countries.

- Three main indicators (in addition to DPT3 coverage) that are chosen by the ICC to monitor implementation of this proposal

- % of oblast and rayon level staff that demonstrate a knowledge of the performance indicators ;

- Vaccine stock levels reflect needs at each facility ;

- % of providers who demonstrate understanding of hepatitis B vaccination policy.

Attached are the supporting documents :

- ICC’s Workplan in 2001 year							Document number    5__

- Terms of reference of the ICC 			    				Document number    6__

- Minutes of the three most recent ICC meetings or of any other

meetings in which partners participated that concerned improving 			Document number    7__

and expanding the national immunization program

# 5.   Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| 1. Vaccine Cold Chain and Logistics for Polio Eradication (Alasdair Wylie) ; 2. Rapid Assessment of AFP Surveillance and Polio Eradication in Tajikistan (Steven Wassilak) ; 3. A Review of Immunization Activities in Tajikistan (Anthony Battersby). 4. MICS – Multi Indicator Cluster Survey | WHO WHO UNICEF UNICEF State Statistics Agency | 15-20 August 2000 22-30 May 2000 2-25 August 2000 6-30 July 2000 |

- The three major problems identified in the assessments :

- Cold chain supplies and equipment in many areas are either not available, or old and beyond their useful life (in some Oblasts up to 60% of refrigerators are not functioning). - Increasing number of babies born at home often without any medical assistance and many children are not being registered and immunizaed. - Problems with injection safety (a shortage of safety boxes to hold all used syringes).

- The three major recommendations in the assessments :

- Develop new strategies to ensuer that safe storage of freeze sensitive vaccines such as DPT and hepatitis B need to be put in place. - Means need to encourage pregnant women to deliver at maternity houses not at home. If this proves impossible at present midwives based at medical houses or SVA should attend the birth at home and the patronage nurse should make sure that the child is registered with the health service and brought for immunization ; - UNICEF should order an additional 60,000 safety boxes. A procedure needs to be developed to ensure that filled safety boxes can be accounted for and to show that they have been safely destroyed. Fund raising to provide the necessary finance to provide a network of suitable incinerators should be started.

- Attached is a complete copy (with an executive summary) of :

- the most recent assessment report on the status of 			Document  number     8__

immunization services

- a list of the recommendations of the assessment report with		Document  number     9__

remarks on the status of their implementation i.e. included in

workplan, implemented, not implemented, in progress….

- Components or areas of immunization services that yet to be reviewed (or studied).

| ##### Title of the assessment | Month/Year |
| --- | --- |
| - A cold chain equipment survey on the volume of equipment available and the volume needed, proper usage. - Vaccination of children in the area with poor or lack of primary health care, as well as poor or lack of cold chain management by team (brigade) method - Role of International and local NGOs in strengthening immunization services and survey of the immunization coverage in all Oblasts and rayons of the country according to WHO cluster method. - Assessment of early registration of newborn children delivered at home. - Assessment of burden of hepatitis B in the country with the support of WHO. - Assessment of the activity on active AFP surveillance in «silent» areas and at less than 80% of standards. | Dec. 2000 г.-Jan.2001 January 2001 г. February-March 2001 г. April-May 2001 г. June-July 2001 г. August-September 2001 г. |

# 6.   Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

- Attached is a complete copy (with executive summary) of  the 		Document number       10_

Multi-Year Immunization Plan or of the relevant pages of the

health sector plan.

- Table 3 :  Vaccination schedule with traditional and new vaccines (add/correct/fill in as appropriate)

| AGE | Visit | Traditional antigens |  |  |  | New vaccines (specify presentation) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Birth | 1 | OPV-0 |  |  |  | hep B-1 |  |  |
| 3-5 days | 2 |  | BCG-1 |  |  |  |  |  |
| 2 months | 3 | OPV-1 |  | DPT-1 |  | hep B-2 |  |  |
| 3 months | 4 | OPV-2 |  | DPT-2 |  |  |  |  |
| 4 months | 5 | OPV-3 |  | DPT-3 |  | hep B-3 |  |  |
| 12 months | 6 | OPV-4 |  |  | Measles-1 |  |  |  |
| 16-23 months | 7 |  |  | DPT-4 |  |  |  |  |
| 6 years | 8 |  | BCG-2 | DT | Measles-2 |  |  |  |

* For newborn infants in maternities hepB vaccine dose 1 (HepB1) will be administered during the first 24 hours and

continued according to the current schedule.

For newborn infants delivered at home hepB-1 will be given the soonest the possible and continued according to

the current schedule along with DPT1 and DPT3.

- Table 4.1 : Baseline and annual targets

|  | Baseline | Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| # of birth | 158.097 | 159.150 | 160.500 | 161.110 | 162.700 | 163.330 | 163.800 |
| # of infants’ deaths | 2814 | 2737 | 2696 | 2626 | 2554 | 2483 | 2440 |
| Surviving infants | 155.283 | 156.413 | 157.804 | 158.484 | 160.146 | 160.847 | 161.360 |
| Drop out rate {DPT1-DPT3}/DPT1}x100 | 4.7% | 4.7% | 4.6% | 4.5% | 4.2% | 4.0% | 3.8% |
| Children vaccinated with DPT 3 | 148.061 | 148.526 | 150.860 | 151.352 | 153.420 | 154.413 | 155.229 |
| Children vaccinated with measles | 139.646 | 142.838 | 144.358 | 146.112 | 147.384 | 148.145 | 159.228 |
| Children vaccinated with hepB* | 0 | 0 | 55,232** | 126,787 | 136.124 | 144.762 | 153.292 |

*    Number of children targeted for vaccination with hepB = number of surviving infants x estimated vaccination with  3 doses of hepB vaccine (70% in 2001, 80% in 2002, 85% in 2003, 90% in 2004 and 95% in 2005);

** HepB vaccination will be introduced in July 2001, therefore the target is calcualated using 50% of surviving infants

x 70% coverage with 3 doses.

- Summary of major action points and timeframe for improving immunization coverage :

- Vaccination of children in the area with poor or lack of primary health care, as well as poor or lack of cold chain management by team (brigade) monthly method	(Starting from March 2001) ;

- Involve International and local NGOs in the survey of the immunization coverage in all Oblasts and rayons of the country according to WHO cluster method in order to identify not-vaccinated children and report to health facilities (Starting from March 2001);

- Ensure local officials (Hukumats) to find means in order to encourage women to deliver at maternity houses and not at home (The MOH will apply to the Central Government with a request to issue a special Order on this issue).

- Summary of the major action points and timeframe for reduction of vaccines wastage rate :

- Strict follow of the WHO open vial policy  		- 	on regular base

- Careful planning of vaccine estimation 			-	October of each year

- Proper distribution of vaccines according to real needs	-	on regular base

- Conducting training of health staff 			- 	quarterly a year

- Conducting monitoring of vaccine wastage		- 	on regular base

Table 4.2 : Estimate of annual DPT wastage rates

|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DPT wastage rate | 20,0% | 20,0% | 18,0% | 18,0% | 15,0% | 10,0% | 10,0% |

- Summary of the safe immunization plan (Guidelines on Country Proposal # 3.) :

- Timely collecting needed vaccines from Oblast/Rayon SES;

- Checking the date of expire of vaccines;

- Transporting (cold boxes, vaccine carriers, thermoses with ice-packs) and keeping vaccines in proper temperature (refrigerators, cold boxes, thermoses);

- Checking indicator cards and registering temperature of the refrigerator in the register book;

- Timely notifying the mothers about the vaccination dates;

- Encouraging mothers to bring their children to the health facility and vaccinate them their;

- Using the vaccines and diluents of the same production and the same series, and according to the provided instructions;

- Providing examination of the child before the vaccination;

- Using separate syringes and needles for different injections;

- Using different bandages for wiping the open vial and other bandage for wiping the skin of the child;

- Providing injection with DPT and DT vaccine in leg and delta muscle;

- Informing mothers on possible consequences, which may take place after vaccination and taking measures on them;

- Keeping open vials in the hole of the ice-pack during the vaccination;

- At the end of the working day boiling all open vials within 1 hour and destroying them;

- Collecting all used syringes in safe boxes and destroying them (at the moment they are burnt in special ovens. There is a plan to purchase incinerators in order to destroy used syringes).

Attached is a copy of the relevant pages of the 2001-2010 National Programme		Document number _11__

on Immunoprophylaxis of the plan Plan to achive Safe Injections (including plans

for transition to auto-distruct syringes) and Safe Management of Sharps Waste.

- Constraints and planning for Polio Eradication Initiative  :

- Possible immigration from the neighboring Afghanistan because of the war and import of wild virus transmission;

- No cases of Polio;

- Need to improve active surveillance for AFP in “silent” zones;

- Getting confirmed laboratory analyses on all cases of polio and AFP;

# Plan for Achievement of Polio Eradication Certification in 2003

| Strategies | Action steps | Responsible party | Dates |
| --- | --- | --- | --- |
| 1. Strengthening active AFP surveillance | 1.1. Conduct series of training workshops (for SES staff and key clinicians) on AFP surveillance, case definition, case classification, case investigation, and specimen collection and handling. | MOH | Quarterly |
|  | 1.2. Conduct a comprehensive inventory of the presence and state of specimen carriers and supply if there are needs. | RCI, UNICEF | Dec. 2000 - Jan. 2001 |
|  | 1.3. Summarizing the work and findings of the mobile teams and send to the WHO/EURO field office in Almaty | MOH RCI | Quarterly |
|  | 1.4. Review all available information for initial submission of national documentation to the Regional Certification Commision. | National Certification Committee | June 2001 |
|  | 1.5. Develop a plan for response to a reported case of imported polyomyelitis. | National Certification Committee | July 2001 |
| 2. Ensure accuarate and proper performance of AFP surveillance | 2.1. Generate Oblast/Rayon level reports and provide feedback to staff and key cliniccians. | RCI SES | Monthly |
|  | 2.2. Conduct survey and technical assistance to « silent » areas and areas at <80% of the standards. | RCI WHO | Aug-Sep 2001 |
|  | 2.3. Print and distribute to all staff involved information on the global and regional polio eradication efforts. | WHO RCI | Quarterly |

7.  New and under-used vaccines

Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines (Guidelines on Country Proposal # 4.4).

- (if new and under-used vaccines have been already introduced)

Implications for storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc … in relation to the current experience with new and under-used vaccines :

- Required number of doses and presentations of  Hepatitis B vaccine

Table 5 : Estimated number of doses of heaptitis B vaccine :

|  | 2001* | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Actual number of children to receive new vaccine – Hepatitis B | 55.232 | 126.787 | 136.124 | 144.762 | 153.292 |
| Number of doses per vaccinated child | 3 | 3 | 3 | 3 | 3 |
| Estimated wastage rate in % for 10 doses vials | 20% | 20% | 15% | 10% | 10% |
| Estimated wastage rate in % for 1 dose vials | 5% | 5% | 5% | 5% | 5% |
| Wastage factor | 1.25 | 1.25 | 1.2 | 1.1 | 1.1 |
| Buffer stock factor for vaccines | 20% | NA | NA | NA | NA |
| Total vaccine doses required | 220.375 | 365.150 | 375.700 | 406.060 | 429.980 |
| Percent age of vaccines requested from the Fund (%) | 100% | 100% | 100% | 100% | 100% |
| Number of doses requested from the Fund | 220.375 | 445.025 | 461.460 | 474.460 | 502.410 |
| Preferred vial size(s) - 1 dose (monoval.) | 34.795 20% | 79.875 (20%) | 85.760 (20%) | 68.400 (15%) | 72.430 (15%) |
| - 10 doses (monoval.) | 185.580 | 365.150 | 375.700 | 406.060 | 429.980 |
| AD syringes (include maximum 5% wastage) | 231.400 | 383.400 | 394.500 | 426.400 | 451.400 |
| Total number of safety boxes requested from the Fund | 2.314 | 3.834 | 3.945 | 4.264 | 4.514 |

- Number of children targeted for vaccination with hepB = number of estimated surviving infants x estimated vaccination coverage with 3 doses of  hepB vaccine (70% in 2001, 80% in 2002, 85% in 2003, 90% in 2004 and 95% in 2005)

- Introduction of hepB vaccination will start in July 2001, thus 50% of surviving infants are targeted.

- Total doses calculated each year = target number of children x  number of doses per vaccinated child x % of estimated wastage rate.

- Estimated number of syringes = target number of children x  doses x wastage factor (5 %).

- NA – not allowed

  - Summary of the action points that address possible implications for storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of Hepatitis B vaccine :

- Assessment of current baseline vaccine wastage and specific reasons for wastage before the introduction of hepatitis B vaccine ;

- Careful planning of vaccine estimation and distribution;

- Regular monitoring of vaccine wastage;

- Careful planning of cold chain equipment maintenance according to volume needs;

- Survey of cold chain equipment in the whole country to establish its location and condition, as well as to compare the volume of the equipment available with the volume needed for all vaccines, including hepatitis B vaccine and if necessary reallocate equipment to suite (Spring 2001);

- Repair all broken equipment with the support of UNICEF (Spring 2001);

- Regular training (quarterly) with health staff on safe immunization practices, including hepatitis B introduction;

- Training on HBV injection and social mobilization of the population on awaring the introduction of the new vaccine.

- As for all EPI forms, administartive and training materials, as immunization schedule, immunization cards, reporting forms etc. have been already reviewed and updated and hepatitis B have been included. In early of 2001 with the support of UNICEF it is planned to print and distribute them during the first training.

- Assessment of burden of hepatitis B:

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
|  | Assessment has not been conducted yet. |  |  |
|  | It is planned to conduct assessment with the support of WHO in April-May 2001. |  |  |

- Attached is the Program for Hepatitis B control and Prophylaxis		Document number _12__

in 2000-2007 years

- Strategic directions to mobilise additional resources for immunization

  - Summary of startegies that the Government intends to pursue to increase the resources for immunization of children, (Guidelines on Country Proposal # 4.3, 4.4, 5.) and that will be converted in a comprehensive « Resource Mobilization Plan » by the time of the mid-term Review (Guidelines on Country Proposal # 6.1.) :

- Develop close professional links with WHO health reform project to test alternative models for the provision of sustainable immunization services;

- Actively involve International and local NGOs in the support and evaluation of the immunization services ;

- Liaise with relevant Hukumats (local officials) to allocate funds for health staff wages, fuel for SES vehicles and routine maintenance, and to repair cold chain equipment;

- Liaize with the Central Government to raise the priority given to health, in particular starting to allocate budget for vaccines procurement, such as BCG, Measles, DT, Td :

    - in 2002-2003 years – 10%

    - in 2004-2005 years – 20 %

  - Table of expenditure for 1999 and 2000 and resource needs detailing the		Document number __13__

sources of funds are attached in Annex 1.

- List of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e : Vaccine Independence Initiative) : (the relevant documents are attached)

| ###### Title | Partners |  |
| --- | --- | --- |
| 1. Medium-term Programme of collaboration between the Ministry of Health of Tajikistan and the Regional Office for Europe/WHO in 2000 – 2001 years | WHO, MOH | Document number 14 |
| 2. Master Plan of Operation in Tajikistan for the period 2001-2004 | UNICEF, MOH | Document number 15 |
| 3. Project « Safe and Sustainable Immunization Services » | UNICEF | Docement number 16 a |
| 4. Project « Expanded Program on Immunization (Strengthening the surveillance system related to EPI target areas) | WHO | Document number 16 b |
| 5. Somoni Health Care Reform Project | WHO | Document number 16 c |

- Summary of support to immunization generated from the poverty			Document number     NA__

Reduction strategies (including the use of funds freed by debt relief)

- Summary of requests to GAVI/GFCV

With reference to all points presented above, the Government of     The Republic of Tajikistan___

- being eligible for support from the Global Alliance for Vaccines and Immunization (GAVI) and the Global Funds for Children’s Vaccines (The Fund),

- considering that DPT3 coverage for 1999 was 73 % corresponding to MICS EPI survey >1 number of children vaccinated with DPT3.

hereby requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government does hereby apply to receive support from the Fund :

###### Yes

- IMMUNIZATION SERVICES SUB-ACCOUNT

To provide funds for strengthening immunization services in 2001 according to the number of additional children that are targeted to be immunized with DPT3, as presented in table 4.1, namely Baseline and annual targets (vaccines procurement, training, assessment etc.)

- Transfer of funds from the immunization services sub-account will be by :

Government		A Partner Agency		An independent

-

+

-

UNICEF			thisrd party

AND

Yes

- NEW AND UNDER-USED VACCINES SUB-ACCOUNT

To supply the hepatitis B vaccine :

Table 6

|  | Presentation | Starting month and year | Number of Doses requested for the first calendar year | Vaccines will also be requested for following 2002-2005 years as described in tables 5 |
| --- | --- | --- | --- | --- |
| hep B | Monovalent | July 2001 | 220.375 |  |
|  | (1) 1 dose vail (2) 10 dose vail |  | 34.795 185.580 |  |

- Vaccines will be procured :

+

By UNICEF			By  GOVERNMENT

10.   Additional comments and recommendations from the ICC

- UNICEF – to strengthen the information system of immunization services ;

- WHO/UNICEF provide training materials on safe immunization practices in local language (Tajik) ;

- WHO provide training package on Hepatitis B ;

- WHO - regular sharing information on immunization services and recommendations on improvement and strengthening on the basis of experience of other countries (in Russian language).

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 1 UNICEF | Donor 2 WHO | Donor 3 АКF | Donor 4 | Total Expenditure in 1999 |
| 1. | Vaccines, AD syringes… | 0 | 0 | 0` | 429.600 | 0 | 0 |  | 429.600 |
| 1.1 | - BCG vaccine |  |  |  | 15.600 |  |  |  | 15.600 |
| 1.2 | - DPT vaccine |  |  |  | 19.250 |  |  |  | 19.250 |
| 1.3 | - Polio vaccine |  |  |  | 233.450 |  |  |  | 233.450 |
| 1.4 | - Measles vaccine |  |  |  | 43.300 |  |  |  | 43.300 |
| 1.5 | - AD syringes |  |  |  | 118.000 |  |  |  | 118.000 |
| 2. | Equipment (cold chain, spare parts, sterilization…) | 0 | 0 | 0 | 8,800 | 0 | 0 |  | 8.800 |
| 2.1 | - Safety boxes |  |  |  | 8.800 |  |  |  | 8.800 |
| 2.2 | - Refrigerators |  |  |  | 0 |  |  |  |  |
|  | - Spare parts |  |  |  | 0 |  |  |  |  |
|  | - Cold boxes |  |  |  | 0 |  |  |  |  |
| 3. | Other item immunization specific | 73.500 | 0 | 0 | 5.000 | 18.500 | 2.240 |  | 99.240 |
| 3.1 | - Technical assistance | 0 |  |  | 2.000 | 3.600 | 0 |  | 5.600 |
| 3.2 | - Training | 0 |  |  | 3.000 | 5.400 | 0 |  | 8.400 |
|  | - Salary | 69.800 |  |  | 0 | 0 | 0 |  | 69.800 |
|  | - Other operational cost | 3.700 |  |  | 0 | 9.500 | 2.240 |  | 15.440 |
| Total expenditure in 1999 |  | 73.500 | 0 | 0 | 443,400 | 18.500 | 2.240 |  | 537.640 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 1999 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 UNICEF | Donor 2 WHO | Donor 3 AKF | Donor |  |  |
| 1. | Vaccines, AD syringes… | 0 | 0 | 0 | 429.600 | 0 | 0 |  | 429.600 | 0 |
| 1.1 | - BCG vaccine |  |  |  | 15.600 |  |  |  | 15.600 | 0 |
| 1.2 | - DPT vaccine |  |  |  | 19.250 |  |  |  | 19.250 | 0 |
| 1.3 | - Polio vaccine |  |  |  | 233.450 |  |  |  | 233.450 | 0 |
| 1.4 | - Measles vaccine |  |  |  | 43.300 |  |  |  | 43.300 | 0 |
| 1.5 | - AD syringes |  |  |  | 118.000 |  |  |  | 118.000 | 0 |
| 2. | Equipment (cold chain, spare parts, sterilization…) | 0 | 0 | 0 | 8.200 | 0 | 0 |  | 66.500 | 58.300 |
|  | - Safety boxes |  |  |  | 8.200 |  |  |  | 12.000 | 3.800 |
| 2.1 | - Refrigerators |  |  |  | 0 |  |  |  | 36.000 | 36.000 |
| 2.2 | - cold boxes |  |  |  | 0 |  |  |  | 14.000 | 14.000 |
|  | - Spare parts |  |  |  | 0 |  |  |  | 4.500 | 4.500 |
| 3. | Other item immunization specific | 92.200 | 0 | 0 | 6.000 | 18.500 | 2.300 |  | 117.000 | 0 |
| 3.1 | - Technical assistance | 0 |  |  | 3.000 | 3.600 | 0 |  | 6.600 | 0 |
| 3.2 | - Training | 0 |  |  | 3.000 | 5.400 | 0 |  | 8.400 | 0 |
| 3.3 | - Salary | 86.000 |  |  | 0 | 0 | 0 |  | 86.000 | 0 |
| 3.4 | - Other operational cost | 4.200 |  |  | 0 | 9.500 | 2.300 |  | 16.000 | 0 |
| Total commitment |  | 92.200 | 0 | 0 | 504.200 | 18.500 | 2.300 |  | 613.`100 | 58.300 |

Table 3

| Expenditure in 2000 from different sources |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 1 UNICEF | Donor 2 WHO | Donor 3 MERLIN | Donor 4 AKF | Total Expenditure in 2000 |
| 1. | Vaccines, AD syringes… | 0 | 0 | 0 | 379,338 | 0 | 0 |  | 379.338 |
| 112 | - BCG vaccine |  |  |  | 16.400 |  |  |  | 16.400 |
|  | - DPT vaccine |  |  |  | 20.000 |  |  |  | 20.000 |
|  | - Polio vaccine |  |  |  | 198,338 |  |  |  | 198.338 |
|  | - Measles vaccine |  |  |  | 13.000 |  |  |  | 13.000 |
|  | - AD syringes |  |  |  | 131,600 |  |  |  | 131.600 |
| 2. | Equipment (cold chain, spare parts, sterilization…) | 0 | 0 | 0 | 39.150 | 0 | 500 |  | 39.650 |
| 2.1 | - Refrigerators |  |  |  | 25,000 |  | 0 |  | 25.000 |
|  | - Cold boxes |  |  |  | 0 |  | 500 |  | 500 |
| 2.2 | - Safe boxes |  |  |  | 14,150 |  | 0 |  | 14.150 |
|  | - Spare parts |  |  |  | 0 |  | 0 |  |  |
| 3. | Other item immunization specific | 117.335 | 0 | 0 | 40.000 | 50.000 |  | 5.875 | 213.210 |
| 3.1 | - Technical assistance | 0 |  |  | 30,000 | 25.000 |  | 0 | 55.000 |
| 3.2 | - Training | 0 |  |  | 10,000 | 15.700 |  | 4.495 | 30.195 |
| 3.3 | - Salary | 112.485 |  |  | 0 | 0 |  | 0 | 112.485 |
|  | - Other operational costs | 4.850 |  |  | 0 | 9.300 |  | 1.380 | 15.530 |
| Total expenditure in 2000 |  | 117.335 | 0 | 0 | 458,538 | 50.000 | 500 | 5.875 | 632.198 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |

Table 4

| Budget for 2000 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 UNICEF | Donor 2 WHO | Donor 3 Merlin | Donor 4 AKF |  |  |
| 1. | Vaccines, AD syringes… | 0 | 0 | 0 | 356.638 | 0 | 0 | 0 | 416.083 | 53.445 |
| 1.1 | - BCG vaccine |  |  |  | 16.400 |  |  |  | 36.280 | 19.880 |
| 1.2 | - DPT vaccine |  |  |  | 52.800 |  |  |  | 58.800 | 0 |
| 1.3 | - Polio vaccine |  |  |  | 198.338 |  |  |  | 198.338 | 0 |
| 1.4 | - Measles vaccine |  |  |  | 16.200 |  |  |  | 41.765 | 25.565 |
| 1.5 | - AD syringes |  |  |  | 72.900 |  |  |  | 80.900 | 8.000 |
| 2. | Equipment (cold chain, spare parts, sterilization…) | 0 | 0 | 0 | 39.150 | 0 | 0 | 0 | 57.100 | 20.100 |
| 2.1 | - Refrigerators |  |  |  | 25.000 |  |  |  | 25.000 | 0 |
|  | - Cold boxes |  |  |  | 0 |  |  |  | 14.000 | 14.000 |
| 2.2 | - Safety boxes |  |  |  | 14.150 |  |  |  | 12.000 | 0 |
|  | - Spare parts |  |  |  | 0 |  |  |  | 6.100 | 6.100 |
| 3. | Other item immunization specific | 116.535 | 0 | 0 | 82.000 | 50.000 | 2.000 | 6.000 | 128.565 | 0 |
| 3.1 | - Technical assistance | 0 |  |  | 72.000 | 25.000 | 0 | 0 | 0 | 0 |
| 3.2 | - Training | 0 |  |  | 10.000 | 15.700 | 1.750 | 4.500 | 12.000 | 0 |
| 3.3 | - Salary | 112.485 |  |  | 0 | 0 | 0 | 0 | 112.485 | 0 |
| 3.4 | - Others | 4.050 |  |  | 0 | 9.300 | 250 | 1.500 | 4.050 | 0 |
| Total commitment |  | 116.535 | 0 | 0 | 477.788 | 50.000 | 2.000 | 6.000 | 601.748 | 73.545 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation provideded

| Background information on Health System Development status Multi-Year Immunization Plan |  |
| --- | --- |
| - Overall government health policies and strategies | Document # 1_ |
| - Structure of the government health services and how it relates to immunization services (with an organizational chart) | Document # 2_ |
| - The Presidential Programme of the Republic of Tajikistan on Health Care Reform (a draft) | Document # 3_ |
| - Government policies on private sector participation, as it relates to immunization Services | Document # 4_ |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| e) ICC’s work plan in 2001 year | Document # 5_ |
| f) Terms of reference of the ICCI | Document # 6_ |
| g) Minutes of the three most recent ICC meetings concerned improving and expanding the national immunization programe | Document # 7_ |
| Immunization Services Assessment |  |
| h) An assessment report : «A review of Immunization Activities in Тajikistan» (A. Battersby, UNICEF, August 2000) | Document # 8_ |
| i) Summary of the recommendations of the assessment report with remarks on the status of their implementation | Document # _9_ |
| Multi-Year Immunization Plan |  |
| j) 2001-2010 National Programme for Immunoprophylaxis | Document # _10_ |
| k) Safe injections Plan | Document # _11_ |
| l) 2000-2007 Programme for Hepatitis B Control and Prophylaxis | Document # _12_ |
| Unmet needs requiring additional resources |  |
| m) Tables of expenditure for 1999 and 2000 (Annex 1) | Document # 13_ |
| n) Agreements made with other agencies as sustainability strategy (i.e.: VII) | Document # 14, 15 |
| o) Projects related to immunization services supported by donors | Document # 16_ |