The Government of

YEMEN

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

# Executive Summary

# Yemen shares most of the social –economic problems associated with the least developed countries. The GNP per capita is 350 US$. The economy as a whole and the national currency have been relatively stable. GDP increased from US$6.8 billion in 1999 to US$ 9.2 billion in 2000 however, the living standard for many Yemeni families has decreased. The percentage of the population residing in absolute poverty has reached an estimated 30%. Although Yemen’s fiscal situation has improved substantially in recent years due to governments emphasis on restoring fiscal stability in the second half of the 1990s, overall public expenditure of the health sector in low accounting for only 1.4% of GDP and about 5% of total government spending. The health care system in Yemen consists of a large public sector along with a sizeable private sector. Public health care is organised at these levels : primary health care supported by secondary and tertiary referral care. Although quality of service, coverage and accessibility still represent major challenges, the overall impact on basic health services is demonstrated in a drop in the IMR from 80 in 1996 to 75 in 1998 ,and in the USMR from 112 in 1996 to 104 in 1998.

Basic Data and indicators          Year		Value

- Midyear population estimates 	2000		18.3  million

- Annual growth rate 		1998		 3.5

- Total fertility rate 	( 15-49) 	1997		 7.5

- Infant mortality rate ( IMR ) 	1997		 75.3

- Under 5 mortality rate (U5MR)	1997		 105

- Number of surviving infants	2000		 593,000

- Vaccination Coverage BCG	1999		 78%

OPV3			72%

OPT3			72%

Measles 			74%

Hep. B3   			 9%

EPI fits under PHC and medical services . EPI is considered a successful public health programme in Yemen. Progress has been achieved specially during the last five years .

Improvement has been noted in overall EPI management, functioning of the cold chain, targeting measles and MNT in addition to polio eradication through campaigns. The government is committed to contributing to the cost of vaccines. (currently the Government is purchasing, through UNICEF, approximately 24% of all vaccines, safety boxes and auto-destruct syringes from their own resources ). The Ministry of Public Health (MoPH) has reached an agreement with the Ministry of Finance to increase the financial contribution to vaccine by 10% yearly.

DPT3 coverage has improved over the last few years from 51% 1997 to 74% in the year 2000. MoPH plans to introduce the Hib vaccine by year 2002 and improve vaccination coverage of the under used Hepatitis –B vaccine .and ensure its full integration by the year 2002.

Estimates of the Hepatitis- B related disease burden were calculated using seroprevalance

data provided by the Yemeni (central Laboratory. It is estimated that over 2,000 Yemeni adults are dying each year from hebatoma and cirrhosis resulting from chronic hepatitis-B infection .It is estimated as many as 15,843 of the children born this year will die from those outcomes in the future if not protected from infection. (Yemen Trip Report, WHO/EMRO/Nov. 2000)

The estimated number of surviving infants is about 600,000 per year .

The requested number of doses of DTP – Hep B – Hib combination vaccine is approximately two million doses per year .

The first preference of MoPH is the combination DTP-Hep B-Hib( 2 dose vials ). The

second preference is DTP-HepB ( 10 dose vials ) and monovalent liquid Hib( 10 dose vials).

The MoPH continues to collaborate closely with WHO, UNICEF and the Japanese Government ( JICA) to improve and sustain EPI – related achievements.

Yemen  now has an active and functioning inter – agency co-ordination committee

( ICC) .Key partners are  represented .Meeting of the heads of the country office of WHO and UNICEF and representative of the Government of Japan and the World Bank have become more frequent . The meetings are chaired by the Minister of Public Health andPopulation . The Deputy Minister for Health Care and Medical Services is a member of the committee and the EPI national manager has been assigned as a secretary to the committee

The MoPH produced a strategy document on health sector reform in 1998 and certain components of  the reform are already being implemented . The reform is focussed on improving management , decentralizing  management functions to districts, implementing cost sharing and cost recovery with users ,and strengthening the role of the MoPH in policy  making and supervision while reducing its role in service delivery .

Yemen is resubmitting this application to GAVI after completing what was found to be

insufficient in the previously submitted proposal ( last September ) .An overall immunization assessment was conducted . A multi –year strategic plan for immunization was revisited and an introduction plan for the requested under used and new vaccines

( Hep B and Hib  ) was developed . A plan of action ( 2001 – 2005 ) to improve injection safety and safe disposal of injection equipment in Yemen EPI was also developed .

# Signatures of the Government

The Government of Yemen

Commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature: Prof. Dr. Abdul Nasser Ali Al-Muniabari                                 Signed

Title:	The Minister of Public Health and Population

Date:	April 18, 2001

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation, which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual. (Guidelines on Country Proposal # 2.) :

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| WHO | Dr.Hashim Al-Zain WHO Representative | Signed |
| UNICEF | Mr. Leonard De Vos UNICEF Representative | Signed |
| JAPAN | Mr. Yoshiaki Hata Councellor , Embassy of Japan | Signed |
| WORLD BANK | Mr. Hashem Awnallah Operations officer | Signed |

In case the GAVI Secretariat have queries on this submission, please contact:

Name : MOHAMMED A. KOLAISE 	Title/Address : EPI NATIONAL MANAGER

Tel.No. : 967.1.241353	            			………………………………..

Fax No. : 967.1.508353 		           		            ………………………………..

E-mail : EPIYEM@Y.NET.YE                  		……………………………….

Alternative address :

Name : DR. ABDULKARIM ALI SHAIBAN 	Title/Address : DEPUTY MINISTER

Tel.No. : 967.1.252246   		                        ………………………………..

Fax No. : 967.1.252247 		                                     ………………………………..

E-mail : PHCMOPH@Y.NET.YE                                ……………………………….

- Immunization-related fact sheet

| Table 1: Basic facts (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 18 324 904 (1) | GNP per capita | 350 $US |
| Surviving Infants* | 592 463 | Infant mortality rate | 75/ 1000 (2) |
| Percentage of GDP allocated to Health | 4% | Percentage of Government expenditure for Health Care | 4% |

* Surviving infants = Infants surviving the first 12 months of life

(1): This is an estimated 2000 population size from the last 1994 population census, Data are provided by

The Central Statistic Organisation.

(2) Source: Central Statistic Organisation. (1999 data)

Table 2: Immunization coverage and disease burden trends as per annual reporting to WHO/UNICEF

| ### Trends of immunization coverage ### By 12 months of age |  |  |  |  |  |  |  | Vaccine preventable disease burden (3) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported (1) |  | Survey (2) |  |  |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  |  | 1998 | 1999 | 1998 | Age group | 1999 | Age group |  | 1998 | 1999 | 1998 | 1999 |
| BCG |  | 77 | 78 |  |  |  |  | Tuberculosis | 35340 | 5366 |  |  |
| DTP | DTP1 | 80.7 | 83.5 |  |  |  |  | Diphtheria | 751 | 1215 |  |  |
|  | DTP3 | 67.9 | 72.3 |  |  |  |  | Pertussis | 13477 | 5319 |  |  |
|  | [( DTP1 - DTP3) / DTP1 ] x 100 | 15.9 | 13.4 |  |  |  |  |  |  |  |  |  |
| OPV3 |  | 67.9 | 72.3 |  |  |  |  | Polio | 16* | 25* |  |  |
| Measles |  | 66.0 | 74 |  |  |  |  | Measles | 20511 | 17762 |  |  |
| TT2+ Pregnant Women |  | 26 | 26 |  |  |  |  | NN Tetanus | 3275 | 226 |  |  |
| Hib |  |  |  |  |  |  |  | Hib |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  | Yellow fever |  |  |  |  |
| HepB |  | 9 | 20 |  |  |  |  | HepB seroprevalence (if available) | 12.7% |  |  |  |

The sources of information:

(1) EPI routine immunization surveillance data, MoPH annual report 1999.

The reporting system includes all public health facilities and part of the private sector

( 2)MoPH did not undertake any cluster ( coverage) survey during the last 3 years

Hepatitis B: A survey conducted in 1988 revealed that HbsAg prevalence in the general population was 12.7%

- Measles, NN tetanus, tuberculosis, diphteria, pertussis: health diseases information system

- Hep B: estimation from WHO

- Polio: AFP surveillance system

* All polio reported cases are "clinical" according to WHO classification; no wild virus has been  isolated since 1998.

Summary of health system development status:

Organization of the ministry of health:

The Ministry of Public Health is responsible for all health services in Yemen and is organized into 3 sectors: medical services and primary health care, health development and planning and ( MoPH) pharmaceutical and medical supplies. A Deputy Minister chairs each sector. EPI is part of medical services and health care sector.

Health services

Yemen adopted the primary health care approach to health services in 1978. To implement primary health care, Yemen has utilized a traditional facility based, three-tier health delivery system of health units, health centers and hospitals.

In the public sector, there are 711 temporary health units in small villages, 1149 fixed health units in medium size villages, 469 health centers in large villages, 79 district hospitals with 2968 beds, 25 governorate hospital with 3517 beds and 14 specialized hospitals with 3814 beds. In 1999, there were 2.16 physicians and 5.9 hospital beds per 10,000 population.

Health Sector Reform

In 1998, the Yemeni health system was assessed and a strategy was designed (Health Sector Reform) to address current constraints. Some indicators of the crisis facing the public health sector included:

- Per capita health care budget of 3.60 $ in 1996 and public health expenditures representing only 4.2% of total public expenditures;

- Lack of essential drugs and services in government health facilities leading to a bypass rate of between 42 to 73%;

- Low geographic access with only 30% of the rural population having access to health care and only 50% as general access (MOH,1995);

- The personal contribution of households to health care costs amounting to 75% ;

- A largely unregulated and low quality private sector, with many private facilities unlicensed;

Health Sector Reform has been planned to occur within the overall context of government reform that is based on decentralization, democratization, civil service reform (or modernization), and financial restructuring. The long-term objectives of the health sector reform program are as follow:

- Adequate/universal access to health care services;

- Equity in both the delivery and eventually the financing of health care;

- Improved allocation and technical efficiency of the service delivery system;

- Improved quality of health services and

- Long-term financial sustainability.

The key elements of the reform are :

- Decentralization : the district level administrative structures include,  the district health council, district hospital board and district health management team.

- redefinition of the role of the public health sector: redefining the limits of the public health service system, developing policies for encouraging alternative health care providers and rationalizing the budget with effective and efficient reform strategies

- district health system: management by team work, community authority and participation and management decentralized to district level

- cost sharing in order to secure sufficient through revenues from fees and charges for services in order to improve maintenance of facilities.

- essential drugs policy

- intersectoral cooperation at the level of the district and the community

- encouragement of participation by the private sector and NGOs,

- encouragement of innovation and

- sector wide approach to donor funding and programming

Supporting documents:  (only copies of relevant pages are attached)

| - Overall government health policies and strategies : | Document number……( 1 )…….. |
| --- | --- |
| - Structure of the government health services and how it relates to immunization services (with an organisational chart) | Document number……( 2 )…….. |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) and their impact on immunization services | Document number……( 3 )…….. |
| - Government policies and practices on private sector participation, as it relates to immunization services | Document number……( 4 )…….. |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services in the country, are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC. (Guidelines on Country Proposal # 4.1.)

- Name of the ICC :       Higher  Coordination Committee

In order to improve the coordination in the health sector, the MoPH organizes regular meetings with donors. This inter-agency coordination committee has a sector wide concern, including EPI activities. Regarding EPI questions a technical committee including WHO, UNICEF, JICA and  MoPH meet regularly in order to coordinate EPI activities. These meetings are more frequent during preparation of NIDs. The MoPH has set up a specific department of liaison, and produced "guidelines for development agencies".

A donor information system is being developed to facilitate coordination .

- Date of constitution of the current ICC:    20/10/1996

- Organisational structure (e.g., sub-committee, stand alone)

- ICC committee supported by EPI  technical  group ( EPI national manager, WHO technical officer and UNICEF Health officer)

- Frequency of meetings  : 4 times/year

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | The Minister of Public Health and Population | Prof. Dr. Abdul Nasser Ali Al-Munibari |
| Secretary | The National EPI manager | Mr.Mohammed A. Kolaise |
| Members | - Deputy Minister for PHC and medical services - Representative of WHO - Representative of UNICEF - Representative of Government of Japan - Representative of World Bank | Dr. Abdulkarim Ali Shaiban Dr.Hashim Al-Zain Mr. Leonard De Vos Mr. Yoshiaki Hata Mr. Hashem Awnallh |

- Functional relationships of the ICC with other institutions in health sector :

- university: collaboration in applied research

-

- Major functions and responsibilities of the ICC:

- To coordinate support  from government ,partner agencies and others to strengthen EPI

- To assess the EPI program activities

- To develop and monitor an EPI communication and social mobilization plan

- To create a fund raising mechanism both externally and locally (government and private sectors)

- To ensure co-ordination among key partners and government in planning and implementation of EPI

- To provide MOH with EPI related technical advices.

- Three major strategies to enhance ICC’s role and functions in the next 12 months :

- To mobilise other partners for child health (expand partnership)

- To reinforce  regional and governorate level committee for immunization

- To involve ICC in routine immunization

- Plan and launch major interventions for measles and MNT elimination .

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Drop out rate

- Vaccine wastage rate

- Safety injections practices( availability of supplies and equipment ,vaccinators’ skills and disposal aspects )

Attached are the supporting documents :

| - ICC’s workplan of next 12 months | Document number…( 5 )… |
| --- | --- |
| - Terms of reference of the ICC | Document number…( 6 )… |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number…( 7 )… |

# 5. Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal. (Guidelines on Country Proposal # 4.2.)

- Assessments, reviews and studies of immunisation services for current reference :

| Title of assessment | Main participating agencies | Date |
| --- | --- | --- |
| 1-Assessment on viral hepatitis situation | WHO | 1998 |
| 2-Measles surveillance review | WHO | 1998 |
| 3-Assessment of safety injections and disposal | WHO | 1999 |
| 4- Assessment o the quality of vaccines and safety of injections | WHO | 19-30 Jan 2000 |
| 5- assessment of Hib situation | WHO | 9-15 Nov 2000 |
| 6- Yemen EPI review | WHO | 5-22 Jan 2001 |
| 7- EPI cold chain review | WHO | 7-22 Jan 2001 |

- The three major strengths identified in the assessments :

- Improvement in coverage rates for all vaccines during the last three years

- Improvement in cold chain capacity

- Investment for safety injections:

- The three major problems identified in the assessments :

- Lack of reliability of the diseases surveillance system

- Poor accessibility to health facilities in rural areas

- In adequate training of EPI workers

- The three major recommendations in the assessments :

- Improvement of disease surveillance

- Reinforcement of training activities and supervisory visits

- Improvement of managerial skills at the governorate and district levels

- Attached is a  complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number…( 8 ).. |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number…( 9 ).. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Title of the assessment | Month/Year |
| --- | --- |
| 1-Assessment of the health surveillance system | 01/2002 |
| 2-Assessment of immunisation missed opportunities | 04/2002 |
| 3-Assessment of mother baby transmission of Hep B virus | 09/2002 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan. (Guidelines on Country Proposal # 4.3)

| - Attached is a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 10 ……. |
| --- | --- |

| #### Table 3 : Vaccination schedule with traditional and new vaccines (add/correct/fill in as appropriate) #### If our first choice Combine DTP-Hib-HepB is available (named in the table: DHH |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AGE | Visit | Traditional antigens |  |  |  | New vaccines |  |  |
| Birth | 1 | BCG | OPV0 |  |  |  |  |  |
| 6 weeks | 2 |  | OPV1 | DTP1 |  | DHH |  |  |
| 10 weeks | 3 |  | OPV2 | DTP2 |  | DHH |  |  |
| 14 weeks | 4 |  | OPV3 | DTP3 |  | DHH |  |  |
| 9 months | 5 |  |  |  | Measles |  |  |  |

- Table 4.1 : Baseline and annual targets   ( In case our first choice DTP-HepB-HiB is available)

|  | Baseline | Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| # of births | 618660 | 640500 | 662620 | 686245 | 711480 | 737835 | 764785 |
| # of infants’ deaths | 46400 | 48038 | 49697 | 51468 | 53361 | 55338 | 57359 |
| Surviving infants | 572261 | 592436 | 612924 | 634777 | 658119 | 682497 | 707426 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 13.5 | 13 | 12 | 11 | 11 | 10.5 | 10 |
| Children vaccinated with DTP3 * | 413 309* | 438422 | 465822 | -- | -- | -- | -- |
| Children vaccinated with DTP-HepB-Hib | -- | --- | --- | 495126 | 526495 | 580123 | 636684 |
| Children vaccinated with HepB3 | 49668 | 118493 | 122585 | --- | --- | ---- | ---- |
| Children vaccinated with Measles ** | --- | NA | NA | NA | NA | NA | NA |
| Children vaccinated with yellow fever ** | --- | NA | NA | NA | NA | NA | NA |
| * While vaccinations with combination vaccines phase in, those with DTP3 only are expected to phase out ** Only complete if applying for yellow fever vaccine NA = not applicable NB : Years 2002 and 2003 estimated number of children based on achieving 80 % coverage Year 2004 estimated number of children based on achieving 85 % coverage Year 2005 estimated number of children based on achieving 90 % coverage |  |  |  |  |  |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

One of the  major objectives for the next five year is to raise immunization coverage for all EPI targeted diseases to above  90% by the year 2005 . The strategies and action steps are the following:

  - Ensure adequate and sustainable funding for the EPI program

Issues: Currently the Government of Yemen provides  24% of funding to support the purchase of vaccines, auto-destruct syringes and safty boxes  for the EPI program. The introduction of new vaccines has the potential to dramatically increase the EPI vaccine budget. This  application is prepared to GAVI to support the introduction of hep B and Hib vaccines and to strengthening immunization services.    Continued support of active partners through the ICC is felt to be a critical element in advocating GOY support for the EPI program.

Action steps:

    - Coordinate with political, planning, and finance units of the government to ensure adequate allocation  and timely release of funds.

    - Review 5 year plan and seek support from members of the ICC

    - Integrate strategies (decentralization, district health system reform) of Health Sector Reform

into EPI .

  - Increase access to services to 90% of population by 2005 

Issues: Currently, it is estimated that 70% of the population have access to fixed clinic immunization services. Increased access to services will be a key strategy to raise coverage

Action Steps:

    - Assess the status of the existing program with regards to access to services and participation of private sector and NGOs.

    - Development and implementation of a plan to provide immunization services in underserved populations.

    - Develop a training plan for health care staff in new service delivery centers.

    - Improve outreach vaccination activities to reach the unreached and the  hard to reach

  - Reduce missed opportunities to provide immunization services 

Issues: The EPI program is committed to optimizing the delivery of immunization services. Reducing missed opportunities is a key strategy that can increase coverage. 

Action Steps:

    - Develop technical committee at national level to provide “Standards of Immunization Practices” to optimize the delivery of immunization services.

    - Training at the district/service delivery level to reduce missed opportunities to provide immunization services.

  - Maintain social mobilization strategies 

Issues: The MoPH has developed highly effective social mobilization strategies for Polio eradication. Highly effective strategies include training  of teachers , religious leaders ,women leaders  of the local communities to form a network of inter- personal communication. Local production of IEC materials and mass media campaign were effectively organized .  High political support was always there .
Action Steps:

    - Using all available media (megaphones, mosque, schools) promote routine EPI immunization at the district level.

    - Use polio eradication activities to promote EPI.

    - Use interpersonal communications .

  - Training of governorate and district program managers on key elements in the five year plan.

Issues: Many program managers at the governorate level have had limited training over the past decade. With the implementation of new strategies to reduce tetanus and measles incidence, promote safety of injections and introduce new vaccines, there is a critical need to provide management training at the national and governorate level. 

Action steps:

    - Development of a training plan and materials for the introduction of a new 5 year plan.

    - Training at the governorate level on the 5 year plan.

  - Conduct nationwide immunization coverage survey  

Issues: There are several limitations to the interpretation of current coverage data including the lack of independent survey data to verify doses administered coverage estimates and uncertainty about reliability of denominator data. In a demographic health survey conducted in 1997, DTP3 coverage was reported to be 43%, however, there are concerns in MoPH  about the reliability of this data.  The EPI program plans to conduct a national EPI cluster survey to compare administrative coverage with survey data. Results of these surveys will allow program managers to better interpret administrative coverage data and target efforts to increase coverage.

Action Steps

Cluster survey to assess immunization coverage

- Summary of the major action points and timeframe for reduction of vaccines wastage rate :

- Training of vaccinators

- Conducting outreach for drop –outs

- Reaching more target children at the same vaccination session .

Table 4.2 : Estimate of annual DTP wastage rates

|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP wastage rate | 25 | 25 | 25 | 5 | 5 | 5 | 5 |

- Summary of the safe immunization plan (Guidelines on Country Proposal # 3.):

  - Continue to supply critical supplies and educational materials for safe injections

Issues: Currently, AD syringes and safety boxes are purchased through UNICEF. Training on the use of AD syringes, prevention of needlestick injuries, and proper disposal of needles has been conducted at the national, regional, and local level. Information on safe injections has been included in the EPI manual.  Recently, WHO produced guidelines on delivering safe injections. These guidelines include instructions on use of multi-dose vials, use of a dedicated injection preparation area, and safe disposal of needles. These guidelines will be included in the EPI manual and the concepts that will be introduced into the EPI program.

Action Steps

    - Prepare an inventory of critical needs (AD syringes and safety boxes) and ensure continuous supply.

    - Include WHO guidelines on safe injections in immunization manual and develop educational materials for service delivery level on safe injections.

    - Training at district and service delivery level on safe injection practices.

  - Develop a plan for waste management at the governorate level with local partners (DG, MCH, primary care, council for environmental protection). 
Issues: Developing an effective waste management system is a challenging and expensive process for most countries. In Yemen, there are numerous barriers to effective waste management at the health facility level. While most facilities have developed an informal system of burning medical waste on site, there are insufficient funds to support the purchase of incinerators. Generally, health services other than EPI do not provide sharp containers and the disposal of medical waste is not optimal. Most containers used to collect waste are not placed in an area with restricted access and they do not contain barriers to prevent access from non-medical personnel. At the district and governorate level, there is no functional system to collect and dispose of medical waste in an environmentally safe way. Developing a plan for medical waste disposal is high priority for the Ministry of  Public Health.

Action Steps

    - Develop guidelines for low cost and appropriate proper waste management.  These guidelines should include simple instructions such as the storage of waste in a fenced-in area and the use of containers that can be secured.

| Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number (12) |
| --- | --- |

- Constraints and planning for Polio Eradication Initiative (Guidelines on Country Proposal # 2.):

In 1996, the Government of Yemen committed itself to eradicate polio by the end of 2000. The eradication activities begun  with NIDs in 1996, followed by two rounds of NIDs each year, targeting all children below 5 years. Yemen has so far implemented 5 campaigns. During the first round of the NIDs, 3.1 million children received a dose of OPV, while 3.5 millions children were immunized during the second round. In 1997, even better successes were achieved. During the first round 3.6 million children were immunized, and 4.1 million children during the second round. The following campaigns undertook in 1998, 1999, 2000 were also very successful. During the second round of polio NIDs of the year 1999 and 2000, Vit.A capsules were distributed .   In March 2000, WHO excluded Yemen from the list of endemic countries. The main reasons for the success include, a very high political commitment, cooperation of different government sectors, effective social mobilization, strong community participation, support from international partners and detailed and accurate planning. In addition to achieving a high coverage of OPV, the success of the NIDs had major impact in the effort to revitalize EPI: increasing the allocated budget, raising awareness of the community regarding vaccination, boosting the morale of health workers and increase in donors support.

In 1998, a concerted effort began to implement active surveillance for Acute Flaccid Paralysis (AFP). In 1999, there were 109 AFP cases reported in Yemen; 25 cases were classified clinically as polio. In 2000, 148 AFP cases were reported and investigated. The final classification (including culture results) is pending. Yemen has had great success in conducting NIDs and it is expected that certification of polio eradication can now be achieved by 2005.

The main constraints to achieve this goal are lack of transportation and difficult access to some mountainous areas which is related to the lack of appropriate transportation,

The action Steps for the next five years are the followings:

Conduct final NID in 2001and 2002

Continue sub-NIDs for high-risk district through 2003.

Conduct mop up campaigns in targeted high risk areas

Ensure that indicators for AFP surveillance are met for all governorates by 2003

# New and under-used vaccines

Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines (Guidelines on Country Proposal # 4.4.).

Status: 
Hepatitis B: Available data indicates that Hepatitis B is highly endemic in Yemen.  Introduction of Hepatitis-B vaccine into EPI has been a long-standing goal of the program. In 1998, the MoPH experimented with a cost recovery program to introduce hepatitis B vaccine into EPI and purchased a limited amount of vaccine to vaccinate infants < 12 months of age. The MoPH also offered vaccine to older children on a cost-recovery basis. The cost recovery program was moderately successful in the first year and the MoPH collected considerable revenue, however, demand for vaccine diminished.  Funding to support vaccination of the entire birth cohort has not been identified and the MoPH plans to apply to GAVI to support this.

H. Influenza: In addition to Hepatitis B vaccine, the MoPH intends to introduce H. influenza B vaccine into the EPI program in Yemen. In November 2000, a WHO team conducted an estimation of the Hib burden of disease in Yemen. Using limited data, the team estimated 1100 to 4,500 deaths occur each year due to invasive Hib disease. Using a variety of scenarios and models on disease incidence, the team estimated that the cost per death prevented ranges from $1,374 to $7,497.

Strategies, Issues, and Action Steps

6.1 Fully integrate Hepatitis B vaccine into EPI by 2002

Issues: The introduction of Hep B vaccine into the infant vaccination program has been difficult since the quantity of vaccine purchased was not sufficient to vaccinate the entire birth cohort. The MoPH selected to offer vaccine in selected clinics in each governorate and there has not been a continuous supply of vaccine in these clinics.  Vaccination coverage in 1999 was estimated to be 9%.  The MoPH experienced initial difficulty in vaccine acceptance when it purchased plasma-derived vaccine. Subsequently, it purchased recombinant-DNA derived vaccine and this is no longer an issue.  The MoPH plans to apply to the Global Alliance Vaccine Initiate for vaccine support in 2001. 
  
Action Steps

1-Prepare plan for vaccine introduction

2-Application to GAVI

3-Develop advocacy and social mobilization plan

4-Provide training on Hep B vaccine

5-Upgrade cold chain capacity if necessary

6.2 Develop plan for program evaluation

Issues : Monitoring of routine activities is not regularly done . It is mainly activated  when it comes to national or subnational vaccination campaign .Monitoring is usually done through the monthly reported vaccination coverage . The main reason behind lack of efficient monitoring and supervision is lack of operational cost budget as well as lack of technical expertise. No functioning system of evaluation

Action Steps
	1- prepare plan for systematic evaluation

2- seek the technical support of WHO,UNICEF and other key organizations

3-Fully integrate Hib vaccine into EPI in 2002

Issues: Similar to the introduction of Hep B vaccine, combination vaccines containing Hib are unlikely to be available in the next few years. The introduction of 2 new monovalent vaccines will place considerable stress on staff providing immunization services. If monovalent vaccines are used, there will be a staged introduction of Hep B in 2002 and Hib in 2003. If combination vaccine becomes available, the MoPH will consider an earlier introduction of Hib. 

Action Steps:

1-Prepare plan for vaccine introduction

2-Application to GAVI

3-Develop advocacy and social mobilization plan on Hib

4-Provide training on Hib vaccine

5- Develop plan for program evaluation

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc…in relation to the current experience with new and under-used vaccines :

In November 1998, the MoPH experimented with a cost recovery program to introduce hepatitis B vaccine integrated with the routine immunizations. A limited amount of vaccines was purchased and used in some areas to immunize free of charge infants  < 12 months of age. The vaccine cost was a constraint to expending the immunization to the whole country. The MoPH also offered vaccine to older children on a cost-recovery basis. The cost recovery program was moderately successful in the first year and the MOH collected considerable revenue, however, demand for vaccine diminished. Funding to support vaccination of the entire birth cohort has not been identified and the MOH plans to apply to GAVI to support this. The HepB vaccine introduction was very well conducted: social mobilization, training of EPI staff, frequent supervisory visits. Population and health workers accepted well this new vaccine. However, since the begining of 2000, some rumors regarding hypothetical adverse effects of the vaccine were circulated by the private sector. The impact of these rumors was relatively low on the vaccine calendar observance. The cold chain capacity was closely monitored during Hepb vaccine introduction  and no problem was reported from the selected sites where the vaccine were introduced.

- Required number of doses and presentations of requested, first preference, new and under-used vaccines: DTP-HepB-HiB

- (For each one of the requested, first preference new and under-used vaccine, please use provided formulas; see guidelines # 5.2)

Table 5.1: Estimated number of doses  of DTP-HepB-HiB.. vaccine (specify for one presentation only)

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) |  | 495126 | 526495 | 580123 | 636684 |
| B | Number of doses per vaccinated child |  | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate in percentage |  | 5 | 5 | 5 | 5 |
| D | Wastage factor [ = 100 / (100-C) ] |  | 1.05 | 1.05 | 1.05 | 1.05 |
| E | Buffer stock factor for vaccines |  | 1.25 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] |  | 1949559 | 1658459 | 1827388 | 2005555 |
| G | Percentage of vaccines requested from the Fund (%) |  | 100 | 100 | 90 | 80 |
| H | Number of doses requested from the Fund [ = F x G / 100 ] |  | 1949559 | 1658459 | 1644650 | 1604444 |
| I | Number of doses per vial |  | 2 | 2 | 2 | 2 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] |  | 1955129 | 1663198 | 1649348 | 1609028 |
| L | Reconstitution syringes [= H / I ] |  |  |  |  |  |
| M | Total number of syringes requested from the Fund [ = J + L ] |  | 1955129 | 1663198 | 1649348 | 1609028 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] |  | 19551 | 16632 | 16493 | 16090 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for hep B and Hib differ from DTP3, explanation of the difference should be provided.

Second preference: A)  DTP-HepB

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) |  | 495126 | 526495 | 580123 | 636684 |
| B | Number of doses per vaccinated child |  | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate in percentage |  | 5 | 5 | 5 | 5 |
| D | Wastage factor [ = 100 / (100-C) ] |  | 1.25 | 1.22 | 1.18 | 1.15 |
| E | Buffer stock factor for vaccines |  | 1.25 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] |  | 2,320,903 | 1,926,982 | 2,053,635 | 2,196,560 |
| G | Percentage of vaccines requested from the Fund (%) |  | 100 | 100 | 90 | 80 |
| H | Number of doses requested from the Fund [ = F x G / 100 ] |  | 2320903 | 1926982 | 1848272 | 1757248 |
| I | Number of doses per vial |  | 10 | 10 | 10 | 10 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] |  | 1955129 | 1663198 | 1649348 | 1609028 |
| L | Reconstitution syringes [= H / I ] |  |  |  |  |  |
| M | Total number of syringes requested from the Fund [ = J + L ] |  | 1,955,129 | 1,663,198 | 1,649,348 | 1,609,028 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] |  | 19551 | 16632 | 16493 | 16090 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for hep B and Hib differ from DTP3, explanation of the difference should be provided.

N.B. Target of the first preference  ( DTP – Hep B – Hib ) is the same of the second preference  ( DTP – Hep B vaccine and Hib monovalent vaccine )

B) Hib monovalent vaccine

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) |  | 495126 | 526495 | 580123 | 636684 |
| B | Number of doses per vaccinated child |  | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate in percentage |  | 5 | 5 | 5 | 5 |
| D | Wastage factor [ = 100 / (100-C) ] |  | 1.25 | 1.22 | 1.18 | 1.15 |
| E | Buffer stock factor for vaccines |  | 1.25 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] |  | 2,320,903 | 1,926,972 | 2,053,635 | 2,253,861 |
| G | Percentage of vaccines requested from the Fund (%) |  | 100 | 100 | 90 | 80 |
| H | Number of doses requested from the Fund [ = F x G / 100 ] |  | 2320903 | 1926972 | 1848272 | 1757248 |
| I | Number of doses per vial |  | 10 | 10 | 10 | 10 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] |  | 1955129 | 1663198 | 1649348 | 1609028 |
| L | Reconstitution syringes [= H / I ] |  |  |  |  |  |
| M | Total number of syringes requested from the Fund [ = J + L ] |  | 1,955,129 | 1,663,198 | 1,649,348 | 1,609,028 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] |  | 19551 | 16632 | 16493 | 16090 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for hep B and Hib differ from DTP3, explanation of the difference should be provided.

NB: any additional syringes quantities will be secured  by MoPH .

(Add any other table to the above format to calculate requested, second preference, doses of different vaccines in different presentations)

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| HepB | The epidemiology of hepatitis in Yemen | 1988 | * HbsAg: 12.7% of general population * 45.7% had some marker of hepatitis B infection |
| HiB | Assessment of Hib situation | November 2000 | Estimate 1100 to 4,500 deaths occur each year due to invasive Hib decease |

| - Attached is the plan of action for vaccinations with new or under-used vaccines - (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number: ( 11) |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, (Guidelines on Country Proposal # 4.3, 4.4, 5.) and that will be converted in a comprehensive «Resource Mobilisation Plan» by the time of the mid-term Review (Guidelines on Country Proposal # 6.1.):

- Increase the annual government contribution to vaccine purchase by 10% at least .

- Improving the accessibility to immunization services: new health centers will be provided  with vaccines

- Increasing donors contribution

- The district health reform will enable the immunization program to share  some materiel resources with other health units;

- Community participation

| - Tables of expenditure for 1999 and resource needs detailing the sources of funds are attached in Annex 1. | Document number : ( 12 ) |
| --- | --- |

- List of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative): (the relevant documents are attached)

| Title | Partners |  |
| --- | --- | --- |
| Memo of understanding on vaccine independence initiative ( under development ) |  | Document number …… |
|  |  | Document number …… |
|  |  | Document number …… |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

| - Summary of support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached : | Document number: NA |
| --- | --- |

# Summary of requests to GAVI/GFCV

With reference to all points presented above, the Government of ……Yemen ………

- being eligible for support from the Global Alliance for Vaccines and Immunization (GAVI) and the Global Funds for Children’s Vaccines (The Fund),

- considering that its DTP3 coverage for 1999 was …72%  corresponding to …400,590…… number of children vaccinated with DTP3.

hereby requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government does hereby apply to receive support from the Fund :

YES  X

NO

- IMMUNIZATION SERVICES SUB-ACCOUNT (tick only one)

To fund the immunization services in year 2002 according to the number of additional children that are targeted to be immunized with DTP3 as presented in table 4.1, namely …495,126……  ( number of children ).

- (Only for countries seeking support from the Immunization Services sub-account)

- Transfer of funds from the immunization services sub-account will be by (tick only one):

| Government |  | A Partner agency (UNICEF) | X | An independent third party |  |
| --- | --- | --- | --- | --- | --- |

- Operational mechanism in place for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds (Guidelines on Country Proposal # 5.1.):

The accounting and financing system of EPI is  under the control of the ministry of finance and the central accounting office . No financial problem have been recorded so far. Upon receiving any cash assistance from any donor, the agreed on budget breakdown is exactly followed

YES X

NO

- NEW AND UNDER-USED VACCINES SUB-ACCOUNT (tick only one)

To supply the following vaccines :  (fill in only what is being requested from the Fund in line with tables 5.1, 5.2…)

| Table 6 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Presentation* | Starting month and year | Number of doses requested for first calendar year | Vaccines will also be requested for following years as described in tables 5.1, 5.2… |
| Hep B | (1)combination | Jan 2002 | 2,469,441 |  |
|  | (2) |  |  |  |
| Hib | (1)combination | Jan 2002 | 2,469,441 |  |
|  | (2)monovalent | Jan 2002 | 2,469,441 |  |
| Yellow fever | (2) |  |  |  |

* Insert types of presentation requested:	(1) 	Monovalent or combination

(2)	Number of doses per vial

DTP / Hep B/ Hib combination 2 dose vials

DTP / Hep B/ 10 dose vials

Hib 10 dose vial ( liquid )

- (Only for countries seeking support from New and Under-used Vaccines sub-account)

- Vaccines will be procured (tick only one) :

YES X

By UNICEF                            By GOVERNMENT

- (If vaccines is procured by the Government)

Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system (Guidelines on Country Proposal # 5.2.):

All the EPI vaccines , even those financed by government are procured by UNICEF . There is a need to strengthen the Government capacity in the area of vaccine needs estimation procurement and distribution .

# Additional comments and recommendations from the ICC

There is a need to have a long term management strategy to protect the EPI program from unforeseen management shakeups and to ensure that there are enough trained / backup personnel able to continue the progress being made . There is also a need to systematize the approach being used to secure the annual fund allocation for EPI and the sustainability of the process.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Private sector | Donor 11 WHO | Donor 2 UNICEF | Donor 3 Japan | Total Expend-iture in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |
| 1.1 | - Line item 1 | 230,024 |  |  | 464,170 | 224,000 |  |
| 1.2 | - Line item n3… |  |  |  | 400,000 | 450,000 |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |
| 2.1 | - Line item 1 | 283853 |  |  |  | 1,900,000 |  |
| 2.2 | - Line item n… |  |  | 111,000 |  | 96,000 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |
| 3.1 | - Line item 1 | 395007 |  | 269,900 | 185,830 |  |  |
| 3.2 | - Line item n… | 565,912 | 10,000 | 250,339 | 195,000 |  |  |
| Total expenditure in 1999 |  | $1,474,769 | $10,000 | $631,239 | $1,245,000 | $2,670,000 | $6,031,035 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |

Table 2

| Budget for 1999 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 WHO | Donor 2 UNICEF | Donor 3 Japan | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item 1 | 240,000 |  |  |  | 464,170 | 244,000 |  |  |  |
| 1.2 | - Line item n3… |  |  |  |  | 155,830 | 450,000 |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item 1 | 300,000 |  |  |  |  | 1,900,000 |  |  |  |
| 2.2 | - Line item n… |  |  |  | 100,000 |  | 96,000 |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item 1 | 60,000 |  |  | 270,000 | 180,000 |  |  |  |  |
| 3.2 | - Line item n… |  |  |  | 230,000 |  |  |  |  |  |
| Total commitment |  | 600,000 | 0 | 0 | 600,000 | 800,000 | 2,670,000 |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organisational chart) | Document number 2 |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) as they impact immunization services | Document number 3 |
| - Government policies on private sector participation, as it relates to immunization services.( it is part of HSR document ) | Document number 4 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number 5 |
| - Terms of reference of the ICC | Document numbe 6 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number 7 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document number 8 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number 9 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 10 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - Safe injections Plan | Document number 11 Document number 12 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number 13 |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Document number 14 |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Document number NA* |

NA = not applicable

Children less than 12 months of age

Formula to calculate DTP vaccine Wastage Rate (in percentage): [ ( A – B ) / A ] x 100.                                                               Whereby : A = The number of DTP doses distributed for use according to the supply  records; B =  the number of DTP vaccinations

NB Any required additional AD syringes will be secured by MoPH.

?  The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The preferred mechanism is payment directly to a Government account (Guidelines on Country Proposal # 5.1)

Please submit hard copy documents with an identical electronic copy whenever possible