Revision 4

August 2002

The Government of

The Republic of Zambia

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The GAVI Board had approved Zambia’s application for pentavalent vaccine support from the Vaccine Fund in 2001. Following the approval, GAVI committed itself to supplying the pentavalent vaccine in third quarter of 2002 but this was later changed to the third quarter of 2003 due to vaccine production failure. However, it was learnt from GAVI in January 2003 that the global vaccine situation was getting increasingly constrained, in particular for DTP and DTP-based combination vaccines and that this information was communicated during the GAVI Partners Meeting in Dakar, Senegal 20-22 November, 2002. Worse still the manufacturer later advised of further reductions in the availability of tetravalent and pentavalent vaccines for 2003 and 2004. As a consequence, the availability of the pentavalent vaccine throughout 2003 and 2004 could not be ascertained.

The GAVI Vaccine Provision Project, implemented by UNICEF, WHO and the Vaccine Fund, at the request of the Government visited Zambia during the period 26-28 January 2003. Following the deliberations, the ICC unanimously endorsed the option of introducing DTP-Hib by January 2004 and switching to pentavalent in 2005. As a follow-up step this proposal has been developed in consultation with the technical members of the Interagency Co-ordinatiing Committee (ICC). The ICC is made up the Ministry of Health, Central Board of Health and co-operating partners/agencies supporting child health activities. The Permanent Secretary or his designate representative chairs the meetings. The signatories on the GAVI proposal document are the heads of the agencies whilst the remaining members are technical persons working in the respective organizations.

There have been problems with the coverage figures reported for DPT3 using HMIS. For example in 1999 DPT3 was reported to be 92%. This prompted the MOH/CBoH to verify the actual immunization coverage by card and/or history by the age of 12-23 months by conducting a rapid EPI 30 cluster survey in March 2001. The finding was that the baseline coverage for DPT3 in 2000 was 75.5%. The 2000 population census figures released from the Central Statistics Office did not help much in rectifying the problems of erroneous coverage.  The main contributing factor to the erroneous coverage has been the use of wrong denominators at facility level and this issue is being addressed.

This proposal seeks to request the Vaccine Fund for financial and technical assistance from the new and under used vaccines sub-account. As earlier indicated, the Government of Zambia requests for the supply of DTP+Hib. The first preference of new vaccine combination is the DPT+Hib (lyophilised) vaccine presented in 10-dose per vial formulation. The second preferred combined vaccine is the tetravalent DPT-Hib (liquid) presented in 10 doses per vial. As already indicated it is anticipated that the country will switch to pentavalent in 2005. The main reasons for opting for DPT+Hib are avoidance of an additional injection to the infants; availability of DTP; smooth transition to pentavalent because of the same reconstitution technique; and easy social mobilisation. The second preference would accordingly only be required in a situation where DPT+Hib was not available.

Introduction of new vaccines is expected to commence in January 2004.  The number of children targeted to be vaccinated with the new vaccine DPT+Hib in 2004 is 406,414 representing 85% of the annual birth cohort of 532,054. The number of doses requested for 2004 is 1,621,592. The other requirements are 1,533,357 AD syringes and needles including those for reconstitution, and 17,020 safety boxes. The requirements for the second preference, tetravalent DPT-Hib (liquid) vaccine, are 1,621,592doses, 1,353,359 A-D syringes and needles, and 15,022 safety boxes.

The ICC has chosen to monitor the implementation of GAVI project using DPT3 coverage; drop out rates; supply of vaccines and AD syringes at facility level; and sentinel disease surveillance for Haemophilus influenzae type b. A Mid Term/EPI Review and an End of Term Evaluation will be conducted to monitor the progress of implementation and assess the impact of new vaccines.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of the Republic of Zambia commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:

Dr. S K Miti

Title:       Permanent Secretary

Ministry of Health

Republic of Zambia

Date:      27 February 2003

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation, which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency / Organization | Name/Title | Date | Signature |
| --- | --- | --- | --- |
| - Ministry of Health (MoH) | Dr. S K Miti Permanent Secretary |  |  |
| - Central Board of Health (CBoH) | Dr. B U Chirwa Director General |  |  |
| - United Nations Children Fund (UNICEF) | Dr. S Goings UNICEF Representative |  |  |
| - World Health Organization (WHO) | Dr. E. T. Maganu WHO Representative |  |  |
| - United States Agency for International Development (USAID) | Mr. R. Clay Director of Population, Health and Nutrition Unit |  |  |
| - Japan International Corporation Agency (JICA)) | Mr. K Sasaki Resident Representative |  |  |
| - Rotary International | Mr. D Babbar Coordinator |  |  |
| - Zambia Integrated Health Project (ZIHP) Services | Dr. M L Mantz Chief of Party |  |  |
| - Zambia Integrated Health Project (ZIHP) Systems | Dr. C Musumali Chief of Party |  |  |
| - Department for International Development (DFID) | Mr. A. Daly Health & Population Sector Coordinator |  |  |
| - Central Board of Health (CBoH) | Dr. G Carlson Senior Health Advisor |  |  |

In case the GAVI Secretariat have queries on this submission, please contact:

Name: Dr. S K Miti             Title/Address: Permanent Secretary, Ministry of Health

Tel.No.:  260 1 252 989

Fax No.: 260 1 250 925

E-mail: mitisk@yahoo.com

Alternative address:

Name: Dr. B U Chirwa	     Title/Address: Director General, CBoH.

Tel.No.:  260 1 254 679

Fax No.: 260 1 253 173

E-mail: bchirwa@cboh.org.zm

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 10, 300, 000 (Census 2000) | GNP per capita | 330$US (2000) |
| Surviving Infants* | 431,249 (2001) | Infant mortality rate | 109/ 1000 |
| Percentage of GDP allocated to Health | 10% (2001) | Percentage of Government expenditure for Health Care | 15% (2001) |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported (1) |  | Survey (2) |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 91% | N/A | N/A | N/A | 92% | 12-23 mo | Tuberculosis | 9,045 | 8,397 |
| DTP | DTP1 |  | N/A | N/A | N/A | N/A | 92.5% | “ | Diphtheria | 51 | 50 |
|  | DTP3 |  | 91% | N/A | N/A | N/A | 75.5% | “ | Pertussis | 1,005 | 803 |
| OPV3 |  |  | 96% | N/A | N/A | N/A | 78% | “ | Polio | 0 | 3 |
| Measles |  |  | 82% | N/A | 85% | 0-59 mo | 85% | “ | Measles | 15,365 | 16,859 |
| TT2+ (Pregnant women) |  |  | 61% | N/A | N/A | N/A | 60% |  | NN Tetanus | 130 | 127 |
| Hib3 |  |  | N/A | N/A | N/A | N/A | N/A | “ | Hib | N/A | N/A |
| Yellow Fever |  |  | N/A | N/A | N/A | N/A | N/A | “ | Yellow fever | N/A | N/A |
| HepB3 |  |  | N/A | N/A | N/A | N/A | N/A | “ | HepB seroprevalence (if available) | 6.5% (1993) | N/A |
| Vitamin A supplementation |  | Mothers (< 6 weeks after delivery) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |
|  |  | Infants (> 6 months) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |

(1) The source of these reports is: Health Management Information System at Central Board of Health

(2) These data are collected from the following surveys:  EPI Survey for Zambia, March 2001 by MOH/WHO; 	Measles Cases Cluster Survey and Impact of Supplemental Anti-Measles Immunisation in Four Urban Districts in Zambia, August 2000 by MOH/CBoH/Tropical Diseases Research Centre (TDRC).

The numbers of reported cases are drawn from reports for under-5 children as there is no system in place with category of under 1 age group. Similarly the system for monitoring routine Vitamin A supplementation and reporting is just being developed.

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: National coverage estimates using HMIS have been unreliable because of the use of wrong denominators in districts. This was why an EPI cluster survey was conducted in 2001 to assess the true coverage rates for DPT and other antigens using immunization card/history of children 12-23 months of age. The survey revealed that the DPT3 coverage for Zambia is 75.5%. Meantime apart from the cluster survey, Measles Cases Cluster Survey and Impact of Supplemental Anti-Measles Immunisation in Four Urban Districts in Zambia, August 2000 by MOH/CBoH/Tropical Diseases Research Centre (TDRC) have also been used to assess coverage. Tally sheets have now been revised and the issue of wrong denominators has been rectified.

- Summary of health system development status relevant to immunization:

Zambia started the Health System Reforms in 1991 with the aim of providing equity of access to quality health services as close to the family as possible. The vision, objectives and targets of the reform are defined in the National Health Policies and Strategies (1992).

A major objective of the reform has been the development of district health systems as the basic units for delivering health services in all parts of the country. The reform process has consequently involved a redefinition of the roles of the Ministry of Health as the health policy making body of Zambia; and the creation of a Central Board of Health (CBoH) as a technical unit responsible for the delivery of services through contractual arrangements with district health management boards. The CBoH was established in January 1997.

The reform process required decentralisation of financial and administrative powers to the district and provincial level hospitals as well as district health management boards, and active involvement of community neighbourhood health committees in the decision making process. This has resulted in the devolution of responsibility for planning and managing health care interventions to the districts with varying degrees of programme integration.

Initially the reform process concentrated on ‘systems development’ to meet external pressures for financial probity and good governance.  It is now recognised at all levels that it is still necessary to place emphasis on service delivery (as outlined in the National Strategic Health Plan 1998 –2000 and reaffirmed in the National Health Strategic Plan 2001-2005) and in particular on programmes dealing with diseases of public health importance (such as all vaccine preventable diseases) in an environment where integration is being encouraged.

| - Attached are the relevant section(s) of strategies for health system development | Document numbers 1& 2 |
| --- | --- |
| - Overall government health policies and strategies: National Health Policies and Strategies | Document number 1 |
| - Structure of the government health services and how it relates to immunization services (with an organisational chart): Ministry of Health and CBoH Organogram | Document number 2 |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) and their impact on immunization services National Health Policies and Strategies | Document number 1 p1-8 |
| - Government policies and practices on private sector participation, as it relates to immunization services National Health Policies and Strategies | Document number 1 p24-5, |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism, which is referred to in this document as ICC.

- Name of the ICC: Zambia Inter-Agency Coordinating Committee for Child Health

- Date of constitution of the current ICC: November 1999 (First as Child Health Advisory Committee that emerged from IMCI Advisory committee which was constituted in April 1997).

- Organisational structure (e.g., sub-committee, stand-alone): stand-alone

- Frequency of meetings: Every two months. The UCI Secretariat is responsible for the coordination of these meetings. Minutes of the last three meeting minutes are attached in the Annex.

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Permanent Secretary, Ministry of Health | Dr. S K Miti |
| Secretary | Child Health Specialist (National EPI Manager) Central Board of Health | Dr. M Katepa-Bwalya |
| Members | - Director General, CBoH | Dr. B U Chirwa |
|  | - Senior Health Advisor (DANIDA), CBoH | Dr. G Carlson |
|  | - WHO Representative, WHO | Dr. E T Maganu |
|  | - UNICEF Representative, UNICEF | Dr. S Goings |
|  | - Director, Population and Health, USAID | Mr. R Clay |
|  | - Resident representative, JICA | Mr. K Sasaki |
|  | - Health and Population Coordinator, DFID | Mr. A Daly |
|  | - Chief of Party, ZIHP SERVICES | Dr. M L Mantz |
|  | - Chief of Party, ZIHP SYSTEMS | Dr. C Musumali |
|  | - Coordinator, ROTARY INTERNATIONAL (DISTRICT 9210) …………. | Mr. D Babbar |

- Major functions and responsibilities of the ICC:

- Resource mobilization.

- Advice and approve plans for routine and supplemental immunizations, IMCI and Child Health promotion week activities.

- Advocacy for sustained political commitment.

- Monitor and evaluate EPI and other child health programmes

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Reduce frequency of full ICC meetings from once every two months to once every quarter, and establish technical sub-groups of the ICC to prepare the technical discussions and decisions

b)   Timely dissemination of minutes of meetings to all members.

c)   Place ICC/vaccine financing issues on Health Sector financing agenda.

d)   Ensure that all EPI plans are discussed and endorsed by  the ICC.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal:

- Drop-out rates

b)    Supply of vaccines and AD syringes at facility level.

c)    Disease surveillance: Hib cases detected at the sentinel surveillance site

Attached are the supporting documents:

| - Terms of reference of the ICC | Document number 3 |
| --- | --- |
| - ICC’s work plan for the next 12 months | Document number 4 |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization programme | Document number 5a, 5b, 5c |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| - Sustaining the Benefits of Immunization within Zambia Health Reform - EPI programme review of 1997 | WHO, UNICEF, JICA, BASICS/USIAD and MOH. | Sep.–Oct. 1997 |
| - Cluster Survey of Measles Cases and Impact of Supplemental measles Immunization in Four Urban Districts in Zambia. | Tropical Diseases Research Centre, UNICEF, MOH, CBOH | July- Oct 2000 |
| - Investigation of Measles Outbreaks in Zambia | CBOH, MOH, WHO, CDC | August 2000 |
| - EPI Cluster Survey for Zambia | MOH, CBOH, WHO | March2001 |

- The three major strengths identified in the assessments:

- EPI Review 1997 - 88 % of the health facilities held fixed immunization session - 77 % of the health facilities held out -reach sessions - 85 % of the health facilities maintained good sterilization procedures - 75 % of the health facilities screened infants appropriately - 89 % used sterile needles/syringes correctly - 91% used children’s clinic card as tool for storing information on growth monitoring and immunization Exit interviews with caretakers revealed that 72% had good knowledge of EPI target diseases and that 72% felt satisfied with the quality of service delivery and interaction with health workers.

- Cluster Survey of Measles Cases and Impact of Supplemental measles Immunisation in Four Urban Districts in Zambia. - Majority of the children (84%) received measles vaccination at health centres within the routine immunization service. - About 84.6% of the cases had been vaccinated. This was an indicator that the vaccination campaign was a success.

3. Investigation of measles outbreaks in Zambia (Lusaka, Choma & Mazabuka districts). - There was less number of cases (35%) in rural districts, under the age of five years than in the urban area (60%). - Higher routine immunisation coverage were achieved leading to a slower build up of susceptibles in the population. - The 1999 mass measles campaign in Lusaka resulted in a decrease in the percentage of total cases in the target age group of 9-59 months.

- The three major problems identified in the assessments:

1. EPI programme review of 1997 - Service delivery and quality assurance – gaps between performance standards and formulated guidelines were identified. - Logistics and Cold chain system – absence of long-term planning (forecasting). - Constant break down of old cold chain equipment. - Communication with caretakers, health information management, disease surveillance and case definitions were weak, unclear and inconsistent. - Importance of surveillance and use of data not known, poor health worker communication skills.

2. Cluster Survey of Measles Cases and Impact of Supplemental anti measles immunisation in Four Urban Districts in Zambia. - Vaccinations conducted through mass campaigns are rarely recorded on individual children’s cards, thus making verification difficult. - Of the age group of 9 – 59 months old children targeted for measles immunization, only 62% were vaccinated on schedule. - There is a high rate of measles cases (84%) among vaccinated children, warranting a closer look at the quality of vaccines and the efficiency of the vaccine delivery system and the cold chain system.

3. Investigation of measles outbreaks in Zambia (Lusaka, Choma & Mazabuka districts). Zambia continues to have many measles cases with a large and increasing percentage occurring in children over five years of age. Mass campaigns conducted in limited geographic areas and reported low campaign coverage of 81%, yielding limited impact as measles cases still persist in the targeted age group in the post campaign period. - Many cases were found in unvaccinated children at 9 months of age, reflecting incomplete coverage at this age of immunization schedule. - Many more cases (72% - 80%) were found in the children documented or reported to have been vaccinated against measles. This may be due to the weak of cold chain system leading to vaccine failure and tallying problems.

- The three major recommendations in the assessments:

- EPI programme review of 1997 - Provide training in EPI management and support visits in order to improve performance and communication skills - Provide simple case definitions and training in surveillance - Improve in long term logistics forecasting including the cold chain

- Cluster Survey of Measles Cases and Impact of Supplemental anti measles Immunisation in Four Urban Districts in Zambia. - Health education, information and communication to focus on timely immunization against measles. - Address the need for cold chain logistics especially in districts where little impact is made at controlling measles morbidity in spite of high reported vaccination coverage. - In view of the epidemiological shift and the increase in measles cases among the age groups 10-15 years and over 15 years, consider including these age groups in future mass measles campaigns.

- Investigation of measles outbreaks in Zambia (Lusaka, Choma & Mazabuka districts). - Conduct a thorough EPI programme review and develop practical strategies to strengthen routine immunization services. - Offer a second opportunity for measles immunization through mass campaign to control / eliminate the disease. - Invest in logistical support to strengthen the cold chain system, training and supervision of staff.

- Attached are complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number 6 |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 7 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Hib Disease Burden Assessment for July-December 2002 | March 2003 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 8 |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Training on New and Under-used Vaccines | Fourth quarter 2003 | WHO & UNICEF |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG, OPV0 | Birth | X |  |  |
| OPV1, DPT1, DPT-Hib1 | 6 weeks | X |  | DPT-Hib1 will be introduced in 2004 |
| OPV2, DPT2, DPT-Hib2 | 10 weeks | X |  | DPT-Hib2 will be introduced in 2004 |
| OPV3, DPT3, DPT-Hib3 | 14 weeks | X |  | DPT-Hib3 will be introduced in 2004 |
| OPV4*, Measles | 9 months | X |  | OPV4 is given if OPV0 was missed |
| DTP4 | 18 months | X |  |  |
| Vitamin A | 6-11months, 12-59months | X |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

| Action points | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| Staff Training Conduct EPI /MCH staff training to update knowledge and skills | x | x | X |  |  |  |
| Strengthen cold chain system Implement cold chain equipment replacement plan | x | x | x | X | X |  |
| Improve transport facilities Improve means of transport Facilities at health centre level e.g. procure/ provide motor bikes and bicycles (when funds are secured) |  | x | x | X | X |  |
| Social Mobilization Strengthen social mobilization for routine immunisation services by developing print and electronic media messages. | x | x | x | X | x | x |
| Personnel allowances Provide adequate funds to health workers’ DSA or lunch allowances and fuel for outreach services. | x | x | x | x | x | x |
| Child Health promotion weeks Continue with established period bi-annual (Feb & Aug) contacts with under five children for catch up immunisation, SOS, vitamin A supplementation, deworming and IEC activities etc. | X | X | X | X | X | X |

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2001 | 2002 | 2003 |  | 2004 | 2005 | 2006 | 2007 | 2008 |
| Births |  | 479,882 | 496,678 | 514,062 |  | 532,054 | 550,676 | 569,950 | 589,899 | 610,546 |
| Infants’ deaths |  | 52,307 | 54,138 | 56,033 |  | 57,994 | 60,024 | 62,125 | 64,300 | 66,550 |
| Surviving infants |  | 431,249 | 446,342 | 461,965 |  | 478,134 | 494,868 | 512,190 | 525,599 | 543,396 |
| Pregnant women |  | 431,249 | 446,342 | 461,965 |  | 478,134 | 494,868 | 512,190 | 525,599 | 543,396 |
| Infants vaccinated with BCG* |  | 441,491 | 466,877 | 488,359 |  | 510,772 | 534,156 | 558,551 | 584,000 | 604,441 |
| Infants vaccinated with OPV3** |  | 344,999 | 366,000 | 388,051 |  | 411,195 | 435,484 | 460,971 | 487,707 | 515,187 |
| Infants vaccinated with DTP3** |  | 327,749 | 348,147 | 369,742 |  | 406,414 | 435,484 | 460,971 | 487,707 | 515,187 |
| Infants vaccinated with**: DPT-Hib 3 |  | 327,749 | 348,147 | 369,742 |  | 406,414 | 435,484 | 460,971 | 487,707 | 515,187 |
| Infants vaccinated with Measles** |  | 366,562 | 388,318 | 411,149 |  | 439,883 | 465,176 | 491,702 | 514,213 | 537,110 |
| Pregnant women vaccinated with TT+ |  | 323,437 | 343,683 | 369,572 |  | 396,851 | 425,586 | 450,727 | 477,104 | 504,225 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |
|  | Infants (> 6 months) | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

Specific strategies for reducing dropout rates and vaccine wastage include the following:

- Re-training of first level health workers on EPI management to improve knowledge and skills.

- Ensure regular supply of all five EPI antigens, appropriate injection and cold chain equipment and other logistics to all districts.

- Replace 65% of the required cold chain equipment of the five-year plan and procure essential supplies for routine maintenance and repair. JICA has provided about 50-55% of the requirements.

- Prioritize health centres in all districts to receive the new fridges expected from JICA in 2002 as part of replacement plan. This has been accomplished with 50-55% of the requirements being met.

- Districts to conduct regular sessions to all outreach sites and increase the number of sites where necessary.

- Establish and conduct periodic and sustainable outreach services, contact with hard to reach population.

- Prioritize districts with below 70% immunization coverage for measles, hard to reach/unreached areas and refugee population through provision of extra financial support.

- Develop, produce and disseminate IEC messages for print and electronic media concerning routine immunization service e.g. radio spots, posters and fliers.

- Improve operational and supervisory capacity of the central-level UCI Secretariat, provincial offices and DHMTs (e.g. transport, communication, office equipment, operating costs for the secretariat, etc.).

- Implement an improved logistics distribution system, from central and provincial to district level and to all health facilities.

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate |  |  | 25% | 25% | 20% | 15% | 10% | 10% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 18% | 17% | 16% | 15% | 14% | 13% | 12% | 10% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

Not Applicable

- Planning and constraints for the Polio Eradication Initiative:

Supplemental Polio SNIDs

The main constraints to the SNIDs implementation are:

- NIDs fatigue both at community and policy planning levels.

- Erratic and inadequate health care financing resulting from deteriorating economic situation makes it very difficult for the nation to contribute to NIDs financially

- Transport/fuel problems to immunize children in hard-to-reach areas.

- Inadequate cold chain equipment/space for outreach services.

- Late arrival of funds and vaccines into the country

AFP surveillance

The main constraint to reaching certification level AFP surveillance had been the late detection of cases resulting in the inability to take stool samples in time. This has been adequately addressed and stool adequacy stood at 100% while non-polio AFP rate was 1.41 per 100,000 children under 15 years as at the end of January 2003.

A major threat to the Zambian polio eradication activities is the possibility of importation of wild-type polio virus from endemic bordering countries. The large number of refugees coming from these countries heightens this threat.

# Injection safety

7.1 Summary of the injection safety strategy for immunization (for all countries):

The current policy of Zambian immunization Programme is to use sterilisable, reusable needles and syringes.  In order to ensure provision of safe immunization injections, including sustainable supply of appropriate injection and sterilization equipment, the following strategies should be in place:

- Ensure adequate supply of reusable needles and syringes including steam-sterilizing equipment until auto-disable equipment is universally available at country level on a sustainable basis.

- Improve health workers knowledge and skills using the newly revised EPI vaccination manual, which includes safe injection safety. Training has already started at central level.

- Advocate for GAVI to supply auto-disable syringes for universal use, which should not only be for new vaccines but also for traditional injectable antigens in the child health programmes. GAVI has already started supplying AD syringes and injection equipment for use in routine immunization.

- Advocate for other donors to invest in childhood immunization programs particularly funding for auto-disable syringes and other vaccine supplies

- Explore and develop strategies for safe disposal of used auto-disable syringes.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 9 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with …… ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | Match with targets in table 4 |  |  |  |  |
| B | Number of doses per child (or per woman in case of TT) | # |  |  |  |  |
| C | Number of …… doses | A x B |  |  |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E |  |  |  |  |
| G | Number of doses per vial | # |  |  |  |  |
| H | Vaccine wastage factor | Either 2 or 1.6 |  |  |  |  |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |  |  |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
|  | AD syringes and waste disposal boxes |  |
| GAVI/Vaccine Fund |  |  |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

- Target group and schedule

Priority for vaccination with new vaccines will be given to children under the age of 1 using the existing schedule for DPT (no booster)

- Injection Equipment and Sharps Waste Management

There is a plan to introduce AD Syringes and waste disposal boxes in routine immunisation

- Surveys/Mid term reviews

These will be conducted to assess the progress, achievements and failures

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | Horizontal Transmission of Hepatitis B Virus Among Children and Adults in Five Rural Villages in Zambia Tabor E, Bayley AC, et al. | 1985 | Residents of five rural villages in rural eastern Zambia were tested for hepatitis B serologic markers to determine whether horizontal transmission of hepatitis B contributes to the high prevalence of this infection in an endemic area. In this study, new infections in children and adolescents were shown to occur within a five-year period with an incidence rate of 18%, representing an estimated minimum annual incidence of 3.6%. Since the mothers of these children and adolescents with new infection were HbsAg-negative, the new infections were probably acquired through horizontal transmission from someone else other than their mothers. Throughout the paediatric age groups the prevalence of HBsAg and anti-HBs increased with age. |
| Hepatitis B | Antibody Responses of Adults, Adolescents, and Children to a Plasma-Derived Hepatitis B Vaccine in a Rural African Setting. Tabor, E., Gerety, R. J., et al. Journal of medical Virology 32:134-138 | 1990 | The response rate to HBV vaccine was higher among children (ages 0 to 11 years). All 100% of children receiving three doses of vaccine responded with protective levels of anti-HBs. This was similar to the anti-HBs response in 95% of children in the Gambia receiving hepatitis B Vaccine. Children in Africa can benefit from hepatitis B vaccination, even if the vaccine is administered later than the newborn period. The use of the recommended three vaccine doses in children is advisable, as significantly more children responded to three doses (100%) than to two doses (78%) (P value < 0. 01). Use of hepatitis B vaccine in this region where pre-vaccination hepatitis B serologic screening was not available did not appear to increase the number of or severity of adverse reactions. |
| Hepatitis B | The prevalence of Hepatitis B antigen (HBsAg) and its antibody (Anti-HBS) among London hemophiliacs and blood donors from London and two tropical areas. | 1976 | Among 12% of the blood donors and 6% of hemophiliacs had HBsAg in Zambia. A high proportion of hemophiliacs (59%) was anti-HBs positive, this being comparable with the Zambian blood donors (53%). |
| Hepatitis B | The incidence of hepatitis B-antigen and anti-hepatitis-B among blood donors in Ndola, Zambia. Islam M N, et al. | 1975 | Hepatitis B antigen (HBsAg) was detected in 11.6% of blood donors in Ndola, Zambia, mostly prisoners and students. Incidence rate among prisoners was 15.1% while among students only 1.6%. Overall anti-HBs was detected in 52.8% of blood donors. |
| Hepatitis B | Epidemiology of Hepatitis B Infection in Zambia |  | Sero-prevalence of hepatitis B virus was studied in pregnant women attending antenatal clinics in urban and rural areas of Zambia and in children in urban community of Lusaka. Zambia is a medium to high endemic area for Hepatitis B virus. Prevalence of HBsAg in pregnant women was 6.65% and HBeAg was present in 16.1% among HBsAg positive women. Both HBsAg and antibodies to HBV were significantly higher in rural than in urban area. The reason for higher prevalence of HBV in rural area is unclear. In Lusaka HBV infection is not common before the age of five and about 15% of children are exposed to HBV by 15 years. Prevalence of HBV markers increased by age in children of urban community. The prevalence of HbsAg and of any markers to HBV was significantly higher in children aged 6-15 years than in those aged o-5 years. Horizontal transmission in childhood rather than vertical is a more important mode of transmission in Zambia. History of injection and blood transfusion was significantly correlated with positivity of HBV markers in children of urban community. Medical treatments might be major risk factors for HBV transmission in children of urban community in Zambia. The significant increase of prevalence of HBV infection found after five years of age suggests that injection for immunisation, which given before the age of one year, may not be a major risk factor for HBV transmission in the study population. The reason why injection for treatment rather than for immunisation was an important risk was not clear. |
| Haemophilus influenzae type b | Hib Sentinel Surveillance (Hib Sentinel Surveillance Site, UTH) | 2002 | It was found that Hib accounted for about 25% of all cases of meningitis seen in UTH during the period January-June 2002 |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

Not Applicable

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines:

  - Storage capacity

The current storage capacity makes provisions for multi-dose vials of DPT-Hib. Therefore, there is adequate storage space at the central and provincial level as long as the vaccine supply is done on a quarterly basis.

  - Staff training

The training of master trainers on Injection Safety and Revised EPI guidelines has just been conducted and the provincial training will follow shortly. However, additional financial resources are required for facility level training.

  - Cold chain

There is need for replacement of obsolete cold chain equipment, and also to provide additional cold rooms at provincial level. However, JICA has recently supplied cold chain equipment to districts and this has met about 55% of the requirements for replacement of such equipment. In addition, UNICEF has also supplied cold boxes and vaccine carriers to some districts but more will be required.

  - Logistics

GAVI has already started supplying AD syringes and injection equipment for use in routine immunisation and will supply the same for new vaccines once the application has been approved.  However, improvement of transport for vaccine delivery and outreach services remains an important issue and so is the rehabilitation or construction of incinerators for safe waste disposal in the districts.

  - Dropout rates

There is need to intensify social mobilization for vaccines, make available resources / supplies for outreach, honour schedules for outreach services to reach those hard to reach, ensure quality services, and encourage community participation in defaulter-tracing. At the facility level a new tally sheet will be introduced alongside training to ensure accurate recording and reporting of data.

  - Missed opportunities

Introduction of the open-vial policy, and introduce immunization services at every health facility in a “supermarket approach”. The other strategy is to provide adequate support to outreach services.

  - Wastage rate

There is need for introduction of open vial policy, proper cold chain management, staff training in strategic planning of immunization sessions, and scheduling with intensive community mobilization to attract more clients and reduce wastage. From the recent training conducted for Master Trainers, it has been observed that staff need to be equipped with knowledge and skills for vaccine management. As a consequence the subsequent trainings will focus a lot on vaccine management.

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses of   DPT+Hib (lyophilized) vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3,)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 369,742 | 406,414 | 435,484 | 460,971 | 487,707 | 515,187 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% | 100% | 100% | 100% | 100% | 100% |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 1,109,226 | 1,219,242 | 1,306,452 | 1,382,913 | 1,463,121 | 1,545,561 |
| E | Estimated wastage factor | see list in table  | 1.33 | 1.33 | 1.25 | 1.18 | 1.11 | 1.11 |
| F | Number of doses (incl. wastage) | A x C x E x B/100 | 1,475,271 | 1,621,592 | 1,633,065 | 1,631,837 | 1,624,064 | 1,715,573 |
| G | Vaccines buffer stock | F x 0.25 | 368,818 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 1,844,089 | 1,621,592 | 1,633,065 | 1,631,837 | 1,624,064 | 1,715,573 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 1,640,629 | 1,353,359 | 1,450,162 | 1,535,033 | 1,624,064 | 1,715,573 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 | 204,694 | 179,998 | 181,270 | 181,134 | 180,271 | 190,429 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 20,483 | 17,020 | 18,108 | 19,049 | 20,028 | 21,157 |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

Table 7.2: Estimated number of doses of   DPT-Hib (liquid) vaccine

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 369,742 | 406,414 | 435,484 | 460,971 | 487,707 | 515,187 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% | 100% | 100% | 100% | 100% | 100% |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 1,109,226 | 1,219,242 | 1,306,452 | 1,382,913 | 1,463,121 | 1,545,561 |
| E | Estimated wastage factor | see list in table  | 1.33 | 1.33 | 1.25 | 1.18 | 1.11 | 1.11 |
| F | Number of doses (incl. wastage) | A x C x E x B/100 | 1,475,271 | 1,621,592 | 1,633,065 | 1,631,837 | 1,624,064 | 1,715,573 |
| G | Vaccines buffer stock | F x 0.25 | 368,818 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 1,844,089 | 1,621,592 | 1,633,065 | 1,631,837 | 1,624,064 | 1,715,573 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 1,640,629 | 1,353,359 | 1,450,162 | 1,535,033 | 1,624,064 | 1,715,573 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 | 0 | 0 | 0 | 0 | 0 | 0 |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 18,211 | 15,022 | 16,097 | 17,039 | 18,027 | 19,043 |

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number 10 |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.e.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

The key issues will be to improve first the funding of vaccines and logistics and second the supply from the central level to districts. Government and the ICC are engaged in the development of the financial sustainability plan. The issues to be considered include:

- Improved allocation by Government of the available local resources to immunization programmes at all levels and strict monitoring of the same

-Government has already accepted the proposal on Vaccine Independence Initiative and the ICC has been informed

The Vaccine Independence Initiative (VII) proposal suggests a Government contribution of 10 % of the total estimated cost of all immunization supplies in the first year of its contribution.  The figure for this contribution is US

$ 100.000. Each subsequent year, it is proposed that the government increases its contribution by an additional 10%, so that by the year 2010 the government would fund all immunization supplies.  In the meantime, the Ministry of Health will continue to seek donor support for the procurement of non-GRZ proportion of the country’s required immunization supplies. Government has made its first contribution of ZMK100, 000,000.00

- Use of international procurement mechanisms for vaccines and timely distribution

-Vaccine forecasting and procurement

-Training of districts in vaccine forecasting and procurement

-Development of district plans of action

- Development of a programme to reduce wastage of vaccines and logistics

-Training and refresher training of health staff

-Monitoring and Supervision

- Consistent and targeted resource mobilization from cooperating partners

-Strengthening the ICC

- Networking the Private Health Service Providers

-Training

-Monitoring

- Devising new strategies to improve access to immunization services

-Enhancing IEC

-Sustaining Outreach Immunization Services

-Maintaining Advocacy and Social Mobilization

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Annex 1 (Tables 1-3) |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

Refer to section 6: Summary of the major action points and time frame for reduction of vaccines wastage rate

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Republic of Zambia

considering that its DTP3 coverage for 2001 was 75.5%  corresponding to 327,749 number of children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		        YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

Not Applicable

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

Since 1999 Government of the Republic of Zambia has established the Health Sector Support Steering Committee. This committee is answerable to the Minister of Health and is chaired by the Permanent Secretary of the Ministry of Health.  The membership consisting of the CBoH and the MOH and representatives of Co-operating Partners in the health sector as follows:

- Danish International Development Assistance (DANIDA)

- Department for International Development of the United Kingdom (DFID)

- German Technical Cooperation

- Ireland Bilateral Aid Programme

- SIDA

- The Commission of the European Union

- The Netherlands Government

- UNICEF

- WHO

- WFP

- UNAIDS

- UNDP

- UNFPA

- World bank

- USAID

The Basket Fund is managed through the MOH/CBoH and in consultation with the Health Sector Support Steering Committee. The Committee holds quarterly meetings to review progress on action plans, accounting/financial reports from the MoH/CBoH, and to review the financial flow in relation to the budget of particular boards.  The Central Board of Health distributed summary financial statements, covering disbursements and actual expenditures from source of funding and item according to each level and cost-centre, together with cost-centre performance appraisals.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| 1st choice: DPT+Hib (lyophilised) | 10 | Jan 2004 | 1,524,053 | 1,541,613 |
| 2nd choice: DPT-Hib (liquid) | 10 | Jan 2004 | 1,524,053 | 1,541,613 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one):

- By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

Not Applicable

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |
| I | Total of reconstitution syringes |  |  |  |  |  |
| J | Total of safety boxes |  |  |  |  |  |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

- The Health Sector Support Steering Committee, safe guards the mechanisms to ensure transparency and accountability in handling of funds from all sources.

- Of great practical concern is what happens after having introduced A-D syringes and subsequently discarding the reusable injection equipment and its sterilisation technology. The ICC will be looking into other ways to sustain the supply of A-D syringes should the GAVI funds stop following at the end of five years.

- Another unmet need is the transport facilities. The infrastructure for delivery of childhood immunisation services in Zambia is in dire need of bicycles, motorcycles, four-wheel drive vehicles to conduct outreach services to the hard-to-reach areas of remote rural Zambian community. For areas surrounded by masses of water (Luapula & Western Provinces), engine motorboats are required as this is the only safe mode of transport for health workers to reach children living on islands.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD, 000)

Table 1

| Expenditure in 2001 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | JICA | Basket | Donor | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - BCG |  |  |  |  | 20,986 | 72,812 |  |  | 93,798 |
| 1.2 | - Meales3 |  |  |  |  | 63,962 |  |  |  | 63,962 |
| 1.3 | - OPV |  |  |  |  | 476,760 |  |  |  | 476,760 |
| 1.4 | - DPT |  |  |  |  | 135,277 |  |  |  | 135,277 |
| 1.5 | - TT |  |  |  |  | 72,545 |  |  |  | 72,545 |
| 1.6 | - AD syringes |  |  |  |  | 26,526 |  |  |  | 26,526 |
| 1.7 | - Sterilisable syringes |  |  |  |  | 56,598 |  |  |  | 56,598 |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Vaccine fridges |  |  |  |  | 2,023 |  |  |  | 2,023 |
| 2.2 | - Cold boxes and Vaccine Carriers3 |  |  |  |  | 5,454 |  |  |  | 5,454 |
| 2.3 | - Training of Cold Chain Technicians |  |  |  |  |  |  | 1,200 |  | 1,200 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Safety boxes |  |  |  |  | 9,293 |  |  |  | 9,293 |
| 3.2 | - Printing vaccination guides and IEC materials |  |  |  |  | 33,668 |  |  |  | 33,668 |
| Total expenditure |  |  |  |  |  | 903,092 | 72,812 | 1,200 |  | 977,104 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Expenditure in 2002 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | JICA | Basket | Donor n. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - BCG |  |  |  |  | 21,375 |  |  |  | 21,375 |
| 1.2 | - Meales3 |  |  |  |  | 378,091 |  |  |  | 378,091 |
| 1.3 | - OPV |  |  |  |  | 507,851 |  |  |  | 507,851 |
| 1.4 | - DPT |  |  |  |  | 253,513 |  |  |  | 253,513 |
| 1.5 | - TT |  |  |  |  | 92,194 |  |  |  | 92,194 |
| 1.6 | - AD syringes |  |  |  |  | 190,693 |  |  |  | 190,693 |
| 1.7 | - Sterilisable syringes |  |  |  |  | - |  |  |  | - |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Vaccine fridges |  |  |  |  | 16,035 | 2,600,000 |  |  | 2,616,035 |
| 2.2 | - Cold boxes and Vaccine Carriers3 |  |  |  |  | 148,262 |  |  |  | 148,262 |
| 2.3 | - Training of Cold Chain Technicians |  |  |  |  |  |  | 1,200 |  | 1,200 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Safety boxes |  |  |  |  | 32,370 |  |  |  | 32,370 |
| 3.2 | - Ice packs |  |  |  |  | 5,137 |  |  |  | 5,137 |
| Total expenditure |  |  |  |  |  | 1,645,521 | 2,600,000 | 1,200 |  | 4,246,721 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 3

| Budget for 2003 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | WHO | UNICEF | JICA | Basket |  |  |
| 1. | Vaccines, AD syringes… | 80,000 |  |  |  |  |  |  |  |  |
| 1.1 | - BCG |  |  |  |  | 86,218 |  |  | 86,218 | __ |
| 1.2 | - Meales3 |  |  |  |  | 133,600 |  |  | 133,600 | 133,600 |
| 1.3 | - OPV |  |  |  |  | 255,000 |  |  | 255,000 | 255,000 |
| 1.4 | - DPT |  |  |  |  | 161,760 |  |  | 207,254 | 45,494 |
| 1.5 | - TT |  |  |  |  | 98,500 |  |  | 98,500 | 98,500 |
| 1.6 | - AD syringes |  |  |  |  | 546,532 |  |  | 546,532 | __ |
| 1.7 | - Sterilisable syringes |  |  |  |  | __ |  |  | __ | __ |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Vaccine fridges |  |  |  |  |  |  |  | 2,127,273 | 2,127,273 |
| 2.2 | - Cold boxes and Vaccine Carriers3 |  |  |  |  | 78,185 |  |  | 78,135 | __ |
| 2.3 | - Training of Cold Chain Technicians |  |  |  | 10,000 |  |  |  | 96,000 | 86,000 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Training Health Workers |  |  |  | 20,000 | 80,000 |  |  | 400,000 | 300,000 |
| 3.2 | - Safety boxes |  |  |  |  | 24,172 |  |  | 24,172 | __ |
|  | - Cold chain spares |  |  |  |  | 13,638 |  |  | 152,330 | 138,692 |
| Total commitment |  | 80,000 |  |  | 30,000 | 1,477,605 |  |  | 4,204,924 | 3,184,559 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number 1 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s work plan for the next 12 months | Document number 3 |
| - Terms of reference of the ICC | Document number 4 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 5a, 5b, 5c |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 6 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 7 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 8 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 9 Document number 10 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Annex 1 (Tables 1-3) |

Formula to calculate DTP vaccine wastage rate (in percentage): [(A – B) / A] x 100.   Whereby: A = The number of DTP doses distributed for use according to the supply records with correction for stock balance at start and end of the supply period; B = the number of DTP vaccinations.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible