Rev 2.

November 2000

The Government of

Bosnia and Herzegovina

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from one or both sub-accounts - immunization services and/or new and underused vaccines. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Government of Bosnia and Herzegovina (BiH) hereby applies for support from the "New and Underused Vaccines" sub-account og the GAVI Global Fund for Children's Vaccines.

Objectives of the support

- Enable BiH' steady access to Hepatitis B vaccine (HepB) for implementing universal infant immunization over 2002-2006, until procurement of HepB is turned over to national funding sources.

- Ensure safe injection of HepB through regular supply of auto-disable syringes and safety boxes which is to become routine practice of the country's EPI.

Eligibility of support

BiH eligibility for the requested support is determined by its per capita GDP of US $ 870, DPT3 coverage rare over 90% (reported 95%, 89% by Cluster surveys) and the Government's determination to raise timely DPT3 and other EPI antigens coverage to over 95% in all geo-administrative units (see Stratagy 2 of the Multi-Year Plan). Operational coverage targets for DPT3 in children <12 months of age down to the municipality level are as follows: >90% from 2001, 95% from 2002 and 96% from 2004.

Parameters of support

|  |  |  | HBv 10 doses | HBv 1 dose |
| --- | --- | --- | --- | --- |
| 2002 | vaccine | doses | 148024 | 51956 |
|  |  | cost | 99175.91 | 32212.93 |
|  | Freight + over expenditures |  | 34711.57 | 11274.52 |
|  | TOTAL |  | 133887.48 | 43487.45 |

ICC participation in preparing this proposal

This Proposal was prepared by the Ministries of Health of FBiH and RS and the EPI coordinators with the technical support of UNICEF/BiH and WHO/BiH. Two meetings were called to discuss draft Proposal. Ongoing discussions had been held between the local UNICEF and WHO and their consultants who carried out a thorough assessment of BiH' EPI, offered guidance in developing of a Multi-Year Strategic Plan for Immunization, participated in 2 ICC meetings and had separatte meetings with different actual and potential international partners.

# Signatures of the Government

The Government of Bosnia and Herzegovina commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:…………………………………………... (Prof. Zlatko Lagumdzija)

Title:	Minister of Foreign Affairs of Bosnia and Herzegovina

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual. (Guidelines on Country Proposal # 2.) :

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Assistant Representative, UNICEF | David Baker |  |
| UNDP | Henrik Kolstrup, Resident Co-ordinator |  |
| Ministry of Health of Republika Srpska | Milorad Balaban, Minister of Health |  |
| The World Bank | Mirjana Karhasanovic, Project Analyst |  |
| World Health Organization | Nezahat Ruzdic, Liaison Officer |  |
| USAID BIH | Robert Jacobs, Deputy Director |  |
| Ministry of Foreign Affairs | Sabahka Radzo |  |
| Federal Ministry of Health | Zeljko Misanovic, Minister of Health |  |

In case the GAVI Secretariat has queries on this submission, please contact:

Ms Sabahka Radjo

Advisor,

Ministry of Foreign Affairs

Musala 2

71000 Sarajevo

Bosnia and Herzegovina

Tel. No.: +387 33 281 158

Fax No.:+387 33 281 007.

E-mail : sradjo@yahoo.com

Alternative addresses:

Dr Zeljko Misanovic					Dr Milorad Balaban

Federal Minister of Health 				Ministry of Health of Republika

Federal Ministry of Health 				Srpska

Marsala Tita 9						Zdrave Korde 8

71000 Sarajevo					78000 Banja Luka

Bosnia and Herzegovina				Bosnia and Herzegovina

Tel: +387 33 664 256					Tel: +387 51 216 600

Fax: +387 33 664 245					Fax: +387 51 216 601

- Immunization-related fact sheet

| Table 1 : Basic facts (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population(1) | (1999) 3,724,580 | GNP per capita(2) | (1998) 870 $US |
| Surviving Infants* (1) | (1999) 42,759 | Infant mortality rate (1) | (1999) 10.1/ 1000 |
| Percentage of GDP allocated to Health (2) | (1998) 7.7 | Percentage of Government expenditure for Health Care (3) | (1997) 8.3 |

* Surviving infants = Infants surviving the first 12 months of life

Sources:

- Agency for Statistics of Bosnia & Herzegovina, Statistical bulletin 2, 2000

- National Health Account for 1998 in Bosnia & Herzegovina; Department for International Development, Know How Fund, Health & Life Sciences Partnership

- Human development report, Bosnia & Herzegovina, 1998 UNDP

Table 2: Immunization coverage and disease burden trends as per annual reporting to WHO/UNICEF

| ### Trends of immunization coverage ### by 12 months of age |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported (1) |  | Survey (2) |  |  |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  |  | 1998 | 1999 | 1999 | Age group | 2000 | Age group |  | 1998 | 1999 | 1998 | 1999 |
| BCG |  | 95 | 99.2 | 98.0 | 13-25 mos | 94.0 | 13-25 mos | Tuberculosis | 2,759 | 2,377 | na | na |
| DTP | DTP1 | 89.5 | 93.5 | Na |  |  |  | Diphtheria | 0 | 0 | na | Na |
|  | DTP3 | 92.0 | 95.0 | 89.0 | 13-25 mos | 89.0 | 13-25 mos | Pertussis | 130 | 71 | na | Na |
|  | [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | Na | Na | Na |  | na |  |  |  |  |  |  |
| OPV3 |  | 92.0 | 95.0 | 87.0 | 13-25 mos | 88.0 | 13-25 mos | Polio | 0 | 0 | 0 | 0 |
| Measles |  | 82.0 | 80.0 | 74.0 | 13-25 mos | 79.0 | 13-25 mos | Measles | 3,141 | 73 | na | Na |
| TT2+ Pregnant Women |  | N/A | N/A | N/A |  | N/A |  | NN Tetanus | 0 | 0 | na | Na |
| Hib |  | N/A | N/A | N/A |  | N/A |  | Hib | N/A | N/A | N/A | N/A |
| Yellow Fever |  | N/A | N/A | N/A |  | N/A |  | Yellow fever | N/A | N/A | N/A | N/A |
| HepB |  | N/A | 80.0 FBiH | N/A |  | N/A |  | HepB seroprevalence (if available) | na | na | na | Na |

Table 2 (supplement) Immunization Coverage of Children before the 1st Birth Day, i.e. born in 1998-1999  – MICS’2000

| BCG | 95% |
| --- | --- |
| ###### DPT1 | 91% |
| DPT3 | 85% |
| DPT1-DPT3 | 6.6% |
| OPV3 | 82% |

- The source of these reports is : Official data from PHIs; WHO/UNICEF Joint Reporting Form on VPD for the period Jan-Dec 1998 prepared by EPI national co-ordinators

- These data are collected from the following surveys : UNICEF (2000), Multiple Cluster Indicator Survey/Household Survey of Women and Children

Summary of health system development status:

The health service system in BiH dates from the pre-war era, when there was a substantial network of facilities and the whole population enjoyed reasonable access to clinics, hospitals and public health facilities.

Since the end of the conflict, responsibility for healthcare has been under the governments of the two Entities. Within the RS the overall system has remained relatively centralized, while in FBiH healthcare has been devolved further down to cantonal level.

Government and public administration of RS follows a unitary state model that subdivides the Entity to 63 administrative municipalities. Law establishes the principle of local self-government. The Entity Prime Minister and its cabinet govern through local level ministerial offices. Municipal level branches of Entity ministries, including the MOH, are responsible directly to their Minister.

The MOH issues statues and regulations for the implementation of its programmes.

The FBiH Constitution endorses decentralization through a cantonal system. The 10 cantons are in turn subdivided in municipalities. Cantons and municipalities have high degree of autonomy and broad powers. Each canton has its own Ministry of Health, i.e. vertical links between the Entity MOH and the Primary Health Care are not that direct and strong as it is in RS.

Health care in BiH is organized at three levels: primary, secondary and tertiary.

Traditionally, much more emphasis had been put on curative medicine than on disease prevention and health promotion. Primary health care (PHC) is performed in Health Centers (HCs) in urban areas and ambulantas in the rural areas. A significant proportion of cases is referred to higher levels of care.

Immunization services are provided by HCs and ambulantas. Public Health Institutes at the Entity level (FPHI&RPHI) are responsible for the implementation of the two parallel  Expanded Programmes on Immunization (EPI). The EPI managers, who are among the senior staff of the Institutes are involved in policy-making on immunization, planning of immunization, annual analysis of immunization coverage and disease burden of vaccine preventable diseases (VPDs) at the Entity level.

Cantonal/Regional PHIs are responsible for the EPI at their respective level. The Public Health network is directly under the Entity MOHs. However, PHIs are mainly involved in guidance of vaccine providers and do not exert systematic monitoring and supervision upon immunization practices.

Among the problems faced by the BiH health care system are duplication despite compartmentalization. There was a distinct separation between inpatient and outpatient care delivered by stand-alone outpatient clinics. Patients and families found it hard to draw a clear line between primary health care and specialized care. A number of adverse incentives were at work such as emphasis on institutional long-term care and long stays in hospitals, outnumbered as well as overspecialized staffing patterns, overstatement of activities, deficits subsidized through non-competitive funding, jobs for life irrespective of performance, lack of effective functional integration.

A Health Care Reform started in both entities at the end of the 1990s. Its cores are the introduction of Health Insurance systems and decentralization. A gradual shift of PHC from the territory principle of serving to “family medicine” has started.  Family Doctor (FD) is to become the entry point for coordination of all health care. As the development of health care based on Family Medicine concept is a long-term process, Health Centers (Dom zdravljas) have to keep some of their functions in a transitional period. It is expected that most specialists now working in these centers will be motivated to work in Family Medicine. A considerable number of the specialists at HCs will continue working in hospitals, but will also provide consultative services to FDs.

Interaction between family medicine and the Public Health Service in the field of immunization has not yet been discussed in details. Immunizations are still obligatory and free-of-charge for the population by law. There is no clear vision on private practice in the field of immunization. Provision of "recommended" immunization is under discussion among researchers but that issue has not yet been addressed to the MOHs.  The recently developed Multi-year Strategic Plan for Immunization (MYSPI) represents a basis for the development and implementation of Health Reform in the area of VPDs prevention and control.

Health financing:

(1)	FBIH

The Health Insurance Law was approved in 1997 in FBiH, providing for most health services to be financed from earmarked payroll taxes and devolving most health financing responsibilities to the cantons. The implementation of this Law in its current form presents some risks, principally among the following:

- Fragmentation of risk pools, particularly in the smallest cantons;

- High administrative costs and inefficiencies;

- Perpetuation of “ethnic” divisions: since the law provides for a voluntary merger of Cantonal Insurance Funds, there is a risk of mergers along the lines of “ethnic affiliation”;

- Wide variations among cantons in the revenues per capita available for health services; and

- Mergers of wealthier cantonal funds, to the exclusion of the poorer funds.

(2)	Republika Srpska

In the Republika Srpska, the main institution for health care financing is the Public Health Insurance Fund. The Fund is in a transitional phase, with a National Office in Banja Luka and four branch offices. The draft statutes include provisions for a “solidarity fund” to cover expenditures including a yet-to be defined “basic minimum package of services”.

Its implementation has to face some challenges including: (1) a high rate of unemployment; (2) refugees and displaced persons are uninsured but have the right to health care; (3) the cost of health care for pensioners and their families which is about 12 times their revenues; and (4) Irregular RS Government transfer to the Fund.

Supporting documents:  (only copies of relevant pages are attached)

| - Overall government health policies and strategies | Document number 1 and 2 |
| --- | --- |
| - Structure of the government health services and how it relates to immunization services (with an organisational chart) | Document number 1 and 2 |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) and their impact on immunization services | Document number 1 and 2 |
| - Government policies and practices on private sector participation, as it relates to immunization services | Document number no policies so far |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services in the country, are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC. (Guidelines on Country Proposal # 4.1.)

- Name of the ICC: Inter Agency Co-ordination Committee

- Date of constitution of the current ICC:  27 October 2000

- Organisational structure (e.g., sub-committee, stand alone) : Stand alone. Two entities Minister of Health share chairmanship on the rotational basis. Secretarial support provided by UNICEF. Members – see below.

- Frequency of meetings: quarterly

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister of Health/Federal Ministry of Health Minister of Health/Ministry of Health of Republika Srpska | Dr Zeljko Misanovic Dr Milorad Balban |
| Secretary | Administrative Assistant/UNICEF | Selma Turkic |
| Members | - Assistant Representative/UNICEF - Resident Representative/ UNDP - Project Analyst/The World Bank - EPI manager/RS Public Health Institute - Liaison Officer/WHO - Deputy Director/USAID BiH - Ministry of Foreign Affairs - EPI manager/FBIH Public Health Institute | David Baker Henrik Kolstrup Mirjana Karahasanovic Mitar Tesanovic Nezahat Ruzdic Robert Jacobs Sabahka Radjo Zlatko Puvacic |

- Major functions and responsibilities of the ICC:

Discusses achievements and failures of the Annual Plans of Action for Immunization in the context of the Multi-year Strategic Plan for Immunization  (2002-2006) as well as additional activities/interventions aiming to meet operational immunization coverage and disease reduction targets, to ensure safe immunization practices and vaccine wastage reduction

Participates into field assessments of basic strategies and activities of the Multi-year Plan such as safe immunization practices, wastage reduction, cold chain effectiveness, adequacy of recording and reporting of VPDs, immunization coverage and AEFI.

Discusses financing of the BiH EPI and mobilizes resources for important needs not met.

Discusses feasibility of supplementary vaccination during epidemic upsurges of VPDs and mobilizes resources for implementation of outbreak control measures.

Discusses achievements and failures of the Annual Plans of Action for Immunization in the context of the Multi-year Strategic Plan for Immunization  (2002-2006) as well as additional activities/interventions aiming to meet operational immunization coverage and disease reduction targets, to ensure safe immunization practices and vaccine wastage reduction

Participates into field assessments of basic strategies and activities of the Multi-year Plan such as safe immunization practices, wastage reduction, cold chain effectiveness, adequacy of recording and reporting of VPDs, immunization coverage and AEFI.

Discusses financing of the BiH EPI and mobilizes resources for important needs not met.

Discusses feasibility of supplementary vaccination during epidemic upsurges of VPDs and mobilizes resources for implementation of outbreak control measures.

Participate in monitoring vaccines distribution and spending   and utilization/ maintenance of cold chain equipment.

- Three major strategies to enhance ICC’s role and functions in the next 12 months

- Nominate a focal point with the following TORs:

- Ensure the flow of information between ICC members

-      Organize meetings on a quarterly basis and on request if felt  needed

-      Ensure the preparation of meetings including documentation, agenda etc.

Involving new partners through advocacy for immunization

Involving all partners in the development of plans and monitoring implementation of activites and       ensuring transparency of partners' (including MOHs) support to immunization

- Functional relationships of the ICC with other institutions in health sector :

ICC is set up under the auspices of the Ministries of Health in Bosnia and Herzegovina, namely the Ministry of Health of the Federation of Bosnia and Herzegovina and the Ministry of Health and Social Welfare of the Republika Srpska. The ICC should serve the following purposes: co-ordination of activities in the area of the national immunization programme (NIP) design and implementation; to provide comprehensive institutional support for the NIP; to review and assess immunization policy and activities; to provide a channel for the co-ordinated and effective international assistance in this field.

The ICC has a broad membership base.  It comprise of representatives of the institutions in country and international agencies (please see the list above).

Governments, Ministry of Foreign Affairs

Federal MoH, RS MoH, 				UNDP,

District MoH				UNICEF, WHO,

Epi Managers			World Bank, USAID, others

Medical Universities

State-level EPI management committee

Central PHIs

-Gastroenterology		Research 	Red Cross	NGOs

Cantonal/regional PHIs

- Oncology			institutes

- Tuberculosis

- Paediatrics

Vaccine providers

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Timely HepB3 coverage (according the operational targets set by the Multi-year Plan: 2002-90%, 2004-95%, 2005-98%, 2006-98%) country-wide.

- Drop-out rates ([HepB1-HepB3/HepB1] x100)  not bigger than 5% (2002) and 3% thereafter at both country and regional/cantonal level

- Staff training coverage on immunization safety

Attached are the supporting documents :

| - ICC’s workplan of next 12 months | Document number: under development |
| --- | --- |
| - Terms of reference of the ICC | Document number: 3 |
| - Minutes of the three most recent ICC meetings or of any other any other meetings in which partners participated that concerned improving and expanding the national immunization programme | Document number: 4 |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal. (Guidelines on Country Proposal # 4.2.)

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Multi-index Based Cluster Surveys | UNICEF | 1999&2000 |
| Assessment of BiH Expanded Programme on Immunization | UNICEF, WHO | 2000 |

- The three major strengths identified in the assessments :

- Good collaboration with UNICEF and WHO in ensuring regular supply of safe and quality vaccines, up-dating of the cold-chain system and training on important aspects of the EPI (reporting coverage, AEFP surveillance etc).

- Regular immunization services restored and reported immunization coverage with EPI antigens increased to the pre-war level.

- Public Health Service well organised and involved in planning, analysis of immunization coverage and VPDs surveillance data and collaboration with the PHIs at the respective levels.

- The three major problems identified in the assessments :

(1) No long-term plans for immunization in either entities. Annual decrees of the two MOHs on "Obligatory Immunization of the Population against Infectious Diseases" considered equal to annual plans but in reality dealing with major legislative issues only (e.g. immunization schedule, list of contraindication).

(2) Primary immunization coverage rates reported by Entities and cantons/regions

are calculated for children up to 2 years of age and are often artificially boosted through inclusion of "not-planned" children (older ones, IDPs) in the nominator, whilst the denominator remains according to the "plan".

(3) Lack of State Policy on Safe Immunization Practices

- The three major recommendations in the assessments :

(1) A State-level Inter-entity EPI Management Unit to be established, responsible for setting common policies, guidelines and schedules for immunization services in all parts of BiH.

(2) Coverage age-specific targets for all EPI antigens to be established I accordance with population estimates for each area. A monthly reporting system for immunization coverage to be introduced at all vaccination sites, and at cantonal/regional and entity level.

(3) Clear and precise policies to be developed to integrate new knowledge and technologies on: Monitoring vaccine potency; Using VVMs; Use of open vials in subsequent immunization sessions; Use of A-D syringes for immunization injections, and Use of safety boxes for waste disposal These practices to be

applied to standardise immunization practices throughout the country.

- Attached is a  complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number 5 |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 6 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Title of the assessment | Month/Year |
| --- | --- |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the Multi-year immunization plan or adjusted the health sector plan. (Guidelines on Country Proposal # 4.3)

| - Attached is a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number: 7 |
| --- | --- |

| #### Table 3 : Vaccination schedule with traditional and new vaccines (add/correct/fill in as appropriate) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AGE | Visit | Traditional antigens |  |  |  | New vaccines |  |  |
| Birth | 1 | BCG |  |  |  | Hep B |  |  |
| 2nd months | 2 |  |  |  |  | Hep B |  |  |
| 3rd months | 3 |  | DPT | OPV |  |  |  |  |
| 4th months | 4 |  | DPT | OPV |  |  |  |  |
| 5th months | 5 |  | DPT | OPV |  | Hep B |  |  |
| 2nd year | 6 |  | DPT | OPV | MMR |  |  |  |
| 4th year | 7 |  | DPT | OPV |  |  |  |  |
| 7th year |  |  | DT | OPV | MMR |  |  |  |
| 14th year |  |  | Td |  |  |  |  |  |
| 18th year |  |  | TT |  |  |  |  |  |

Table 4.1 : Baseline and annual targets

|  | Baseline |  | Targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1999 |  |  | 2001 | 2002 |  | 2003 | 2004 | 2005 | 2006 |  |
| # of births | 42759 |  |  | 37254 | 39896 |  | 42601 | 45656 | 48986 | 52626 |  |
| # of infants’ deaths | 455 |  |  | 395 | 424 |  | 453 | 486 | 523 | 562 |  |
| Surviving infants | 41857 |  |  | 36859 | 39473 |  | 42148 | 45169 | 48464 | 52064 |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 6.6 % |  |  | 3% | 3% |  | 2% | 1% | 1% | 1% |  |
| Children vaccinated with DTP3 * | 37253 |  |  | 33173 | 37499 |  | 40040 | 43362 | 46525 | 49981 |  |
| Children vaccinated with HB-vaccine (insert new vaccine other than yellow fever) | NA |  |  | 33173 | 37499 |  | 40040 | 43362 | 47494 | 51022 |  |
| Population data Since the beginning of the war, birth rate, fertility rate are decreasing. In general, the total population of Bosnia & Herzegovina is decreasing. However, as consequence of the peace agreement and the political stability, it is expected that the trends will change and the number of birth will increase in the coming years. Source : Agency for Statistics of Bosnia & Herzegovina, Statistical Bulletin 2, 2000 Federal office for statistics, Sarajevo, Republika Srpska Institute for Statistics, Banja Luka Brcko DHES |  |  |  |  |  |  |  |  |  |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

(Please find enclosed  the Multi-year Strategic Plan for Immunization - doc.no…)

- Ensure regular provision of quality vaccines and supplies - Ongoing.

- Decide on the most appropriate methodology for estimating eligible population for immunization (State-level Management Committee) -  2001

- Review List of Contraindications to Immunization - April 2001

- Emphasize simultaneous use of EPI antigens through Annual Decree on Obligatory Immunization-April 2001

- Issue and supply vaccine providers with the UNICEF recording forms and Immunization cards and consider space for vaccines lot no and vaccine provider signature - 2002

- Set >95% immunization coverage time-, geo-administrative- and communities-specific targets (State-level Management Committee) - 2001

- Aggregate age-specific coverage data at State, Entity, District, and Cantonal/Regional level as one of the tasks of the State-level Management Committee - Ongoing, starting from 2001

- Aggregating annual age-specific coverage data at Entity, Cantonal/Regional, and municipality level to be devolved to the Central PHIs, Cantonal/Regional PHIs and vaccine providers - Ongoing, starting from  - Ongoing, starting from 2001

- Introduce a monthly immunization reporting system from the bottom-up, starting at vaccination sites, up to cantonal/regional and Entity/District level - April 2001

- Introduce performance indicators of reporting immunization coverage (timeliness and completeness) at cantonal/regional and Entity/District level - 2001

- Provide capacity building through training in calculating immunization coverage, recording, and reporting of immunization - yearly, starting from October 2001

- Establish mechanism of collaboration between Entities/District to certify immunization status of migrant children - 2001

- Summary of the major action points and timeframe for reduction of vaccines wastage rate :

1). Development and introduction of a vaccine wastage reporting system (April 2001)

- Introduction at all vaccine storage units of a vaccine stock record book with indication of vaccine movements, provenance and destination, batch number and expiry dates, quantity in stock;

- Regular (at least monthly) physical check of vaccine quantity and expiry date;

- Introduction at vaccine provider level of the newly developed vaccine consumption monitoring form, to be filled monthly, indicating the number of doses used, number of children receiving a dose of vaccine and wastage rate and wastage factor. The calculation of wastage rates for each vaccine will sensitized the health personnel on vaccine consumption;

- Monthly compilation of vaccine wastage rates by municipalities, canton/region; quarterly compilation by FPHI/RPHI and DHES.

2). Ensuring safe vaccine storage and handling by training (Sept. 2001 and yearly) and supplying cold chain equipment and temperature monitoring devices (April 2001 and as needed)

2.1. Safe vaccine storage

- Conduct a cold chain inventory, with specification of vaccine storage capacity (February 2001 and yearly);

- Organize regular maintenance and replacement of cold chain equipment (on-going);

- Supply regularly and adequately temperature monitoring devices, including thermometers and stop watch indicator (March 2001 and regularly);

- Train health personnel on temperature monitoring and vaccine storage and conservation (September 2001).

2.2. Vaccine handling (training September 2001 and yearly, supervision on-going)

- Emphasize the use of Vaccine Vial Monitor and visual check

- Implementation of the WHO Multi-dose vial policy and re-enforcement through training and supervision activities

- Ensure safe vaccine handling during immunization session (use of frozen ice pack or foam)

3.) Vaccine presentation

- introduction of mix vials (2002) i.e. HepB vaccine in single dose vial for immunization at birth; BCG in 10 doses vials instead of 20.

- promotion of VVM-equipped vaccines

- consider introduction of combined DPT-HepB vaccine (2005)

Table 4.2 : Estimate of annual DTP wastage rates

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP wastage rate | na | 33% | 33% | 25% | 25% | 20% | 20% |

No data is available on wastage rates for the period from 1999 to 2001 but it is expected to be high. The absence of vaccine monitoring in BiH is a great concern for the Federal/Republic Public Health Institute and Brcko District. A monitoring system will be implemented in March 2001. Due to the supposed high wastage rate, a 33% to 20% wastage rate for the next years seems realistic.

- Summary of the safe immunization plan (Guidelines on Country Proposal # 3.):

Three strategies will be used for the implementation of the Safe Immunization plan :

- Development and dissemination of a policy on Safe Immunization Practices (SIP)

- Training of health personnel (vaccine providers, pediatrician and epidemiologists) on SIP and mid-level EPI managers on Immunization Services.

- Regular and adequate supply of safe vaccine and injection material, cold chain equipment and temperature monitoring devices.

The Safe immunization plan is composed in three components :

1). Procurement and delivery of safe vaccines

- procurement of vaccines from pre-qualified manufacturers;

- sufficient vaccine storage capacity at all level, general inventory on going, maintenance and replacement of cold chain equipment

- adequate temperature monitoring , supply of proper thermometers, freeze watch indicators

- training of health staff on cold chain management and vaccine storage and handling

2).Ensuring safe vaccine injections

- implementation of use of Auto-Disable (AD) syringes for all vaccine injections,

- supply of AD syringes and Safe Disposal Boxes (SDB) for collection of sharps

- introduction of single dose or 10 dose vials to reduced risk of contamination of vaccine,

- introduction use of combined vaccines to reduce number of injection,

- training of health staff on vaccine administration (use of AD syringes, SDB, vaccine dilution and administration)

3). Ensuring a safe waste disposal

- Instruct municipalities to organize collect and destruction of waste disposal

- Generalize incineration of waste in municipalities incinerator

- Conduct studies for alternative waste destruction where no incinerators are available and in the mean time, promote use of pit or drum incinerator in the health facility or in the municipality or use of protected land-field disposal.

Safe immunization practices will be monitored by :

1). Reinforcing the surveillance system on Adverse Events Following Immunization (AEFI) by developing

adapted reporting form and procedure, instructing clinician and epidemiologists on AEFI surveillance and reporting, analyzing data on AEFI and developing quick investigation response.

2). Conducting monthly supervision to vaccine providers and vaccine keepers.

| Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 7 |
| --- | --- |

- Constraints and planning for Polio Eradication Initiative (Guidelines on Country Proposal # 2.):

AFP surveillance is not yet sufficiently sensitive to confirm absence of circulating wild virus, however, and reported AFP rates were 0.9 per 100,000 children under 15 years in 1999 and 0.3 per 100,000 in 2000.

At present, a documentation set is being prepared by the Ministries of Health for the WHO certification of BiH as a polio free country.

# New and under-used vaccines

Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines (Guidelines on Country Proposal # 4.4.).

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc…in relation to the current experience with new and under-used vaccines :

Experience in the Federation BiH.

Temperature monitoring is well known by staff.  The storage capacity is largely sufficient and the quality of cold chain is adequate.  The implementation of the multi-year plan will address monitoring of wastage and safety of injections.  To ensure the potency of Hep B vaccines, freeze watch indicators will be introduced to monitor temperature during storage and transport.

As Hep B vaccination was performed only for older children, the new schedule will be included in training manuals as well as in informational material to be largely diffused.

- Required number of doses and presentations of requested, first preference, new and under-used vaccines

- (For each one of the requested, first preference new and under-used vaccine, please use provided formulas; see guidelines # 5.2)

Table 5.1: Estimated number of doses  of  Hep B vaccine (specify for one presentation only) :10-dose vials

|  |  | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) | 39,473 | 42,148 | 45,169 | 48,464 | 52,064 |
| B | Number of doses per vaccinated child |  | 2 | 2 | 2 | 2 |
| C | Estimated wastage rate in percentage | 33% | 25% | 25% | 20% | 20% |
| D | Wastage factor [ = 100 / (100-C) ] | 1,5 | 1,33 | 1,33 | 1,25 | 1,25 |
| E | Buffer stock factor for vaccines | 1.25 | 1 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] | 148,124 | 112,367 | 120,421 | 121,160 | 130,160 |
| G | Percentage of vaccines requested from the Fund (%) | 100% | 100% | 100% | 100% | 100% |
| H | Number of doses requested from the Fund [ = F x G / 100 ] | 148,024 | 112,367 | 120,421 | 121,160 | 130,160 |
| I | Number of doses per vial | 10 | 10 | 10 | 10 | 10 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] | 103,913 | 88,764 | 95,126 | 102,065 | 109,647 |
| L | Reconstitution syringes [= H / I ] | NA | NA | NA | NA | NA |
| M | Total number of syringes requested from the Fund [ = J + L ] | 103,913 | 88,764 | 95,126 | 102,065 | 109,647 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] | 1,040 | 888 | 952 | 1,021 | 1,097 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for Hep B and Hib differ from DTP3, explanation of the difference should be provided.

Table 5.2 : Estimated number of doses of  …….. vaccine (specify for the other presentation only if any other presentation of the same vaccine is required) :

|  |  | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) immunization | 39,473 | 42,148 | 45,169 | 48,464 | 52,064 |
| B | Number of doses per vaccinated child | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate in percentage | 5 | 5 | 5 | 5 | 5 |
| D | Wastage factor [ = 100 / (100-C) ] | 1,053 | 1,053 | 1,053 | 1,053 | 1,053 |
| E | Buffer stock factor for vaccines | 1,25 | 1 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] | 51,956 | 44,382 | 47,536 | 51,033 | 54,823 |
| G | Percentage of vaccines requested from the Fund (%) | 100% | 100% | 100% | 100% | 100% |
| H | Number of doses requested from the Fund [ = F x G / 100 ] | 51,956 | 44,382 | 47,536 | 51,033 | 54,823 |
| I | Number of doses per vial | 1 | 1 | 1 | 1 | 1 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] | 51,956 | 44,382 | 47,563 | 51,033 | 54,823 |
| L | Reconstitution syringes [= H / I ] | NA | NA | NA | NA | NA |
| M | Total number of syringes requested from the Fund [ = J + L ] | 51,956 | 44,382 | 47,563 | 51,033 | 54,823 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] | 520 | 444 | 476 | 511 | 549 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for Hep B and Hib differ from DTP3, explanation of the difference should be provided.

records; B =  the number of DTP vaccinations

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in Multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

Only for lyophilized vaccines : Yellow Fever and DTP-HepB-Hib

(Add any other table 5.3, 5.4…as necessary to calculate required doses of different vaccines in different presentations)

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- Allocating existing equipment actually stored and identify funds for completing the replacement, expansion and maintenance

A cold chain inventory with specification of vaccine storage capacity was conducted in February 2001. Approximately 50% of the cold chain equipment were supplied by UNICEF in 1999-2000 and were in good condition. Following an yearly inventory, cold chain equipment will be supplied to replace obsolete equipment and reinforce storage capacity in maternities and canton/region vaccine storage points, to meet the needs of storing single dose vials. Adequate temperature monitoring devices will be supplied as an urgent matter to all vaccine storage units and regular supply will be organized.

A regular maintenance system will be implemented at region/canton level; MOHs will identify donors for funding of cold chain maintenance.

- Staff training

- Training of vaccine providers on safe immunization practices including vaccine storage and handling, emphasizing hepatitis B vaccine, on advantages and proper using of AD syringes and on waste disposal.

- Training of mid- and central level EPI coordinators on monitoring and supervision of logistic issues

(3) Cold Chain/vaccine storage capacity

Upgrading of cold chain

(4) Vaccine wastage

Vaccine wastage has not been monitored but it is expected to be high. A vaccine wastage monitoring system will be implement in the first quarter of 2001. Vaccine consumption and wastage rate will be calculated monthly by vaccine providers. Cantons/regions will compile monthly data and Entities PHI will do it quarterly. 
Vaccine wastage reduction will be emphasized by :

- Introducing mix of vial presentations e.g. single dose vials of HepB for maternities and remote health facilities; replacement of BCG 20 doses vials with 10 dose vials.

- Upgrading cold chain management, temperature monitoring and vaccine handling

- Promotion introduction of VVM equipped vials

- Implementing policy and guideline for use of opened multi-dose vaccine vials

- Considering introduction of combined vaccines when available (DTP+HepB; DTP+HepB+Hib)

(5) Drop out rate

- Mobilizing and sensitizing the population and health care workers

- Supplying regularly and adequately Hepatitis B vaccine

- Reviewing and disseminating the list of contra-indications

- Preparing introduction of combined vaccines

- Required number of doses and presentations of requested, second preference, new and under-used vaccines (please use provided formulas) SeeTables 5.1 and 5.2 above

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |
| B | Number of doses per vaccinated child |  |  |  |  |  |
| C | Estimated wastage rate in percentage |  |  |  |  |  |
| D | Wastage factor [ = 100 / (100-C) ] |  |  |  |  |  |
| E | Buffer stock factor for vaccines |  |  |  |  |  |
| F | Total vaccine doses needed [= A x B x D x E] |  |  |  |  |  |
| G | Percentage of vaccines requested from the Fund (%) |  |  |  |  |  |
| H | Number of doses requested from the Fund [ = F x G / 100 ] |  |  |  |  |  |
| I | Number of doses per vial |  |  |  |  |  |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] |  |  |  |  |  |
| L | Reconstitution syringes [= H / I ] |  |  |  |  |  |
| M | Total number of syringes requested from the Fund [ = J + L ] |  |  |  |  |  |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] |  |  |  |  |  |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for Hep B and Hib differ from DTP3, explanation of the difference should be provided.

(Add any other table to the above format to calculate requested, second preference, doses of different vaccines in different presentations)

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number 7 (pages 33 – 36) |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, (Guidelines on Country Proposal # 4.3, 4.4, 5.) and that will be converted in a comprehensive «Resource Mobilisation Plan» by the time of the mid-term Review (Guidelines on Country Proposal # 6.1.):

Bosnia and Herzegovina is a country in the post-war period. The World Bank estimates total damage inflicted upon the country by the war activities at 100 billion USD. The level of economic activities in 2000, measured by GDP, is still below 50% of that archived in 1990.

Furthermore, the economic progress is hindered by the unstable political situation in the country. For example, it took five month for local political parties to implement the November 2000 election results. Nationalistic right wing forces appears not to be defeated, despite massive international efforts, as proved by recent attempted declaration of “self-rule” in Croat majority areas. Therefore, stability of the country, by most accounts, still needs to be safeguarded by the international community both in political sense, by the Office of High Representative, OSCE and other international organizations as well as in military terms, by the NATO-led Stabilisation Forces.

In such environment it appears to be difficult to take for granted future Government’s capabilities to ensure significant participation and steady financing of the immunization programme. However, a nation-wide advocacy and communications plan will be developed with the cooperation and consensus of all stakeholders. This process will involve government, health professionals, local and international agencies, and NGOs working in BiH.

| - Tables of expenditure for 1999 and resource needs detailing the sources of funds are attached in Annex 1- page 25 of this document | Document number see table at the page 25 and document 8 |
| --- | --- |

- List of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative): (the relevant documents are attached)

| Title | Partners |  |
| --- | --- | --- |
|  |  | Document number …… |
|  |  | Document number …… |
|  |  | Document number …… |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

| - Summary of support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached : | Document number Poverty Reduction Strategy in preparation |
| --- | --- |

# Summary of requests to GAVI/GFCV

With reference to all points presented above, the Government of Bosnia and Herzegovina

- being eligible for support from the Global Alliance for Vaccines and Immunization (GAVI) and the Global Funds for Children’s Vaccines (The Fund),

- considering that its DTP3 coverage for 1999 was ………%  corresponding to ……… number of children vaccinated with DTP3.

hereby requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government does hereby apply to receive support from the Fund :

YES

NO

- IMMUNIZATION SERVICES SUB-ACCOUNT (tick only one)

To fund the immunization services in year 2001 according to the number of additional children that are targeted to be immunised with DTP3 as presented in table 4.1, namely ………………  ( number of children ).

- (Only for countries seeking support from the Immunization Services sub-account)

- Transfer of funds from the immunization services sub-account will be by (tick only one):

| Government |  | A Partner agency (specify name) |  | An independent third party |  |
| --- | --- | --- | --- | --- | --- |

- Operational mechanism in place for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds (Guidelines on Country Proposal # 5.1.):

YESv

NO

- NEW AND UNDER-USED VACCINES SUB-ACCOUNT (tick only one)

To supply the following vaccines :  (fill in only what is being requested from the Fund in line with tables 5.1, 5.2…)

| Table 6 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Presentation* | Starting month and year | Number of doses requested for first calendar year | Vaccines will also be requested for following years as described in tables 5.1, 5.2… |
| Hep B | Monovalent 10 dose vial | January 2002 | 148,024 |  |
|  | Monovalent 1 dose vial | January 2002 | 51956 |  |
| Hib |  |  |  |  |
| yellow fever |  |  |  |  |

* Insert types of presentation requested:	(1) 	Monovalent or combination

(2)	Number of doses per vial

- (Only for countries seeking support from New and Under-used Vaccines sub-account)

- Vaccines will be procured (tick only one) :

By UNICEF                            By GOVERNMENT

- (If vaccines is procured by the Government)

Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system (Guidelines on Country Proposal # 5.2.):

# Additional comments and recommendations from the ICC

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD, 000)

Table 1  Expenditure in 1999 from different sources

| Ref. # | Category / Line item | Federation of BiH | Republika Srpska | Private sector | UNICEF | WHO | Donor n.. 2 | Total Expenditure in 1999 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Vaccines, AD syringes… | 419,450 | 45,000 |  | 377,668 |  |  | 842,118 |
| 1.1 | Vaccines | 410,000 | 45,000 |  | 190,702 |  |  | 645,702 |
| 1.2 | Syringes/disposal boxes | 9,450 |  |  | 115,920 |  |  | 123,370 |
| 1.3 | Freight |  |  |  | 71,046 |  |  | 71,046 |
| 2. | Equipment (cold chain, spare parts, sterilization…) | 13,490 |  |  | 45,224 |  |  | 58,714 |
| 2.1 | Equipment | 6,750 |  |  |  |  |  | 6,750 |
| 2.2 | Maintenance | 4,500 |  |  |  |  |  | 4,500 |
| 2.3 | Temperature monitor | 1,340 |  |  |  |  |  | 1,340 |
| 2.4 | Freight | 900 |  |  | 6,460 |  |  | 7,360 |
| 3. | Other item immunization specific | 53,900 |  |  | 162,132 | 5,625 |  | 221,657 |
| 3.1 | Transport, custom | 4,500 |  |  | 19,961 |  |  | 24,461 |
| 3.2 | Training | 27,000 |  |  | 30,439 | 5,625 |  | 63,064 |
| 3.3 | Social mobilization | 13,400 |  |  | 54,000 |  |  | 67,400 |
| 3.4 | Administrative costs | 9,000 |  |  | 57,732 |  |  | 66,732 |
| Total expenditure in 1999 |  | 486,840 | 45,000 |  | 585,024 | 5,625 |  | 1,122,489 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |

Table 2 Estimated budget 2002

| Budget for 2002 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Federation of BiH | Republika Srpska | Private sector | UNICEF | WHO | Donor n.. 2 | Total Expenditure in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  | 473,805 |
| 1.1 | Vaccines |  |  |  |  |  |  | 302,057 |
| 1.2 | Syringes/disposal boxes |  |  |  |  |  |  | 55,023 |
| 1.3 | Freight |  |  |  |  |  |  | 116,725 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  | 13,308 |
| 2.1 | equipment |  |  |  |  |  |  | 6,287 |
| 2.2 | maintenance |  |  |  |  |  |  | 2,960 |
| 2.3 | temperature monitor |  |  |  |  |  |  | 2,337 |
| 2.4 | freight |  |  |  |  |  |  | 1,724 |
| 3. | Other item immunization specific |  |  |  |  |  |  | 189,200 |
| 3.1 | transport, custom |  |  |  |  |  |  | 20,000 |
| 3.2 | training |  |  |  |  |  |  | 77,000 |
| 3.3 | social mobilization |  |  |  |  |  |  | 60,000 |
| 3.4 | administrative costs |  |  |  |  |  |  | 32,200 |
| Total expenditure estimated for 2002 |  |  |  |  |  |  |  | 676,313 |

Please see detailed table below (page 30)

ANNEX  2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 and 2 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organisational chart) | Document number 1 and 2 |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) as they impact immunization services | Document number 1 and 2 |
| - Government policies on private sector participation, as it relates to immunization services. | Document number no policies so far |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number under development |
| - Terms of reference of the ICC | Document number 3 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number 4 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document number 5 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number 6 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 7 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, Multi-year plan, please indicate page and paragraphs) - Safe injections Plan | Document number 7 (pages 33-36) Document number 7 (page 15) |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number see page 25 of this document and document 8 |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Document number…… |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Document number…… |

Decrees on the programme on obligatory immunization 			         Document number 9

| BOSNIA & HERZEGOVINA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Multi year plan 2002 - 2006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Vaccine requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In USD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | BCG | DPT | OPV | MMR | HBv 10 doses | HBv 1 dose | Td | DT | TT | TOTAL |  |  |
| 2002 | vaccine | doses | 109266 | 303608 | 375302 | 121454 | 148024 | 51956 | 104072 | 71694 | 109046 |  | 2002 |  |
|  |  | cost | 10380.27 | 30,360.75 | 27021.71 | 81,009.58 | 99175.91 | 32212.93 | 10927.51 | 3226.23 | 7742.23 | USD | 302,057.12 | vaccine cost |
|  | freight+overexpenditures |  | 3633.09 | 10626.26 | 9457.60 | 28353.35 | 34711.57 | 11274.52 | 3824.63 | 1129.18 | 2709.78 | USD | 105,719.99 | freight+overexp. |
|  | Total |  | 14013.36 | 40987.01 | 36479.31 | 109362.94 | 133887.48 | 43487.45 | 14752.14 | 4355.41 | 10452.01 |  |  |  |
| 2003 | vaccine | doses | 114616 | 280529 | 341768 | 111226 | 112367 | 44382 | 87418 | 61239 | 94504 |  | 2003 |  |
|  |  | cost | 10888.52 | 28,052.85 | 24607.29 | 74,187.73 | 75285.60 | 27516.74 | 9178.90 | 2755.77 | 6709.81 | USD | 259,183.22 | vaccine cost |
|  | freight+overexpenditures |  | 3810.98 | 9818.50 | 8612.55 | 25965.71 | 26349.96 | 9630.86 | 3212.62 | 964.52 | 2348.43 | USD | 90,714.13 | freight+overexp. |
|  | Total |  | 14699.50 | 37871.35 | 33219.84 | 100153.44 | 101635.56 | 37147.60 | 12391.52 | 3720.29 | 9058.24 |  |  |  |
| 2004 | vaccine | doses | 119014 | 293212 | 356924 | 117086 | 120421 | 47563 | 87885 | 63712 | 92937 |  | 2004 |  |
|  |  | cost | 11306.33 | 29,321.20 | 25698.53 | 78,096.49 | 80681.77 | 29489.03 | 9227.89 | 2867.04 | 6598.51 | USD | 273,286.80 | vaccine cost |
|  | freight+overexpenditures |  | 3957.22 | 10262.42 | 8994.49 | 27333.77 | 28238.62 | 10321.16 | 3229.76 | 1003.47 | 2309.48 | USD | 95,650.38 | freight+overexp. |
|  | Total |  | 15263.55 | 39583.62 | 34693.02 | 105430.26 | 108920.39 | 39810.20 | 12457.65 | 3870.51 | 8907.99 |  |  |  |
| 2005 | vaccine | doses | 126438 | 288394 | 344035 | 110409 | 121160 | 51033 | 79671 | 55641 | 86828 |  | 2005 |  |
|  |  | cost | 12011.61 | 28,839.38 | 24770.52 | 73,642.58 | 81177.20 | 31640.21 | 8365.48 | 2503.86 | 6164.75 | USD | 269,115.58 | vaccine cost |
|  | freight+overexpenditures |  | 4204.06 | 10093.78 | 8669.68 | 25774.90 | 28412.02 | 11074.07 | 2927.92 | 876.35 | 2157.66 | USD | 94,190.45 | freight+overexp. |
|  | Total |  | 16215.67 | 38933.16 | 33440.20 | 99417.48 | 109589.22 | 42714.28 | 11293.40 | 3380.21 | 8322.42 |  |  |  |
| 2006 | vaccine | doses | 132824 | 309661 | 361983 | 112901 | 130160 | 54823 | 76875 | 52321 | 86726 |  | 2006 |  |
|  |  | cost | 12618.28 | 30,966.13 | 26062.74 | 75,305.13 | 87207.20 | 33990.50 | 8071.88 | 2354.46 | 6157.56 | USD | 282,733.88 | vaccine cost |
|  | freight+overexpenditures |  | 4416.40 | 10838.14 | 9121.96 | 26356.80 | 30522.52 | 11896.68 | 2825.16 | 824.06 | 2155.15 | USD | 98,956.86 | freight+overexp. |
|  | Total |  | 17034.68 | 41804.27 | 35184.70 | 101661.93 | 117729.72 | 45887.18 | 10897.03 | 3178.52 | 8312.71 |  |  |  |
| NOTE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Wastage rate used : |  | DPT, OPV,DT, Td, TT, MMR, Hepatitis B vaccine (10 dose vial) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2001-2002 : Wastage = 33 % (wastage factor = 1,5) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2003-2004 : Wastage = 25 % (wastage factor = 1,33) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2005-2006 : wastage = 20 % (wastage factor = 1,25) |  |  |  |  |  |  |  |  |  |  |  |
|  | A reserve stock of 20% for eachHepB vaccine will be procured for the year 2002. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | The target population is 100% of the age cohort, considering the surviving infants for birh cohort. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Vaccine prices are according to UNICEF procurement. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Starting 2002; 10 doses vials will be introduce for BCG vaccine ; mix presentation of single dose and 10 dose vials for hepatitis B vaccine. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Freight and overexpenditures represent 35% of the cost of the vaccines |  |  |  |  |  |  |  |  |  |  |  |  |  |

Children less than 12 months of age

Formula to calculate DTP vaccine Wastage Rate (in percentage): [ ( A – B ) / A ] x 100.                                                               Whereby : A = The number of DTP doses distributed for use according to the supply  records; B =  the number of DTP vaccinations

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The preferred mechanism is payment directly to a Government account (Guidelines on Country Proposal # 5.1)

Please submit hard copy documents with an identical electronic copy whenever possible