The Government of COTE D’IVOIRE

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.ch or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Signatures of the Government

The Government of ……COTE D’IVOIRE……………………………………….. commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:	……………………………………… Prof. Janine Saracino-Tagliante

Title:	Minister of Health, Cote d’Ivoire

Date:	30/6/2000

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |
| European Union |  |  |
| Worldbank |  |  |
| KFW/GTZ |  |  |
| Canadian Development Cooperation |  |  |
| French Development Cooperation |  |  |
| WHO |  |  |
| UNICEF |  |  |
| AMP |  |  |

Signed this day of : _____________/2000

In case the GAVI Secretariat have queries on this submission, please contact :

Name :  Dr SANGARE Sekou Victor	Title/Address : Directeur Executif du PEV

INSP,  BPV 47, Abidjan 01

Tel.No. :  (225) 20 22 05 33			Cell : (225) 05 04 75 14

Fax No. :  (225) 20 22 05 40

E-mail : 	depevci@africaonline.co.ci

- Immunization-related fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 16 302 025 | GNP per capita | 700 $US |
| Infants 0-11 months | 643 930 | Infant mortality rate | 112/1000 |
| Percentage of GDP allocated to Health | 1,3 % | Percentage of Government expenditure for Health Care | 8.7 % |

| Health system development status |  |
| --- | --- |
| Please find attached background documentation in French on: |  |
| - Overall government health policies and strategies Plan National de Developpement Sanitaire Tome 1 et 2 (with summary) | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services summary with original ministerial bylaw including organizational chart | Document number 2 |
| - Status of the ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies and practices on private sector participation, as it relates to immunization | Document number 4 |

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 71 | 77 | 87 |  | Diphtheria | 0 | NA | NA | NA |
| DTP3 | 64 | 60 | 70 | 61 | Pertussis | NA | NA | NA | NA |
| OPV3 | 64 | 60 | 70 | 61 | Polio | 13 | 9 | NA | NA |
| Measles | 66 | 59 | 63 | 66 | Measles | 12 289 | 4 824 | NA | NA |
| TT2+ Pregnant Women | 49 | 69 | 70 |  | NN Tetanus | 95 | 83 | NA | NA |
| Hib | SO | S0 | SO |  | Hib | NA | NA | NA | NA |
| Yellow Fever | 57 | 50 | 65 |  | Yellow fever | 0 | 1* | NA | NA |
| HepB | S0 | ~ | SO |  | HepB seroprevalence (if available) | 9%** | 9% | NA | NA |

# *   A tourist was the only case of Yellow fever

# ** seroprevalence of Hepatitis B in blooddonors

# Profile of the Inter Agency Coordinating Committee (ICC)

(Various agencies and partners supporting immunization services in the country are coordinated and organized through an inter-agency coordinating mechanism, which is referred to in this document as ICC)

- Name of the ICC :  ‘Groupe Thematique PEV’,

- Date of constitution of the current ICC :   June 2000. The predecessor of the current ICC was the Interagency Coordination Committee for the Polio-eradication, which was functional since October 1996 (see Document 5). In June 2000, the Minister of Health has decided to extend its mandate from solely Polio-eradication to the comprehensive field of EPI and place it directly in her cabinet.

- Organizational structure: subcommittee of the ‘Comite de Suivi de PNDS’, which is located in the Ministry of Health, in the ‘Secretariat Technique Permanent du PNDS’. (see Document 6)

- Frequency of meetings : 4 times per year

- Composition: Since the committee has recently changed its mandate, the composition and the terms of references are not yet fully defined, or adopted. However, the committee is already functional on an unofficial basis, with approval of the Minister of Health.

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Ministry of Health |  |
| Secretary | DE-PEV (National EPI-Services) | Dr S.V. Sangare |
| Members | - INHP - INSP - PSP - IPCI - DIEM - DEPS - DAF - DIPE - DSC - Directeur Regional de la Sante ( 1) - Directeur Departemental de la Sante (1) - Ministere de l’Economie et des Finances - Ministere de l’Interieur et de la Decentralisation - Representatives of the Development Agencies (bi- & multilateral) | Institut National d’Hygiene Publique Institut National de la Sante Publique Pharmacie de la Sante Publique Institut Pasteur de Cote d’Ivoire Direction des Infrastructures, de l’Equipement et de la Maintenance Direction des Etablissement et de Personnel de Sante Direction Administrative et Financiere Direction de l’Information, de la Planification et des Etudes Direction de Sante Communautaire |

- Major functions and responsibilities :

- Defining the Immunization policies and strategies - Assuring sustainability of the EPI services through efficient resource mobilization (internal & external) - Review and endorse the national plans of action with the budgets, and monitoring the EPI-implementation countrywide, advising on corrective actions. - Advising on operational research, other studies and evaluations of the EPI services

- The following diagram shows the ICC functional relationships with other institutions in health sector :

Ministere de la Sante Directeur de Cabinet Secretariat Technique Permanent de PNDS Groupe Thematique PEV Autres groupes

Find attached the following documents:

| - Proposed terms of reference of the ICC ‘Groupe Thematique PEV’ | Document number 7 |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings in which partners participated that concerned improving and expanding the national immunization program | Not available |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Enquete Demographique et de Sante 1994, Document 8 | DHS, Institut Nationale de la Statistique (INS) | Dec. 1995 |
| Enquete National d’Evaluation de la Couverture Vaccinale 1998, Document 9 | Ministere de la Sante Publique, DE-PEV | Oct. 1998 |
| Enquete Demographique et de Sante, Cote d’Ivoire1998/99, Document 10 | DHS, MACRO Int., Ministere de la Planification et de la Programmation du Developpement, INS | May 1999 |
| Case Study on the Costs and Financing of the Immunization Services in Cote d’Ivoire, Document 11 | PHR, USAID, WHO, Gouv. de Cote d’Ivoire | May 2000 |

- The following are the three major problems identified in the assessments :

- In the EDS 1998/99, an significant improvement of the EPI-coverage is noted: - DPT 3 1998/99 61 % compared to DPT 3 1994 51 %) - Fully vaccinated children in 1998/99 51 % compared to 41 % in 1994 However, both surveys state a significant difference between the immunization coverage in urban areas compared to those in rural areas. - Findings from the National Immunization Coverage survey 1998: 9 % of the children are not reached by the routine EPI services, high dropout rate national average 18 % (range 5% - 54%). Concerning services delivery: missed vaccinations-opportunities, in 13 % the Yellow fever is not administered simultaneously with Measles. In Abidjan, 12 % of the children received invalid dosages for DTP 3 and 11 % received invalid dosages of the measles vaccine. - Findings of the Case Study on Costs & Financing: - Financing strategy is heavily dependent on the EU & other donors and is not sustainable over the long term. This dependency might have relaxed the pressure on the efficient use of the resources. - Need for information exists concerning: the disease burden (regular disease surveillance and reporting), an inventory on cold chain equipment and its condition to determine maintenance and replacement needs, cost-effectiveness data on different strategies to improve immunization coverage.

- The following are the three major recommendations in the assessments :

- To address the inequity of the EPI-services between the urban and the rural areas by strengthening the outreach services and mobile strategies - To develop an IEC strategy adapted to the target groups (ex. illiterate women) - To strengthen supervision and in-service training on EPI technical issues and managerial topics - To create sustainable long-term financing for the immunization program, especially for the operational costs, by both increasing central government budget allocations through the operating budget and tapping into other local sources, such as insurance, local government and community contributions. - To develop a national immunization strategic multi-year plan including program objectives maintaining & improving the current coverage rates and introducing new vaccines and other innovative strategies (ex. auto-destruct syringes). The plan should include also: capacity building in critical areas, addressing financing and maintenance issues, planning for operational research on national and district level - To develop a detailed annual EPI-planning on the district levels facilitating monitoring. - To assess the vaccine-procurement process and to improve the vaccine-stock management.

- Find attached a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number 8,9,10 & 11 |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in workplan, implemented, not implemented, in progress…. | Document number 12 |

- The following components or areas of immunization services are yet to be reviewed (or studied). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |
| Burden of Disease assessment Hepatitis B | 2001 | Funded by AMP |
| Entomological & Serologic Surveys for all vaccine-preventable diseases | 2001-2005 | 850,000 over 5 years |
| Burden of Disease assessment Haemophilus influenza | 2002 | 30,000 |
| Detailed cost-assessment on district level | 2003 | n.a. |
| National EPI assessment (WHO) | 2003 | 85.000 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 13 |
| --- | --- |

- As per 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 361,942 |
| Used doses of DTP | 460,000 |

- Estimated annual targets

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Children planned to be vaccinated with DTP3 | 647,686 | 669,060 | 691,139 | 713,947 | 737,507 | 761,845 |
| Doses of DTP planned to be used | 1,833,300 | 1,497,800 | 552,500 | - | - | - |

Note: the phasing-out of the DPT-doses is due to the gradual introduction of the combo-DTP-Hb.

# New and under-used vaccines

Find below a summary of those aspects of the plan, mentioned in section five that refer to introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Pneumopathy | Prise en charge de Pleurisie de l’enfant en reanimation, Abidjan (42 cas) These medicale de S. Konate | 1994 | Haemophilus 10 % |
| Meningitis | Meningite a Haemophilus Influenzae chez l’ enfant a Abidjan, (886 cas de 1990-1994) Bissagnegne et coll. Med. D’ Afrique Noire 1996, 43 (10) | 1996 | Haemophilus 36 % (89% serotype b) Pneumococ 38 % |
| Meningitis | Profile actuelle de meningite purulente de l’enfant au CHU de Yopougon de 1993-1995, (101 cas) These medicale de P.D. N’zue 1998 | 1998 | Haemophilus 24 % |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of monovalent vaccine :

Not Applicable

- Planning for hepB vaccinations : Note: DPT-Hb requested

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 345,602 | 483,797 | 713,947 | 737,507 | 761,845 |
| Total vaccine doses required | 946,400 | 1,905,500 | 2,535,600 | 2,752,900 | 2,864,300 |
| Preferred vial size(s) | 10 D | 10 D | 10 D | 10 D | 10 D |
| Estimated wastage rate | 25 % | 25 % | 25 % | 25 % | 25 % |
| % of vaccines requested from the Fund | 41 % | 71 % | 78 % | 80 % | 81 % |
| AD syringes * | 5,762,100 | 7,201,100 | 6,189,400 | 6,764,600 | 7,008,500 |

* The AD-syringes are requested not only for the DTP-Hb, but for all vaccines except for BCG.

- Planning for Hib vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | - | - | 713,947 | 737,507 | 761,845 |
| Total vaccine doses required | - | - | 2,535,600 | 2,752,900 | 2,864,300 |
| Preferred vial size(s) |  |  | 10 D | 10 D | 10 D |
| Estimated wastage rate |  |  | 25 % | 25 % | 25 % |
| % of vaccines requested from the Fund |  |  | 78 % | 80 % | 81 % |
| AD syringes |  |  | 6,189,400 | 6,764,600 | 7,008,500 |

- Planning for yellow fever vaccinations: not applic., Yellow Fever incorporated in the routine EPI 1983

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

| - Find attached the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number 13 Included in the multi-years plan of action |
| --- | --- |

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each line item and for each year are attached in Annex 1. | Document not available |
| --- | --- |

- Find below a list of financial sustainability strategies and of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative). The information is obtained from the Director of the National EPI services, for detailed information contact him.

(USD ,000)

| Strategy title / Line item | Partner1 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel | Gov. | 5,130,535 |  |  |  |  |  |  |  |
| Vaccines & Supplies | EU budget-aid | 1,869,000 | 1,953,183 | 1,953,183 |  |  |  |  |  |
| Transport | Gov. | 130,800 |  |  |  |  |  |  |  |
| Maintenance/Overhead | Gov. | 100,000 |  |  |  |  |  |  |  |
| Measles control | UNICEF |  | 200,000 |  |  |  |  |  |  |
| Support to GAVI-initiative | UNICEF |  |  | 150,000 |  |  |  |  |  |
| Elimination of Neonatal Tetanus | UNICEF |  |  | 250,000 | 250,000 |  |  |  |  |
| Yellow control | WHO |  |  | 152,050 | 173,370 |  |  |  |  |
| Surveillance, with focus on Polio | WHO | 90,000 | 86,000 | ? |  |  |  |  |  |
| Polio NIDs | WHO /Rotary | 300,000 | 350,000 | ? |  |  |  |  |  |
|  | Japanese Gov. /UNICEF | 1,167,000 | 950,000 |  |  |  |  |  |  |
|  | Rotary Nat |  | 50,000 |  |  |  |  |  |  |
| Cold chain and logistics investments | UNICEF | 37,000 | 11,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 | 35,000 |
|  | JICA | 265,020 |  |  |  |  |  |  |  |
|  | KFW |  | 5,000,000 |  |  |  |  |  |  |

| - We summarize hereunder the support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached. | Document not available |
| --- | --- |

The PNDS is an integrated part of the plan of action in the Fight against Poverty, which was adopted by the Government in 1998. Unfortunately, the implementation of the PNDS is confronted with serious delays, and in the current election year, the focus of the government is more oriented toward the political arena rather to social policies. Due to the political circumstances, the negotiations concerning the debt relief are not pursued as before, but will be resume as soon as the results of the General Elections are known. In these discussions, investments in the EPI-services will be taken into account, since the EPI is a priority program in the plan of action against Poverty as an important preventive program executed by the Ministry of Health, one of the basic social services of Cote d’Ivoire.

# Preferred channel of funds

(Only for countries seeking support from the immunization services sub-account)

- From the immunization services sub-account, funds will be transferred to the country through the following channel or system (tick only one) :

| Directly to the Government |  | Through a partner agency |  | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the following box we describe how the mechanism will operate and how it will address transparency, standards of accounting, long-term sustainability and empowerment of the government.

The details of the fund disbursement mechanisms are not yet finalized. The Government would like to create a separate budget-line for the GAVI-funds on the account of the INHP to integrate the increased expenditures for the EPI-services in the national budget straight from the beginning. It would like to handle the GAVI- funds in a similar way as the financing of the routine vaccines with the budget-assistance of the European Union. However, it would simultaneously welcome an involvement of UNICEF to enhance financial transparency. This issue requires further consultation between the Government, ICC partners, UNICEF Abidjan and UNICEF Headquarters-New York.

# Country concerns

The following are the ICC’s concerns and recommendations while submitting this proposal :

Cote d’Ivoire is currently undergoing a critical period of Government transition, which puts the basic social services in a difficult position to mobilize internal resources. The EPI services, which request substantial financing, are especially in a vulnerable position. In the recent past the EPI-services of Cote d’Ivoire have shown remarkable achievements in improving their performance, increasing the DTP 3 coverage from 41 % in 1995 to 70 % in 1997. This achievement was mainly obtained through an improved supervision and management by the central level, even before the major investments in the cold chain and logistics had taken place. At this point in time it is imperative to sustain the good performance of the EPI-services and to avoid putting the children in Cote d’Ivoire at risk for preventable diseases. Thus, the Government of Cote d’Ivoire takes the opportunity to request the GAVI-funding on the sub-account Immunization services to reinforce capacity of the EPI-service to face the challenge of improving immunization coverage under difficult circumstances. Since the first step in introducing new vaccines in the routine EPI has already been undertaken (introduction of Hepatitis B vaccination in the capital, 20% of total target-group), the Ministry of Health has decided to continue this effort. Therefore, it appeals to GAVI for funding the gradual extension of the Hepatitis immunization nation-wide over the 3 years period. Secondly, the multi-years plan projects an introduction of the Hib-immunization in 2004. The political commitment to universal immunization exists on all levels of the Government, and with the debt-relief foreseen in the near future, it is important to assist the Ministry of Health now to reinforce the EPI-services’ capacity with a financial and technical assistance. The partners in development are strongly supportive to this renewed EPI-initiative and are willing to take part in the planning and implementation, as the active participation in the planning-workshop (June 2000) and the various contributions to this proposal have shown.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Government | Local Government | Private sector AXA | JICA & UNICEF | KFW | USAID/WHO | Total Expenditure in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |
| 1.1 | - Line item Routine Vaccines | 2,222,222 |  |  |  |  |  | 2,222,222 |
| 1.2 | - Line item OPV |  |  |  | 750,376 |  |  | 750,376 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |
| 2.1 | - Line item Cold Chain & logistics |  |  |  |  | 5,500,000 |  | 5,500,000 |
| 2.2 | - Line item n… |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |
| 3.1 | - Line item Polio operational cost | 281,749 |  | 32,593 | 78,518 |  | 311,112 | 703,972 |
| 3.2 | - Line item n… |  |  |  |  |  |  |  |
| Total expenditure in 1999 |  |  |  |  |  |  |  |  |

Table 2

| Budget for 1999 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USD | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | UNICEF | WHO | Others | Donor n.. 2 |  |  |
| 0. | Operational Costs (Salaries EPI central level, maintenance of duty-vehicles etc.) | 50,4000 |  |  |  |  |  |  | 50,400 |  |
| 1. | Vaccines, AD syringes… (EU) |  |  |  |  |  |  |  |  |  |
| 1.1 | Line item Routine Vaccines | 2,222,222 |  |  |  |  |  |  |  |  |
| 1.2 | Line item OPV |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item n… |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Social Mobilization/IEC | 99,260 |  |  | 18,000 |  | 12,000 |  | 129,000 |  |
| 3.2 | - Training | 26,000 |  |  | 7,400 | 18,000 |  |  | 50,400 |  |
| 3.3 | - Studies & Evaluation | 59,000 |  |  |  |  |  |  | 59,000 |  |
| 3.4 | - Monitoring & Surveillance | 296,300 |  |  | 29,600 | 220,000 |  |  | 561,000 |  |
| 3.4 | - Logistics | 49,500 |  |  |  |  |  |  | 49,500 |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number 2 |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies on private sector participation, as it relates to Immunization. | Document number 4 |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC for Polio eradication - Terms of reference of the Secretariat Technique Permanent du PNDS - Terms of reference of the ICC –Groupe Thematique sur le PEV- | Document number 5 Document number 6 Document number 7 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Not available |
| Immunization Services Assessment |  |
| - Enquete Demographique et de Sante, Cote d’Ivoire 1994 - Enquete National d’Evaluation de la Couverture Vaccinale 1998 - Enquete Demographique et de Sante, Cote d’Ivoire1998/99 - Case Study on the Costs and Financing of the Immunization Services in Cote d’Ivoire | Document number 8 Document number 9 Document number 10 Document number 11 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number 12 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 13 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | Document number 13 Included in Multi-year plan |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number…… |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Not available |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Not available |

# MINISTRY OF HEALTH

# CÔTE D’IVOIRE

CLARIFICATIONS

ON THE CÔTE D’IVOIRE APPLICATION

TO GAVI

# August 2000

# Abidjan

# Table of Content

I.		Côte d’Ivoire Specific Information  				P 3

I. A.	Concerning the decision to support the Immunization Services

P  3

- DTP 3 coverage

- Coverage Targets

I.B.	Concerning the proposal for the support for new and underused vaccines								P  4

- Combination DTP-Hep B Vaccines versus Hep B Monovalent Vaccines

- Provision of the combination vaccines

## II.		Additional Information						P  6

- Verification of the AD syringe requirements

- The nationally adopted immunization schedules

# Estimated requirements of the combined DTP-Hep B vaccine

# Additional requirements of the cold chain equipment

# Burden of disease assessment on Hepatitis B

III.		Critical Issues							P  7

- Resource mobilization

- Polio eradication

- Injection Safety Strategy

- Advocacy and IEC

## IV.	Policy Issues raised during the Proposal Review process	P  10

- Buffer stock and wastage rates

- AD syringes and safety boxes

- Replacement funding

- DTP Drop-out rates

# Clarifications on the Côte d’Ivoire application

# to GAVI

I.		Côte d’Ivoire Specific Information

I. A.	Concerning the decision to support the Immunization Services

1.	 DTP 3 coverage

In the proposal of Côte d’Ivoire to GAVI, we have used the population data extracted from the census of November 1998. This census was financed by the Government, the World Bank, the French Development cooperation, UNFPA and UNICEF. However, on verifying the figures, we have come to the total of 454,073 children of the age 0-11months on a total population of 15,366,672 in November 1998. Based on the above and a 3,3 % annual population growth, the number of beneficiaries in 2001 will be 484,536 children of 0-11 months of age. For the details see annexed table and Annex 2 : Résultats définitifs du Recensement Général de la Population et de l’Habitat RGPH 98.

- Coverage Targets

After thoroughly reviewing the EPI-targets, Côte d’Ivoire will adhere to the targets previously submitted to GAVI. Thus, the objectives for the annual in DTP 3 (Hep B) coverage-increase remain 73%, 75%, 80%, 80% and 80% for the period between 2001-2005.

In the HIPC negotiations, the target of at least a 70% EPI coverage rate is mandatory.

I.B.	Concerning the proposal for the support for new and underused vaccines

- Combination DTP-Hep B Vaccines versus Hep B Monovalent Vaccines

In the case of Côte d’Ivoire, we are dealing with the extension of combined DTP-Hep B vaccination and not with an introduction of a new vaccine. The country is vaccinating already 20 % of its target population since March 1999 in Abidjan. The following tables show the achievements in the combined DTP-Hep B vaccination:

Comparison of the DTP vaccination in 1998 and DTP-Hep B vaccination in 1999 in Abidjan

| Indicators | #### 1998 | 1999 |
| --- | --- | --- |
| Antigen | ##### DTP only | First 2 months DTP Last 10 months DTP-Hep B |
| No. of doses 1 administered | 76,257 | 91,572 |
| No. of doses 3 administered | 68,568 | 78,574 |
| Coverage of dose 1 | 77 % | 89 % |
| Coverage of dose 3 | 65 % | 77 % |

After the introduction of the Hepatitis B vaccination in Abidjan, an increased demand for the vaccination is noted as the following table shows. It reflects the interest of the parents for this vaccination.

| Month | 1998 | 1999 | 2000 |
| --- | --- | --- | --- |
| Antigen | DTP | DTP & DTP-Hep B | DTP-Hep B only |
| March | 55 % | 53 % | 62 % |
| June | 55 % | 59 % |  |
| December | 65 % | 77 % |  |

The nationally adopted strategy is to use the combined DTP-Hep B preparation and not the monovalent Hepatitis vaccination. The reasons are the following:

- The difficulties in vaccine logistics management due to changing to the monovalent vaccine;

- The introduction of new guidelines for immunizing the children against hepatitis, when the health personnel is already used to the administration of the combined DTP-Hep B vaccination;

- The need for increased storage place when the monovalent vaccine will be used.

- The increased number of simultaneously administered injections to the target population, which will result in inadequate coverage. The example of simultaneous EPI vaccination in Côte d’Ivoire is the measles vaccination simultaneously with the Yellow Fever vaccination. It shows that over the years the Yellow Fever coverage is always less then the Measles coverage.

- The increased number of injections will in counterproductive to the injection safety.

- A reduced of wastage rates: the wastage rate decreased from 25 % to 15 % in one year since introducing the combined DTP-Hep B vaccination in Abidjan, which represents 20 % of the total EPI target population.

The country would not like to consider the option of using the monovalent vaccine for the EPI. In conclusion, Côte d’Ivoire would request to be given the highest priority for receiving the combination vaccine DTP-Hep B as the request to GAVI concerns an extension of EPI services offered already.

2.	Provision of the combination vaccines

If due to constraints in the vaccine production there would be insufficient supplies of the combined DTP-Hep B vaccines, Côte d’Ivoire could consider reducing the quantities of the combined vaccine, requested in its application to GAVI. This adjustment would delay the extension to a national coverage of the children 0-10 months and would have its repercussion on the objectives as described in the Strategic Plan 2001-2005.

II.		Additional Information

### Verification of the AD syringe requirements.

### The request to GAVI for the AD syringes is to complement the national government allocation for injection materials. This allocation is insufficient to bear the increased cost of needed to convert to the national wide use of AD syringes for the relevant antigens. The Government deems this request reasonable as it will continue to fund 20% of the DTP-Hep B vaccine requirements.

2.	The nationally adopted immunization schedule, including DTP- Hepatitis B vaccination is as follows:

| ##### Vaccination Schedule | Antigen |
| --- | --- |
| Birth | BCG |
| 6 weeks | DTP-Hep B 1, OPV 1 |
| 10 weeks | DTP-Hep B 2, OPV 2 |
| 14 weeks | DTP-Hep B 3, OPV 3 |
| 9 months | Measles, Yellow Fever |

3.	Estimated Requirements of the Combined DTP-Hep B vaccine

For details see the annexed table. A considerable reduction in wastage rate was obtained in Abidjan with the combined preparation, from 25 % to 15 %. In the projections, we have used a similar progressive reduction of the wastage rates to achieve a 13 % wastage rate in 3 years. See the annexed table.

4.	Additional Requirements of the cold chain equipment

Côte d’Ivoire has in the recent past renewed and extended its entire cold chain with the financial assistance of KFW and the Government of Japan. In the near future no additional equipment will be needed. The issues at stake are now the maintenance and the renewal in seven years time, which will be addressed by the Interagency Coordinating Committee. A study of the cold chain conducted by Electrolux will be the basis for reflection on the issues of maintenance and write-off.

5.	Burden of disease-assessment on Hepatitis B

This year, AMP (Aide pour la Médecine Préventive) conducts an epidemiological study on the mother-to-child transmission of the Hepatitis B in Abidjan. It is a prospective epidemiological study, involving 5000 pairs of mother & child; the first inclusions in the study are planned for November 2000. The first study objective is to compare the immunization efficacy of two different Hepatitis B immunization schedules, one that will start with the first vaccination at birth and the second is the currently used Hepatitis B vaccination schedule starting at six weeks). The second study objective is to assess the disease burden of Hepatitis among pregnant women using of the serological markers for Hepatitis B. The study will last 18 months and is a comparative, prospective cohort study, conducted in several centers in Abidjan. The children will be followed until the age of 9 months. AMP collaborates frequently with WHO in the area of vaccination.

III.		Critical Issues

1.	Resource mobilization

The issue of resource mobilization and financing of the EPI is a topic of serious concern, which will be addressed by the ICC. Since 1992, a government budget-line exists for purchasing vaccines and injections materials and it has increased over the years. However, the budget-line depends on the financial assistance to the Côte d’Ivoire budget by the European Union.

There are certain elements to the solution of the EPI-financing.

- Government budget

The budget-line will be maintained on the same level in the coming years; it is secured. The Ministry of Health decides on the exact allocation for vaccines and injection-material; the Institut National d’Hygiène Publique, responsible for the EPI-purchases does the estimation.

|  | 1999 (F CFA)* | 2000 (F CFA) |
| --- | --- | --- |
| Vaccines & Injection materials | 1 303 900 000 | 1 390 000 000 |
| Recurrent Costs | 600 000 000 | 500 000 000 |

*1FF = 100 F CFA, 1 USD = 695 F CFA

It is important to note that the government allocation for EPI has increased in a period of a reducing government budget in general. The funds released by the contribution of GAVI to finance the DTP-Hep B vaccines will be added to the injection materials allocation. In the beginning, it will be difficult for Côte d’Ivoire to finance the complete changeover to using Auto Disabled syringes (AD syringes) for the EPI due to the increased cost. However, an increased allocation to the injection materials will enable Côte d’Ivoire to finance partly the required AD syringes-purchase.

b. 	European Union assistance to the benefit of EPI

The European Union budget assistance in EPI is assured until 2010, according to the ‘convention ACP-CEE du VIII FED’ concerning non-targeted assistance.

- Highly Indebted Poor Countries II (HIPC)

Côte d’Ivoire is eligible for inclusion in HIPC-initiative, and the EPI has been chosen as a priority program to benefit of the funds made available through the debt-relief. One of the criteria for eligibility is increasing the EPI-routine vaccination coverage to at least 70 % in 2001. The negotiations are ongoing and will probably be concluded in 2001.

- Contribution of Agencies

In the recent past, KFW (German agency for financial development aid) and the Japanese Government have financed an almost complete renewal of the cold chain and made a considerable investment in the EPI logistics. UNICEF and WHO have reinforced their financial contributions and technical assistance in the field of EPI, and will continue to do as active members of GAVI. It is to be expected that the GAVI initiative will attract other agencies and donors to participate in reinforcing the EPI either with financial or technical assistance.

2.	Polio eradication

Since 1997, Côte d’Ivoire has been committed to the Polio eradication by implementing annually NIDs with an increasing success. Three months after a coup d’état in December 1999, the country honored its commitment to the Polio eradication by conducting the NIDs 2000 as planned with a 109 % coverage-rate. In October/November 2000, Côte d’Ivoire will participate in the synchronized NIDs for West Africa; thus this year, it conducts two rounds of NIDs plus the mopping campaigns last May. The effort of organizing annually two NID-rounds will be sustained until 2005 in order to meet the WHO standards for the Polio eradication certification. (Annex 1 Document de Planification des Journées de Vaccination Synchronisées)

In 1998, the WHO has accredited the ‘Laboratoire de Virologie l’Institut Pasteur’, Abidjan as the reference laboratory for the sub-region. The quality control by the laboratory has improved the AFP surveillance; for 12 months the wild virus has not been detected in the whole of national territory and the AFP-rate is 1,3 among 100 000 children less then 15 years of age.

3.	Injection Safety Strategy

Côte d’Ivoire subscribed to the Yamoussoukro International declaration for Injection Safety (1994); the national policy was finalized in 1995. Since then, the country assured the single use syringes for all injections including the EPI over the whole national territory. The Ministry of Health is collaborating with the KFW and WHO to finalize the strategy for disposal of medical waste, of which the EPI waste is a component. GAVI-funding will enable the country to make the complete changeover to AD-syringes.

4.	Advocacy and IEC concerning the routine EPI

In the Ministry of Health, a group of IEC-experts is responsible for advocacy and social mobilization, headed by the special advisor to the Minister of Health for public relations and communication. The group has received training from WHO and UNICEF, concerning social mobilization for EPI. The Minister of Heath welcomes technical assistance to elaborate a comprehensive national strategy for Social Mobilization and IEC.

## IV.	Policy Issues raised during the Proposal Review process

1.	Buffer stock and wastage rates

The annexed table shows that the issue of the buffer stock and gradual reduction of wastage rates have been taken into account.

2.	AD syringes and safety boxes

Côte d’Ivoire is already applying the ‘bundling approach’ according to the WHO/UNICEF/UNFPA Joint Statement on Safety of Immunization Injections since 1995 and will continue the same strategy after the full scale introduction of the AD syringes.

3.	Replacement funding

Concerning the replacement funding, Côte d’Ivoire will continue financing its purchase of vaccines and injections materials. Funds will be gradually freed up as the DTP vaccine, currently purchased by the government is progressively replaced by the combined DTP-Hep B vaccine purchased by GAVI. The government can use the available funds to reinforce the injection safety measures and can gradually finance the purchase of the AD syringes.

4.	DTP Drop-out rates

In Côte d’Ivoire, the DTP drop-out rates have gradually decreased from 39 % in 1995 to 25 % in 1999.

DTP Drop-out rates from 1995-1999

| Indicators | 1995 | 1996 | 1997 | 1998 | 1999 | Average |
| --- | --- | --- | --- | --- | --- | --- |
| DTP 1 in % | 66 | 78 | 92 | 82 | 77 | 79 |
| DTP 3 in % | 41 | 55 | 70 | 64 | 60 | 58 |
| Drop-out rate | 39 | 29 | 24 | 23 | 25 | 28 |

The effort to reduce the DTP drop-out rates will be reinforced. Côte d’Ivoire has been able to increase considerably its national immunization coverage in the period from 1995 to 1997 without additional funding. During a recent training for EPI officer in Douala, Cameroon, the Côte d’Ivoire EPI was presented as a case study in improving EPI services.

Please submit hard copy documents with an additional electronic copy wherever possible