Rev 2.

November 2000

The Government of

LIBERIA

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from one or both sub-accounts - immunization services and/or new and underused vaccines. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

Liberia is applying for support from the new and underused vaccines sub-account in order to incorporate Yellow Fever vaccine into the routine immunization services. Yellow fever is endemic in Liberia and over the last five years, four outbreaks have been confirmed. Between July and December 2000, two outbreaks of Yellow fever were confirmed; one in Grand Cape Mount in August and the other in Rivercess county in December. The mass campaigns conducted following the confirmation of outbreaks since 1995 have reached close to 1,500,000 persons protecting the population in the highest risk counties aged above 6 months. Those children aged below 6 months and those born after the campaigns were conducted were left unprotected and remain susceptible. The inclusion of Yellow fever vaccine into routine immunization services will cover this segment of the population and will greatly reduce the risk of the localized “jungle” Yellow fever outbreaks transforming into explosive “urban” outbreaks.

Efforts undertaken to improve routine EPI since the end of the war are beginning to bear fruit. In 1999 34,082 children aged below 1 year received three doses of DPT while in 2000 this number rose to 81,448. The improvement in the delivery of routine immunization services has not been homogenous across all counties in the country and the performance in some counties remains very poor.

This proposal seeks support for the administration of one dose of Yellow fever vaccine to children aged 9 months during routine immunization contact. During the first year after inclusion into routine immunization (2001-2002), it is expected that 63,464 children (40% of surviving infants cohort) will be vaccinated with Yellow fever vaccine in 2001 and by 2005, 174,305 children (80% of surviving cohort) will be vaccinated against Yellow fever.

The required doses of Yellow fever vaccine over the next five years are 105,509 doses (2001), 102,833 doses (2002), 153,011 doses (2003), 159,080 doses (2004) and 155,567 doses (2005). Government will provide 5%, 10% and 15% of total Yellow fever vaccine requirements in 2003, 2004 and 2005 respectively. The 10-dose Yellow fever vaccine vial is preferred as this is expected to be associated with lower vaccine wastage rates. All the Yellow fever vaccine obtained from GAVI will be used solely for routine immunization and not for outbreak control. The Government of Liberia in partnership with WHO and MSF is building up contingency stock of Yellow fever vaccine to be used in any event of outbreaks.

The technical sub-committee of the ICC drafted this proposal and this was reviewed and discussed extensively by the ICC before endorsement and submission to GAVI.

# Signatures of the Government

The Government of ……LIBERIA…………….. commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Dr. Peter S. Coleman

Title:	…MINISTER OF HEALTH AND SOCIAL WELFARE...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual. (Guidelines on Country Proposal # 2.) :

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health and Social Welfare (MOHSW) |  |  |
| United Nations Children’s Fund |  |  |
| World Health Organization |  |  |
| United States Agency for International Development |  |  |
| National Drug Service |  |  |
| Rotary Clubs of Liberia |  |  |
| World Vision International (Chair Health Sector NGOs) |  |  |
| OXFAM |  |  |
| Ministry of Internal Affairs |  |  |
| Ministry of Information, Culture and Tourism |  |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name :Dr. Abebu B. S. Hiedala………	Title/Address :EPI/NIDS/Surveillance National Coordinator

Tel.No. (231) 226-229……….   		            Deputy Chief Medical Officer (Preventive

Fax No. (231) 227367/ 226208. 		            	Services, Ministry of Health and Social

E-mail :……………………………                         Welfare………………….

Alternative address :

Name : Mrs. Cefanee Kesselly…		Title/Address : EPI Director, Ministry of Health

Tel.No. : (231) 226-229…….   		            And Social Welfare, Liberia.

Fax No. :(231) 227367……. . 		            ………………………………..

E-mail :……………………………             ……………………………….

- Immunization-related fact sheet

| Table 1 : Basic facts (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 2,666,000 | GNP per capita | US$ 242.00 |
| Surviving Infants* | 147,540 | Infant mortality rate | 134/ 1000 |
| Percentage of GDP allocated to Health | 3.0% | Percentage of Government expenditure for Health Care | 5.1% |

* Surviving infants = Infants surviving the first 12 months of life

Table 2: Immunization coverage and disease burden trends as per annual reporting to WHO/UNICEF

| ### Trends of immunization coverage ### by 12 months of age |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported (1) |  | Survey (2) |  |  |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  |  | 1998 | 1999 | 1998 | Age group | 1999 | Age group |  | 1998 | 1999 | 1998 | 1999 |
| BCG |  | 28% | 42.6% | N/A | N/A | N/A | N/A | Tuberculosis | 2356 | 1756 | N/A | 0.014 |
| DTP | DTP1 | 46% | 62% | N/A | N/A | N/A | N/A | Diphtheria | N/A | N/A | N/A | N/A |
|  | DTP3 | 19% | 23.1% | N/A | N/A | N/A | N/A | Pertussis | 1,114 | 394 | 0 | 0 |
|  | [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 72% | 63% | N/A | N/A | N/A | N/A |  |  |  |  |  |
| OPV3 |  | 19% | 24.8% | N/A | N/A | N/A | N/A | Polio | 44 | 29 | 0 | 0 |
| Measles |  | 31% | 34.9% | N/A | N/A | N/A | N/A | Measles | 1,436 | 1,679 | 0.129 | 0.139 |
| TT2+ Pregnant Women |  | 14% | 11% | N/A | N/A | N/A | N/A | NN Tetanus | 166 | 174 | 0.423 | 0.415 |
| Hib |  | N/A | N/A | N/A | N/A | N/A | N/A | Hib | N/A | N/A | N/A | N/A |
| Yellow Fever |  | N/A | N/A | N/A | N/A | N/A | N/A | Yellow fever | N/A | N/A | N/A | N/A |
| hepB |  | N/A | N/A | N/A | N/A | N/A | N/A | hepB seroprevalence (if available) | N/A | N/A | N/A | N/A |

- The source of these reports is : …Routine immunization and surveillance returns from health facilities

- These data are collected from the following surveys : ……………………………………………………………………………………………………………………………………………………………………………………

Summary of health system development status :

Liberia embraced the tenets of Primary Health Care in the late 1970s following the Altma Ata conference.  By the early 1980s the public health system was coordinated by a centralized Ministry of Health and Social Welfare which was responsible for formulating health policy, training health workers and providing technical oversight and supervision over health activities. County health services headed by medical directors were responsible for the provision of curative and preventive services at the county level and were answerable to the Ministry of Health and Social Welfare.

Prior to the civil war, the health service infrastructure was characterized as a pyramid of referral institutions, from village health teams, rural health posts and health centres, county hospitals to the tertiary national referral JFK Medical centre at the top of the pyramid.

The seven year civil crisis dealt a severe blow to the national health system. Prior to 1990 access to health services was around 35% but this has now been reduced to less than 10%. Reduction in the number of functional health facilities as a result of physical destruction of health facilities, shortage of trained health workers and lack of drugs and essential medical supplies are a legacy of the civil crisis that remain to this day.

In July 2000 the Ministry of Health and Social Welfare conducted a National Health Policy Conference to develop a framework for health reform in the new millennium and thereby strength the national health system.

The revised national health policy thrusts for the new millennium reached at this milestone conference in the development of Liberia’s health system include:

- Prioritising primary health care strategies and the use of the Bamako initiative to increase access to services and reduce the burden of diseases

- Transfer responsibility and authority for planning, managing health services to the operation level i.e counties, districts and communities

- Nurture and strengthen partnerships for health development and ensure that the efforts of partners complement each other

- Generation of Political will needed to provide the resources required for effective implementation of health and social welfare programs

Supporting documents:  (only copies of relevant pages are attached)

| - Overall government health policies and strategies | Document number……1…….. |
| --- | --- |
| - Structure of the government health services and how it relates to immunization services (with an organisational chart) | Document number……1 (pg 49) |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) and their impact on immunization services | Document number1 (pg35-40) |
| - Government policies and practices on private sector participation, as it relates to immunization services | Document number…2…….. |

# 4. Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services in the country, are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC. (Guidelines on Country Proposal # 4.1.)

- Name of the ICC…Inter-agency Coordinating Committee for the Strengthening of Immunization in Liberia

- Date of constitution of the current ICC  …June 1998………………………………………………

- Organisational structure (e.g., sub-committee, stand alone) …ICC with technical and social mobilization sub-committees….

- Frequency of meetings  ……Monthly………………………………………………………

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Hon. Minister of Health and Social Welfare, Republic of Liberia | Peter S. Coleman MD, MSc, FWACS |
| Secretary | EPI/NIDS/Surveillance National Coordinator/Deputy Chief Medical Officer (Preventive Services) | Abebu B. S. Hiedala MD, MPH |
| Members | - Chief Medical Officer, Republic of Liberia - WHO Representative to Liberia - UNICEF Representative to Liberia - Director, USAID-Liberia - Coordinator, Rotary Liberia - Health Coordinator, OXFAM - Country Representative, World Vision International - Ministry of Internal Affairs - Ministry of Information, Culture and Tourism - National Drug Service | - Dr. Nathaniel S. Bartee - Dr. Andre Ndikuyeze MD, MPH, PhD - Mrs Scholastica Kimaryo - Mr. Rudolph Thomas - Mr Eugene Cooper - Dr Yusupha Ceesay - Mr Jonas Njelango - Mr. Amadu Kiawu - Amb Juli Endee Tarpeh - Mr. Raymond Jallah Jr. |

- Functional relationships of the ICC with other institutions in health sector :

Ministry of Health and Social Welfare

ICC                                                Technical Assistance

Financial Assistance

Support to Policy development,

Advocacy, resource mob…

County Heath Services and partners

Health training institutions

Health research organizations

National Referral Health Centres

Health facilities-

- Public,

- Private-not-for-profit,

- Private-for-profit

- NGO/PVO

- Major functions and responsibilities of the ICC:

- To foster solid partnerships by coordinating all inputs and resources from inside and outside the country in order to maximize resources for the good of the child.

- To review EPI policy and strategy

- To deliberate EPI technical, social mobilization and educational issues

- To review and endorse EPI/NIDS/AFP workplans and budgets

- To mobilize resources from within the country and externally for use by EPI Programme.

- To enhance transparency and acountability by reviewing use of funds and other resources at regular intervals.

- To strengthen management and authority of the national EPI programme

- To support and encourage information sharing and feedback at all levels of implementation and among all partners within and outside the country.

- Three major strategies to enhance ICC’s role and functions in the next 12 months:

- ICC to play a more direct role in monitoring and evaluating performance of immunization services e.g. ICC will participate in a mid-year review workshop with all County Health teams

- Budget line to support the involvement of the ICC in field supervision and monitoring visits has been included in the 2001 National EPI Plan of Action.

- ICC members will be asked to serve in specialized sub-committees/working groups (where the ICC member has comparative advantage) to be established to tackle challenging areas such as developing a sustainable financing mechanism for immunization services in Liberia.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal:

- Yellow fever vaccine wastage rate by county

- Yellow fever vaccination coverage by county

- Number of counties reporting and investigating at least one case of suspected Yellow fever per year

Attached are the supporting documents :

| - ICC’s workplan of next 12 months | Document number..3… |
| --- | --- |
| - Terms of reference of the ICC | Document number…4…. |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number…5…. |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal. (Guidelines on Country Proposal # 4.2.)

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| STRENTHENING ROUTINE IMMUNIZATION AS THE FOUNDATION FOR POLIO ERADICATION FROM LIBERIA : BASELINE ASSESSMENT REPORT | - Ministry of Health and Social Welfare - UNICEF - WHO | December 1999 |

- The three major strengths identified in the assessments :

- High level of political commitment and goodwill towards immunization at all levels. A functional Inter-agency coordinating committee at national level met regularly and was chaired by the Minister of Health.

- There was widespread use of auto-disable injection technology for immunization and this was a plus for immunization safety.

- The institution of the Polio eradication initiative in 1998 was accompanied by a massive investment in new cold chain equipment which resulted in all counties in the county having sufficient cold chain capacity.

- The three major problems identified in the assessments :

- Poor planning capacity at all levels

- EPI service providers insufficiently trained and poorly motivated

- Inadequate EPI monitoring system and supportive supervision of EPI activities at all levels

- The three major recommendations in the assessments :

- Micro-planning sessions to improve management and planning capacity at county, district and health facility level.

- Training and intensive supportive supervision of EPI service providers and institution of performance based incentive and motivation enhancement bundles.

- Strengthening of EPI information systems including setting targets and monitoring indicators down to district level

- Attached is a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number…6.. |
| --- | --- |
| a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number…7.. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Title of the assessment | Month/Year |
| --- | --- |
| Assessment of different vaccination strategies (pulse catch-up mini-campaigns, routine static and outreach vaccination delivery) | Ongoing (December 2000-Mar 2001) |
| Assessment of the comparative advantage of different energy sources of cold chain: Solar versus kerosene operated | April 2001 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan. (Guidelines on Country Proposal # 4.3)

| - Attached is a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…8…. |
| --- | --- |

| #### Table 3 : Vaccination schedule with traditional and new vaccines (add/correct/fill in as appropriate) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AGE | Visit | Traditional antigens |  |  |  | New vaccines |  |  |
| Birth | 1 | BCG | OPV0 |  |  |  |  |  |
| 6 weeks | 2 |  | OPV1 | DTP1 |  |  |  |  |
| 10 weeks | 3 |  | OPV2 | DTP2 |  |  |  |  |
| 14 weeks | 4 |  | OPV3 | DTP3 |  |  |  |  |
| 9 months | 5 |  |  |  | Measles | Yellow Fever |  |  |

- Table 4.1 : Baseline and annual targets

|  | Baseline | Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| # of births | 170,370 | 176,674 | 183,211 | 189,990 | 197,020 | 204,309 | 211,869 |
| # of infants’ deaths | 22,830 | 23,674 | 24,550 | 25,459 | 26,401 | 27,377 | 28,390 |
| Surviving infants | 147,540 | 153,000 | 158,661 | 164,531 | 170,619 | 176,932 | 183,479 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 38.9% | 30% | 20% | 10% | 7.5% | 5% | 2.5% |
| Children vaccinated with DTP3 * | 34,082 | 76,500 | 95,197 | 115,172 | 136,495 | 159,239 | 174,305 |
| Children vaccinated with*: (insert new vaccine other than yellow fever) |  |  |  |  |  |  |  |
| Children vaccinated with*: (insert new vaccine other than yellow fever) |  |  |  |  |  |  |  |
| Children vaccinated with Measles ** | 51,491 | 76,500 | 95,197 | 115,172 | 136,495 | 159,239 | 174,305 |
| Children vaccinated with yellow fever ** | N/A | N/A | 63,464 | 82,266 | 136,495 | 159,239 | 174,305 |
| * While vaccinations with combination vaccines phase in, those with DTP3 only are expected to phase out ** Only complete if applying for yellow fever vaccine |  |  |  |  |  |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

- Reducing drop out rates through improving the management of EPI logistics (vaccines, kerosene for cold chain equipment), quality micro-planning down to district level, health worker training and regular supportive supervision.

- Information, education and communication strategies focussing on health workers and key community contacts who would encourage parents/caretakers to ensure that children complete the entire vaccination schedule.

- Increasing access to immunization services through the implementation of outreach services and localized “multi-antigen catch up campaigns” in some areas.

- Quarterly monitoring of performance at county and district level that would allow timely institution of corrective measures and more aggressive interventions where performance remains below targets.

- Summary of the major action points and timeframe for reduction of vaccines wastage rate :

- Operationalize the multi-dose vial policy that is already incorporated in Liberia’s national EPI Policy through health worker training and strengthened supportive supervision: October 2000-March 2001

- Intensive monitoring of vaccine utilization and wastage rates at all levels and all health facilities and use this to identify counties and service providers that need more supportive supervision and refresher training.: September 2000-Ongoing

- Ensure adequate vaccine management including accurate calculation of needs, timely forecasting and reasonable delivery schedule. August 2000- Ongoing

Table 4.2 : Estimate of annual DTP wastage rates

|  | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP wastage rate | 95% | 75% | 25% | 20% | 15% | 10% | 5% |

- Summary of the safe immunization plan (Guidelines on Country Proposal # 3.):

- Adoption of auto-disable injection technology, which presents the lowest risk of person-to-person transmission of blood-borne pathogens, for all immunization injections by December 2001.

- The use of puncture proof ‘safety boxes’ for collecting and disposal of all used needles and syringes and other injection materials to reduce risk to health staff and other members of public.

- Training of health staff to update knowledge and skills to make sure that their behaviour is consistent with current best practice.

- Ensuring adequate supplies at all levels of A-D syringes and safety boxes provided with good quality vaccines i.e. ‘safe immunization bundle’

- Disposal and destruction of waste and final containment.

- Development and application of monitoring tools for all above aspects of safe immunization injections

- Documentation of guidelines for adverse events following immunization (AEFI) surveillance

- Piloting and phased introduction of AEFI surveillance (this was began in one county i.e Grand Bassa in January 2001 and is to be extended to all counties).

| Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number..10…. |
| --- | --- |

- Constraints and planning for Polio Eradication Initiative (Guidelines on Country Proposal # 2.):

- High operational costs of Polio eradication National Immunization days due to high fuel costs to run generators to support cold chain as there is no national grid, high transport costs due to very deplorable road conditions….etc

- Poor access to several areas and communities due to poor road conditions especially during the rainy season. This is especially bad for four counties in the South Eastern Part of the country (Maryland, Grand Kru, Sinoe and Grand Gedeh.

- Inaccessibility to target children in Lofa where there is currently a civil conflict. Prior to the onset of full fledged fighting in July 2000 there had been recurrent rebel incursions into the area and this poor security had compromised the quality and coverage of four rounds of intensified NIDs conducted there between January and May 2000. During the 1999 NIDS, target age children vaccinated in Lofa county accounted for 22% of the entire number of target age children vaccinated.

- In October and November 2000, synchronized NIDs are scheduled to be conducted in all West African and some central African Countries. Because of political hostilities currently existing between Liberia and Guinea and Sierra Leone and fighting in the border areas of these countries, the chances of conducting quality NIDs and cross border immunization activities in these areas are very slim.

- Seven year civil crisis resulted in devastation of the national economy and this has led to a nearly total reliance on donor funding to support Polio eradication. If this funding is not sustained, the gains made so far will be lost very rapidly.

# New and under-used vaccines

Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines (Guidelines on Country Proposal # 4.4.).

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc…in relation to the current experience with new and under-used vaccines :

No new vaccine has been introduced into routine immunization services in Liberia since the inception of EPI in 1978. However as a result of Yellow fever outbreak confirmation in several counties, Yellow fever outbreak campaigns have been performed. In some counties (Rivercess-Dec 2000; Sinoe-Jan-2001) where the performance of routine immunization was found to be very poor, the concurrent administration of other antigens (Measles, DPT, OPV, TT) was encouraged as part of the Yellow fever vaccination campaigns.

During these integrated vaccination campaigns, health workers underwent training in the techniques of Yellow fever vaccine administration and they rapidly gained sufficient competencies in this. Cold chain storage capacity was sufficient as in 1998 massive infusion of cold chain equipment (freezers, cold boxes and vaccine carriers) were provided by WHO and UNICEF for the Polio eradication initiative.

Yellow fever vaccine wastage rates during the “integrated mass campaigns” conducted in 2000 and 2001 ranged from 7.5-15%.

- Required number of doses and presentations of requested, first preference, new and under-used vaccines

- (For each one of the requested, first preference new and under-used vaccine, please use provided formulas; see guidelines # 5.2)

Table 5.1: Estimated number of doses  of  Yellow Fever vaccine (specify for one presentation only) : “10-dose Yellow fever vaccine vial”

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) | 63,464 | 82,266 | 136,495 | 159,239 | 174,305 |
| B | Number of doses per vaccinated child | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate in percentage | 25% | 20% | 15% | 10% | 5% |
| D | Wastage factor [ = 100 / (100-C) ] | 1.33 | 1.25 | 1.18 | 1.11 | 1.05 |
| E | Buffer stock factor for vaccines | 1.25 | 1 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] | 105,509 | 102,833 | 161,064 | 176,755 | 183,020 |
| G | Percentage of vaccines requested from the Fund (%) | 100% | 100% | 95% | 90% | 85% |
| H | Number of doses requested from the Fund [ = F x G / 100 ] | 105,509 | 102,833 | 153,011 | 159,080 | 155,567 |
| I | Number of doses per vial | 10 | 10 | 10 | 10 | 10 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] | 83,534 | 86,626 | 136,543 | 150,911 | 156,012 |
| L | Reconstitution syringes [= H / I ] | 10,551 | 10,283 | 15,301 | 15,908 | 15,557 |
| M | Total number of syringes requested from the Fund [ = J + L ] | 94,085 | 96,909 | 151,844 | 166,819 | 171,569 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] | 941 | 969 | 1,518 | 1,668 | 1,716 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for hep B and Hib differ from DTP3, explanation of the difference should be provided.

Table 5.2 : Estimated number of doses of  …….. vaccine (specify for the other presentation only if any other presentation of the same vaccine is required) :

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) |  |  |  |  |  |
| B | Number of doses per vaccinated child |  |  |  |  |  |
| C | Estimated wastage rate in percentage |  |  |  |  |  |
| D | Wastage factor [ = 100 / (100-C) ] |  |  |  |  |  |
| E | Buffer stock factor for vaccines |  |  |  |  |  |
| F | Total vaccine doses needed [= A x B x D x E] |  |  |  |  |  |
| G | Percentage of vaccines requested from the Fund (%) |  |  |  |  |  |
| H | Number of doses requested from the Fund [ = F x G / 100 ] |  |  |  |  |  |
| I | Number of doses per vial |  |  |  |  |  |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] |  |  |  |  |  |
| L | Reconstitution syringes [= H / I ] |  |  |  |  |  |
| M | Total number of syringes requested from the Fund [ = J + L ] |  |  |  |  |  |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] |  |  |  |  |  |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for hep B and Hib differ from DTP3, explanation of the difference should be provided.

(Add any other table 5.3, 5.4…as necessary to calculate required doses of different vaccines in different presentations)

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

The increased cold chain storage requirements at national level following the inclusion of 10-dose Yellow fever vaccine is 633 litres (assuming that the entire years supply arrived in one shipment). The current cold chain capacity at the national level is sufficient to meet this amount. The cold chain equipment at national level is nearing the end of its life expectancy as most of the freezers are > 10 years old. National cold chain plan allows for replacement of cold chain equipment at the national level in 2002. At county level, cold chain capacity is sufficient to meet the increased needs of Yellow fever. 229 of the 276 functioning health facilities in the country have sufficient cold chain storage in the form of kerosene operated refrigerators and efforts are underway to mobilize additional refrigerators before end of 2001.

If GAVI approves this proposal, it is envisaged that Yellow fever vaccine will not be available for at least 6 months. This period is to be used to train health workers, update training, vaccination record and social mobilization materials.

Improved EPI logistics management as well as targeted social mobilization messages encouraging parents to ensure that their children complete vaccination schedule are the mainstay for reducing vaccine drop out rates. Vaccine wastage rates will be minimized by calculating forecasts and needs down to district level and monthly monitoring of vaccine stocks and wastage rates down to district level. The monthly monitoring will allow timely detection of areas with unacceptably high wastage so that appropriate corrective measures can be instituted.

- Required number of doses and presentations of requested, second preference, new and under-used vaccines (please use provided formulas) “ 20-dose Yellow Fever vial”

|  |  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Actual number of children to receive new vaccine* (match with targets in table 4.1) | 63,464 | 82,266 | 136,495 | 159,239 | 174,305 |
| B | Number of doses per vaccinated child | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate in percentage | 25% | 20% | 15% | 10% | 5% |
| D | Wastage factor [ = 100 / (100-C) ] | 1.33 | 1.25 | 1.18 | 1.11 | 1.05 |
| E | Buffer stock factor for vaccines | 1.25 | 1 | 1 | 1 | 1 |
| F | Total vaccine doses needed [= A x B x D x E] | 105,509 | 102,833 | 161,064 | 176,755 | 183,020 |
| G | Percentage of vaccines requested from the Fund (%) | 100% | 100% | 95% | 90% | 85% |
| H | Number of doses requested from the Fund [ = F x G / 100 ] | 105,509 | 102,833 | 153,011 | 159,080 | 155,567 |
| I | Number of doses per vial | 20 | 20 | 20 | 20 | 20 |
| J | AD syringes (Include 5% wastage rate) [= A x B x E x 1.053 x G / 100] | 83,534 | 86,626 | 136,543 | 150,911 | 156,012 |
| L | Reconstitution syringes [= H / I ] | 5,275 | 5,142 | 7,651 | 7,954 | 7,778 |
| M | Total number of syringes requested from the Fund [ = J + L ] | 88,809 | 91,768 | 144,194 | 158,865 | 163,790 |
| N | Total number of safety boxes requested from the Fund [ = M / 100 ] | 888 | 918 | 1,442 | 1,589 | 1,638 |

*Target estimates should be adjusted if a phased or mid-year introduction is intended. If targets for hep B and Hib differ from DTP3, explanation of the difference should be provided.

(Add any other table to the above format to calculate requested, second preference, doses of different vaccines in different presentations)

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Yellow Fever | Enhancing Yellow Fever Surveillance in Liberia | July-Dec 2000 | Yellow fever cases confirmed in 3 out of 9 counties covered. |

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number..9… |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, (Guidelines on Country Proposal # 4.3, 4.4, 5.) and that will be converted in a comprehensive «Resource Mobilisation Plan» by the time of the mid-term Review (Guidelines on Country Proposal # 6.1.):

In the immediate term the Government proposes to mobilize resources from:

- Community based contributions schemes along the principles of the Bamako Initiative: This source of funding is now being promoted and piloted in several areas. The aim of these schemes would be to increase mobilization of resources to pay a portion of the costs of the essential health basket which includes immunization at the first level of health delivery.

- At the county and national level, strategic partnerships with donors and partners involved in immunization services will be maintained and strengthened. UN agencies and bilateral agencies such as USAID, EU have contributed in recent years either directly or through health sector NGOS to financing of immunization services. This source of funding is to be strengthened through strict transparency and accountability of all resources received with the assistance of the ICC.

- Mobilization of resources in-country from national traditional partners has been successfully initiated by national ICC and county “ICC” for planning and implementing Polio NIDs. Business houses and firms not traditionally associated with health have been encouraged to contribute “in kind” to operational expenses and have contributed printed materials, fuel …etc. Adequate recognition and publicity of such donors at national and local level will be used to motivate and maintain these “non-traditional” partnerships.

- Improving Programme Efficiency:

  - Incentive schemes are also being designed to reward county health teams and EPI service delivery points who implement EPI efficiently with maximum utilization of limited resources available.

  - Operational research to determine the most cost-effective approach to cold chain in the context of Liberia as well as the different strategies of immunization delivery (static, outreach, pulse campaigns) in the hard to reach urban and rural is also expected to provide vital information that will help service providers adopt more efficient approaches to the use of limited available resources.

Strategies for long term resource mobilization for health services including immunization, as laid down in the national health policy include:

- Major reform of the Liberian budget process and allocative efficiency: There is significant political goodwill towards immunization services. As national economy performance improves advocacy will be employed at the highest level to ensure that contributions from the national budget to immunization services are increased.

- Major increase in external resource flows to Liberia: Efforts to develop relationship with the African Development Bank have began and it is hoped that this will soon bear fruit.

| - Tables of expenditure for 1999 and resource needs detailing the sources of funds are attached in Annex 1. | Document number .11. |
| --- | --- |

- List of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative): (the relevant documents are attached)

| Title | Partners |  |
| --- | --- | --- |
|  |  | Document number …… |
|  |  | Document number …… |
|  |  | Document number …… |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- Adoption of vaccine wastage reduction strategies as described under section 6.

- Integration of essential services at the service delivery points.

- Use of more cost-effective source of energy for cold chain e.g. solar power.

| - Summary of support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached : | Document number…… |
| --- | --- |

# Summary of requests to GAVI/GFCV

With reference to all points presented above, the Government of ..LIBERIA………

- being eligible for support from the Global Alliance for Vaccines and Immunization (GAVI) and the Global Funds for Children’s Vaccines (The Fund),

- considering that its DTP3 coverage for 1999 was …23…%  corresponding to …34,082.. number of children vaccinated with DTP3.

hereby requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government does hereby apply to receive support from the Fund :

YES

NO

- IMMUNIZATION SERVICES SUB-ACCOUNT (tick only one)

To fund the immunization services in year 2001 according to the number of additional children that are targeted to be immunized with DTP3 as presented in table 4.1, namely ………………  ( number of children ).

- (Only for countries seeking support from the Immunization Services sub-account)

- Transfer of funds from the immunization services sub-account will be by (tick only one):

| Government |  | A Partner agency (specify name) |  | An independent third party |  |
| --- | --- | --- | --- | --- | --- |

- Operational mechanism in place for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds (Guidelines on Country Proposal # 5.1.):

YES  S

NO

- NEW AND UNDER-USED VACCINES SUB-ACCOUNT (tick only one)

To supply the following vaccines :  (fill in only what is being requested from the Fund in line with tables 5.1, 5.2…)

| Table 6 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Presentation* | Starting month and year | Number of doses requested for first calendar year | Vaccines will also be requested for following years as described in tables 5.1, 5.2… |
| hep B | (1) |  |  |  |
|  | (2) |  |  |  |
| Hib | (1) |  |  |  |
|  | (2) |  |  |  |
| yellow fever | (2) 10-dose Vial | August 2001 | 105,509 |  |

* Insert types of presentation requested:	(1) 	Monovalent or combination

(2)	Number of doses per vial

- (Only for countries seeking support from New and Under-used Vaccines sub-account)

- Vaccines will be procured (tick only one) :

By UNICEF                            By GOVERNMENT

- (If vaccines is procured by the Government)

Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system (Guidelines on Country Proposal # 5.2.):

# Additional comments and recommendations from the ICC

The ICC appreciates the decision of the GAVI board that allowed countries with DPT3 coverage less than 50% to be able to apply for support for the inclusion of Yellow fever vaccine into routine immunization services.

This flexibility on the part of GAVI has served as a positive re-inforcement and re-invigorated the determination of the ICC in Liberia to ensure the reduction of the risk of Yellow fever through routine infant vaccination as well as oversee a general improvement in the quality and performance of all routine immunization services.

The ICC will ensure that, if support from GAVI for incorporation of Yellow fever vaccine into routine immunization is approved, this is done in a manner that will exert maximal benefit on the delivery of routine immunization services in the country. Opportunities to improve the quality of immunization service delivery, strengthen advocacy and programme communication as well as resource mobilization for immunization services will be seized.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | UNICEF | WHO | USAID | EU | Donor n.. 2 | Total Expend-iture in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - OPV |  |  |  | 200 |  |  |  |  | 200 |
|  | - DPT |  |  |  | 100 |  |  |  |  | 100 |
|  | - Measles |  |  |  | 80 |  |  |  |  | 80 |
|  | - BCG |  |  |  | 50 |  |  |  |  | 50 |
|  | - AD syringes |  |  |  | 180 |  |  |  |  | 180 |
|  | - 5 ml mixing sysringes |  |  |  | 20 |  |  |  |  | 20 |
| 1.2 | - Safety boxes |  |  |  | 10 |  |  |  |  | 10 |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Kerosene Refrigerators |  |  |  | 50 |  |  |  |  | 50 |
| 2.2 | - Solar Refrigerators |  |  |  | 60 |  |  |  |  | 60 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - EPI info system/Surveillance |  |  |  | 20 | 70 |  |  |  | 90 |
|  | - Training/capacity building |  |  |  | 20 | 40 |  |  |  | 60 |
|  | - Transport |  |  |  |  |  |  | 30 |  | 30 |
|  | - Social Mobilization/Communic |  |  |  |  | 40 |  |  |  | 40 |
|  | - EPI Programme Management | 75 |  |  |  | 20 |  |  |  | 95 |
| Total expenditure in 1999 |  | 75 |  |  | 790 | 170 |  | 30 |  | 1,065 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 1999 (Target: 600,000 < 5 Children) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | UNICEF | WHO | EU | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
|  | - OPV |  |  |  | 250 |  |  |  | 250 | 50 |
|  | - DPT |  |  |  | 150 |  |  |  | 150 | 50 |
|  | - Measles |  |  |  | 100 |  |  |  | 100 | 20 |
|  | - BCG |  |  |  | 100 |  |  |  | 100 | 50 |
|  | - AD syringes |  |  |  | 240 |  |  |  | 240 | 60 |
| 1.1 | - 5 ml mixing syringes |  |  |  | 33 |  |  |  | 33 | 13 |
| 1.2 | - Safety boxes |  |  |  | 25 |  |  |  | 25 | 15 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Kerosene Refrigerators |  |  |  | 320 |  |  |  | 320 | 270 |
| 2.2 | - Solar refrigerators |  |  |  | 200 |  |  |  | 200 | 0 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - EPI info system |  |  |  | 30 | 70 |  |  | 100 | 20 |
| 3.2 | - Training/capacity building |  |  |  | 30 | 30 |  |  | 60 | 0 |
| 3.3 | - Transport | 20 |  |  |  |  | 30 |  | 50 | 20 |
| 3.4 | - Social Mobilization |  |  |  | 20 | 20 |  |  | 40 | 0 |
| 3.5 | - Programme Management | 90 |  |  |  | 20 |  |  | 110 | 15 |
| Total commitment |  | 110 |  |  | 1,490 | 140 | 30 |  | 1,778 | 583 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number..1… |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organisational chart) | Document number. ..1(pg 49).. |
| - Ongoing or planned health reforms (e.g. decentralisation, integration of functions, changes in financing) as they impact immunization services | Document number ..1 (pg 35-40)… |
| - Government policies on private sector participation, as it relates to immunization services. | Document number..2… |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number..3. |
| - Terms of reference of the ICC | Document number..4… |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number..5… |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document number…6 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number…7 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…8 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - Safe injections Plan | Document number…9 Document number…10 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number..11 |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Document number N/A |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Document number N/A |

From the national consensus conducted in 1984

From the number of children in this age group actually vaccinated during 1999 Polio eradication NIDs

Children less than 12 months of age

The total number of children actually vaccinated with DPT3 by end of 2000 exceeded this target i.e. 81,448.

It is anticipated that it will take two years after introduction for the yellow fever coverage to match measles coverage.

Formula to calculate DTP vaccine Wastage Rate (in percentage): [ ( A – B ) / A ] x 100.                                                               Whereby : A = The number of DTP doses distributed for use according to the supply  records; B =  the number of DTP vaccinations

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The country would aim for a maximum wastage rates of 25% is set for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines is normally set at 25%. This is calculated by using a buffer stock factor of 1.25 that is applied only with the first stock of doses required to introduce the vaccination in any given geographic area. In case the introduction of the new vaccines is done in annual phases, the factor of 1.25 is applied only to the difference in numbers of annual targets of children. The factor is 1 for other following years. If these vaccine wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate in Section 6, and plan for wastage reduction should be included.

? A maximum wastage rate of AD syringes of 5% (= AD syringes wastage factor of 1.053) is applied to the total number of vaccine doses required, excluding the wastage of vaccines.

? Only for lyophilized vaccines : Yellow Fever and DTP-hepB-Hib

The preferred mechanism is payment directly to a Government account (Guidelines on Country Proposal # 5.1)

Please submit hard copy documents with an identical electronic copy whenever possible